## Small Project Screen
Small Project Screening
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Criterion | Click & Collect | Loyalty App | Warehouse Study | Evidence / rationale
Temporary and unique | Yes | Yes | Yes | Compare option briefs
Under six months | Yes | No | Yes | Duration from option brief
Limited budget and team | Yes | No | Yes | Budget/team thresholds
Limited dependencies | Yes | No | Yes | Interface count
No significant strategic impact | Yes | No | Review | Sponsor judgement
Screen result |  |  |  | Gate decision

## Weighted Selection
Weighted Option Selection
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Criterion | Weight | Click & Collect | Loyalty App | Warehouse Study | Scoring rationale
Value | 30% | 5 | 4 | 3 | 1 low to 5 high
Feasibility | 25% | 4 | 2 | 4 | Evidence from screen
Urgency | 15% | 5 | 3 | 2 | Sponsor priority
Risk | 15% | 4 | 2 | 3 | Higher score means lower exposure
Strategic fit | 15% | 4 | 5 | 3 | Relevant but proportionate
Weighted total |  |  |  |  | Highest passing option

## Decision
Sponsor Selection Decision
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Field | Response | Owner | Date
Recommended option | Click & Collect | Project team
Decision | Approve / Hold / Reject | Sponsor
Conditions |  | Sponsor
Next gate | Develop business case and charter | Project manager