## Stakeholder Register
Requirements Stakeholder Register
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Stakeholder | Role / interest | Influence | Impact | Requirement source | Workshop role | Owner
Sponsor | Investment and authority | High | High | Success and tolerances | Decision maker | Project Manager
Outlet Supervisor | Operational flow | Medium | High | Collection process | Subject expert | Operations Lead
Customer | Convenience and reliability | Low | High | Service outcomes | User voice | Business Analyst
POS Vendor | Interface feasibility | High | Medium | Technical constraints | Subject expert | Vendor Lead

## Workshop Log
Requirements Workshop Decision Log
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
ID | Need / conflict | Evidence | Decision required | Decision owner | Due date | Status
D-01 | Collection promise | Customer interviews | Set readiness target | Sponsor |  | Open
D-02 | Interface release window | Vendor plan | Confirm API freeze | IT Lead |  | Open

## Requirements
Testable Requirements and Acceptance
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Req ID | Source | Requirement | Priority | Deliverable | Acceptance method | Measure / threshold | Owner | Status
REQ-01 | Customer | Orders ready within promised collection window | Must | Outlet workflow | Timestamp sample | 90% within 10 minutes | Operations Lead | Draft
REQ-02 | Outlet Supervisor | Correct items are picked | Must | Picking process | Check sheet | At least 98% line accuracy | QA Lead | Draft