## Approach Canvas
Delivery Approach Tailoring Canvas
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Deliverable | Requirement uncertainty | Technical uncertainty | Feedback speed | Cost of change | Chosen approach | Rationale
POS interface | Low | Medium | Weekly | High | Predictive with test cycles | Stable interface; early integration
Outlet workflow | High | Low | Daily | Low | Adaptive | Rapid observation and feedback

## Quality Plan
Quality Management Plan
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Quality objective | Metric | Target | Collection method | Frequency | Owner | Response threshold
Ready on time | Ready-on-time rate | 90% | Timestamp check sheet | Daily | Operations Lead | Below 88%
Pick accuracy | Correct line rate | 98% | Sample inspection | Daily | QA Lead | Below 97%

## Definition of Done
Definition of Done
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Condition | Evidence | Approver | Applies to | Met? | Comments
Acceptance criteria passed | Test record | Business Owner | All deliverables | No
Current documentation stored | Versioned file | Project Manager | All deliverables | No

## Kanban Policy
Kanban Policies
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Column | Entry policy | Exit policy | WIP limit | Blocker threshold | Review cadence
Ready | Dependencies cleared | Owner pulls work | 8 | 1 day | Daily
In Progress | Owner and evidence defined | Peer review ready | 4 | 1 day | Daily
Review | Evidence attached | Accepted or returned | 3 | 2 days | Daily