## Capacity
Resource Capacity by Skill
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Role | Available person-days | Demand person-days | Gap | Critical skill? | Decision
Business Analyst | 6 | 12 |  | Yes | Resolve constraint
QA Lead | 10 | 8 |  | Yes | Available
Operations Lead | 8 | 8 |  | Yes | At capacity
Trainer | 6 | 6 |  | No | At capacity
Vendor Lead | 8 | 8 |  | Yes | At capacity

## Procurement Decision
Make or Buy Analysis
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Criterion | Weight | Internal score | Contract score | Rationale
Cost | 25% | 4 | 3 | 1 low to 5 high
Lead time | 25% | 2 | 5 | Constraint is immediate
Quality | 20% | 4 | 4 | Both require review
Interface knowledge | 15% | 5 | 3 | Internal advantage
Knowledge transfer | 15% | 5 | 2 | Contract needs handover
Weighted total |  |  |  | Compare with schedule impact

## Options
Resource Optimisation Options
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Option | Finish effect days | Incremental cost SGD | New risk | Feasible? | Recommendation rationale
Smoothing | 0 | 0 | Uses float | Yes
Levelling | 8 | 0 | Launch delay | Yes
Crashing | -6 | 9000 | Onboarding and quality | Yes
Fast tracking | -4 | 0 | Rework | Review