## EVM
Earned Value and Forecast
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Measure | Value | Formula / meaning | Interpretation
BAC | 162000 | Authorised measured budget | Input
PV | 108000 | Planned value at status date | Input
EV | 90000 | Earned value at status date | Input
AC | 105000 | Actual cost at status date | Input
SV |  | EV-PV | Negative adverse
CV |  | EV-AC | Negative adverse
SPI |  | EV/PV | Below 1 adverse
CPI |  | EV/AC | Below 1 adverse
EAC |  | BAC/CPI | Current efficiency continues
ETC |  | EAC-AC | Remaining forecast

## Status Report
Integrated Status Report
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Area | Threshold | Current evidence | Forecast | Cause | Action / owner | Decision needed
Schedule | SPI below 0.95 | SPI from EVM
Cost | CPI below 0.95 | CPI from EVM
Quality | Below 98% pick accuracy | Control chart
Risk | Exposure above tolerance | Risk register

## Issue Log
Issue Log
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
ID | Issue | Detected | Impact | Containment | Root cause | Resolution owner | Due | Status | Closure evidence
ISS-01 | Interface acceptance ownership unclear |  | Testing delay | Joint review | Decision-right gap | Project Manager |  | Open

## Change Log
Change Request and Impact
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
CR ID | Request | Reason | Scope impact | Schedule days | Cost SGD | Quality impact | Resource impact | Risk impact | Recommendation | Approver | Decision
CR-01 | Add loyalty points | Sponsor request | New deliverable | 15 | 24000 | More testing | Vendor and BA | Interface and adoption | Defer | Sponsor | Pending

## Decision Log
Decision Log
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
ID | Decision | Options | Rationale | Owner | Date | Records to update | Communicated to
DEC-01 |  | Approve / reject / defer / trade |  | Sponsor |  | RTM; WBS; schedule; budget; risk | Team and vendors