## Budget vs Actual Monthly - List
Project Budget - Monthly
| Start Date: | 2023-06-30 |  |  |  |  | versus Actual Cost |  |  |  |  | Budget Name: |  |  |  |  | ◄ Insert more columns to have more dates. You can also overwrite the dates and change them to weeks or days as you prefer.
# | Expenses | Type | 2023-06-30 | 2023-07-30 | 2023-08-30 | 2023-09-30 | 2023-10-30 | 2023-11-30 | 2023-12-30 | 2024-01-30 | 2024-02-29 | 2024-03-29 | 2024-04-29 | 2024-05-29 | 2024-06-29 | Total | ◄ Drag and copy across an existing column to ensure the formulas and formatting stay the same.
1 | [ expense name] | Budgeted | 5 | 3 | 3 | 3 | [9 empty] | 14
|  | Actual | 5 | 3 | 4 | 2 | [9 empty] | 14
2 | [ expense name] | Budgeted | 3 | 1 | 4 | [10 empty] | 8
|  | Actual | 3 | 4 | 4 | [10 empty] | 11
3 | [ expense name] | Budgeted | 3 | 2 | 2 | 1 | 10 | [8 empty] | 18
|  | Actual | 3 | 4 | 4 | 4 | 9 | [8 empty] | 24
4 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
5 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
6 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
7 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
8 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
9 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
10 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
11 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
12 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
13 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
14 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
15 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
16 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
17 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
18 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
19 | [ expense name] | Budgeted | [13 empty] | 0 | ◄ Insert more expenses by inserting more rows (two at a time)
|  | Actual | [13 empty] | 0 | ◄ Drag and copy two rows from above to copy the formulas and formatting to your new rows
20 | [ expense name] | Budgeted | [13 empty] | 0
|  | Actual | [13 empty] | 0
| Total Budget | Budgeted | 11 | 6 | 9 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
| Cumulative Budget | Budgeted | 11 | 17 | 26 | 30 | 40
| Total Actual Cost | Actual | 11 | 11 | 12 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
| Cumulative Cost | Actual | 11 | 22 | 34 | 40 | 49

## Budget vs Actual Weekly - List
Project Budget - Weekly
| Start Date: | 2023-06-30 |  |  |  |  | versus Actual Cost |  |  |  |  | Budget Name: | [45 empty] | ◄ Insert more columns to have more dates. You can also overwrite the dates and change them to weeks or days as you prefer.
# | Expenses | Type | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21 | 2023-07-28 | 2023-08-04 | 2023-08-11 | 2023-08-18 | 2023-08-25 | 2023-09-01 | 2023-09-08 | 2023-09-15 | 2023-09-22 | 2023-09-29 | 2023-10-06 | 2023-10-13 | 2023-10-20 | 2023-10-27 | 2023-11-03 | 2023-11-10 | 2023-11-17 | 2023-11-24 | 2023-12-01 | 2023-12-08 | 2023-12-15 | 2023-12-22 | 2023-12-29 | 2024-01-05 | 2024-01-12 | 2024-01-19 | 2024-01-26 | 2024-02-02 | 2024-02-09 | 2024-02-16 | 2024-02-23 | 2024-03-01 | 2024-03-08 | 2024-03-15 | 2024-03-22 | 2024-03-29 | 2024-04-05 | 2024-04-12 | 2024-04-19 | 2024-04-26 | 2024-05-03 | 2024-05-10 | 2024-05-17 | 2024-05-24 | 2024-05-31 | 2024-06-07 | 2024-06-14 | 2024-06-21 | 2024-06-28 | 2024-07-05 | Total | ◄ Drag and copy across an existing column to ensure the formulas and formatting stay the same.
1 | [ expense name] | Budgeted | 5 | 5 | 14 | 3 | [50 empty] | 27
|  | Actual | 5 | 7 | 16 | 2 | [50 empty] | 30
2 | [ expense name] | Budgeted | 3 | 1 | 4 | [51 empty] | 8
|  | Actual | 3 | 4 | 4 | [51 empty] | 11
3 | [ expense name] | Budgeted | 3 | 2 | 2 | 1 | 10 | [49 empty] | 18
|  | Actual | 3 | 4 | 4 | 4 | 9 | [49 empty] | 24
4 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
5 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
6 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
7 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
8 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
9 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
10 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
11 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
12 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
13 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
14 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
15 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
16 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
17 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
18 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
19 | [ expense name] | Budgeted | [54 empty] | 0 | ◄ Insert more expenses by inserting more rows (two at a time)
|  | Actual | [54 empty] | 0 | ◄ Drag and copy two rows from above to copy the formulas and formatting to your new rows
20 | [ expense name] | Budgeted | [54 empty] | 0
|  | Actual | [54 empty] | 0
| Total Budget | Budgeted | 11 | 8 | 20 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53
| Cumulative Budget | Budgeted | 11 | 19 | 39 | 43 | 53
| Total Actual Cost | Actual | 11 | 15 | 24 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
| Cumulative Cost | Actual | 11 | 26 | 50 | 56 | 65

## ©
Budget vs Actual Template
© 2024 David McLachlan
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
You may make archival copies and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
Do not delete this worksheet.
Limitation of Liability
This template and any related documentation are provided to you "as is." While every effort has been made to provide an outstanding product, without limiting the above you accept that this template may not meet your requirements, operate error free, or identify any or all errors or problems. This agreement does not affect any statutory rights you may have as a consumer.