## Acceptance Matrix
Deliverable Acceptance Matrix
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Req ID | Deliverable | Criterion | Evidence | Verifier | Approver | Status | Sign-off date
REQ-01 | Outlet workflow | 90% ready within 10 minutes | Timestamp test | QA Lead | Business Owner | Pending
REQ-02 | Picking process | 98% line accuracy | Check sheet | QA Lead | Business Owner | Pending

## Handover Checklist
Operational Handover
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Item | Operational owner | Evidence / location | Training complete? | Support level | Effective date | Accepted?
Outlet operations | Operations Lead | Current SOP | Yes | Business hours |  | No
System support | Support Lead | Runbook and contacts | Yes | P1-P3 |  | No
Data ownership | Business Owner | Data register | Yes | Monthly review |  | No

## Open Items
Open-Item Disposition
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
ID | Type | Description | Owner | Due | Disposition | Transferred to | Acceptance
OI-01 | Warranty | Confirm warranty start | Project Manager |  | Complete / transfer | Support Lead | Pending

## Lessons
Lessons Learned Register
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Theme | What happened | Cause | Impact | Recommendation | Future owner | Reusable where
Interface ownership | Acceptance delayed | RACI gap | Testing queue | Name one A at planning gate | PMO | Supplier projects

## Benefits Tracker
Benefits Realisation Tracker
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Benefit | Baseline | Target | Unit | Owner | Measure source | Review date | Actual | Status
Ready-on-time rate | 0.82 | 0.9 | % | Operations Lead | Timestamp sample |  | 0 | Not measured
Pick accuracy | 0.94 | 0.98 | % | QA Lead | Check sheet |  | 0 | Not measured

## Closure Gate
Closure Gate Decision
Source: supplied v17, PMP v16, Agile v9 and Project Management Templates Guide; adapted to HarbourHub Fresh v19.
Gate criterion | Evidence complete? | Open condition | Owner | Due | Sponsor decision
Deliverables accepted | No | Complete sign-off | Business Owner
Operations handover accepted | No | Support owner confirms | Support Lead
Contracts and records complete | No | Warranty date | Project Manager
Benefits ownership transferred | No | Review dates | Business Owner