Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

LEARNER GUIDE

For

Effective Project Management for Small Projects

TGS Ref No: TGS-2020505545

Conducted by

Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

Version 19.0

DOCUMENT VERSION CONTROL RECORD

| Version Number | Effective Date of Release | Summary of Included Changes | Author |
| --- | --- | --- | --- |
| 17.0 | 19 August 2026 | Legacy master trainer slide release used as the controlling syllabus. | Tertiary Infotech Academy |
| 18.0 | 19 August 2026 | Complete visual and instructional redesign; content enriched from the Agile and PMP references; seven connected tool-based activities and self-contained editable template packs added; LG and LP regenerated. | Dr Alfred Ang |
| 19.0 | 19 August 2026 | Expanded to the complete five-phase lifecycle and 200 substantive trainer slides; twelve connected tool-based activities, six new lifecycle workbooks, deeper reference-sourced guidance and an aspect-correct cover hero added; LG and LP regenerated. | Dr Alfred Ang |

TABLE OF CONTENTS

1. Course Overview	8

1.1 Learning Outcomes	8

1.2 Skills Framework Alignment	8

1.3 Running Case	9

1.4 Complete Project Lifecycle	9

1.5 Tool-Based Evidence	9

1.6 Supplied Reference Base	9

Topic 01 — Initiation of a Project	11

Why This Topic Matters	11

Core Concepts	11

Applied Guidance	11

Reference-Sourced Deep Dives	11

Project Work versus Operations	11

The Small-Project Qualification Test	12

From Output to Benefits	12

Project Selection Methods	12

Sponsor and Project Manager—Different Accountability	12

Business Documents at Initiation	12

A Charter That Can Govern	13

Assumption, Constraint, Dependency or Risk?	13

Lightweight Governance with Tolerances	13

Kickoff as an Alignment Decision	13

Activity 1 — Screen and Select the HarbourHub Pilot	14

Tool Files	14

Detailed Procedure	14

Acceptance Criteria	15

Debrief	15

Activity 2 — Authorise the Pilot and Run the Kickoff Gate	15

Tool Files	15

Detailed Procedure	15

Acceptance Criteria	15

Debrief	15

Topic 02 — Develop a Project Plan	17

Why This Topic Matters	17

Core Concepts	17

Applied Guidance	17

Reference-Sourced Deep Dives	18

The Integrated Project Plan	18

Requirements Elicitation	18

Weak versus Testable Requirements	18

Prioritisation Choices	18

Traceability from Need to Evidence	18

Scope Statement Essentials	19

WBS Decomposition	19

WBS Dictionary—Why It Matters	19

Dependency Relationships	19

Critical Path Calculation	20

Estimating Methods	20

Cost Baseline and Reserves	20

Activity 3 — Discover Requirements and Map Acceptance Evidence	20

Tool Files	21

Detailed Procedure	21

Acceptance Criteria	21

Debrief	21

Activity 4 — Build the Scope Baseline with WBS and Dictionary	21

Tool Files	21

Detailed Procedure	21

Acceptance Criteria	21

Debrief	21

Activity 5 — Develop the Integrated Schedule and Cost Baseline	23

Tool Files	23

Detailed Procedure	23

Acceptance Criteria	24

Debrief	24

Topic 03 — Apply Methods and Tools to Drive a Project	25

Why This Topic Matters	25

Core Concepts	25

Applied Guidance	25

Reference-Sourced Deep Dives	25

Method versus Tool	25

Predictive, Adaptive and Hybrid	26

Direct and Manage Project Work	26

A Lean PMIS for a Small Project	26

Quality Planning, Assurance and Control	26

HarbourHub Quality-Cost Decision	27

Quality Tool Sequence	27

Common Cause versus Special Cause	27

Kanban Operating Policies	27

PDCA Improvement Loop	28

Manage Project Knowledge	28

Activity 6 — Tailor the Delivery Method and Quality Plan	28

Tool Files	28

Detailed Procedure	28

Acceptance Criteria	29

Debrief	29

Activity 10 — Diagnose the Pilot Quality Failure	29

Tool Files	29

Detailed Procedure	30

Acceptance Criteria	30

Debrief	30

Topic 04 — Manage Project Risk	31

Why This Topic Matters	31

Core Concepts	31

Applied Guidance	31

Reference-Sourced Deep Dives	31

Risk, Issue and Assumption	31

The Risk Management Cycle	32

Risk Breakdown Structure	32

Writing an Actionable Risk	32

Qualitative Risk Factors	32

HarbourHub Threat-Response Workshop	33

Opportunity Response Strategies	33

Response Architecture	33

Decision Tree and Sensitivity	33

Risk Review Agenda	34

Activity 7 — Build the Risk Register and Fund Responses	34

Tool Files	34

Detailed Procedure	34

Acceptance Criteria	35

Debrief	35

Topic 05 — Collaborate with Stakeholders	36

Why This Topic Matters	36

Core Concepts	36

Applied Guidance	36

Reference-Sourced Deep Dives	36

The Stakeholder Engagement Cycle	36

Stakeholder Register Fields	37

Stakeholder Mapping Lenses	37

Seven Salience Classes	37

Directions of Influence	37

Communication Model	38

Communication Methods	38

Stakeholder Engagement Levels	38

HarbourHub RACI Failure Test	38

Evidence-Based Escalation	39

Activity 8 — Align Stakeholders, Accountability and Communications	39

Tool Files	39

Detailed Procedure	39

Acceptance Criteria	40

Debrief	40

Topic 06 — Deploy Resources	41

Why This Topic Matters	41

Core Concepts	41

Applied Guidance	41

Reference-Sourced Deep Dives	41

Resource Management Plan	41

Organisation Structure and PM Authority	42

Role, Authority, Responsibility and Competence	42

Two-Week Capacity Worked Example	42

Acquire, Develop or Procure	42

Make-or-Buy Decision	43

Contract Type and Risk	43

HarbourHub Team-Stage Diagnostic	43

Conflict Approaches	43

HarbourHub Bottleneck Options	44

Team Performance Signals	44

Activity 9 — Deploy Resources and Resolve the Bottleneck	44

Tool Files	44

Detailed Procedure	45

Acceptance Criteria	45

Debrief	45

Topic 07 — Track Project Deliverables and Correct Misalignments	46

Why This Topic Matters	46

Core Concepts	46

Applied Guidance	46

Reference-Sourced Deep Dives	46

The Monitoring and Control Cycle	46

Data, Information and Reports	47

A Decision-Ready Status Report	47

Validate Scope versus Control Scope	47

Earned Value Building Blocks	47

Variance and Performance Indices	48

Forecasting with EAC	48

Issue Management	48

Loyalty-Points Change Worked Example	48

Three Types of Action	49

Control Across Knowledge Areas	49

Closure from Acceptance to Benefits	49

Activity 11 — Control Performance, Issues and Change	49

Tool Files	50

Detailed Procedure	50

Acceptance Criteria	50

Debrief	50

Activity 12 — Accept, Handover and Close the Project	50

Tool Files	50

Detailed Procedure	50

Acceptance Criteria	50

Debrief	50

Assessment Readiness	53

Glossary	53

# 1. Course Overview

This guide accompanies the visual trainer deck. Detailed procedures live here and in the self-contained activity folders; the PowerPoint intentionally contains only activity briefings and success criteria.

## 1.1 Learning Outcomes

LO1: Develop project scope and team to initiate the facilitation of a small project

LO2: Develop a realistic project plan based on the agreed project scope

LO3: Utilise appropriate methods and tools to track and drive a project

LO4: Identify, analyse and manage project risks

LO5: Collaborate effectively with project stakeholders

LO6: Deploy manpower, budget and other resources for efficient completion

LO7: Track project deliverables and correct misalignments through control and closeout

## 1.2 Skills Framework Alignment

| Code | Ability / Knowledge | Evidence |
| --- | --- | --- |
| A1 | Facilitate execution of small projects that are typically less than six months, with limited budget and interdependencies, and no significant strategic impact | Activities 1–2 |
| A2 | Implement realistic project plans based on project objectives and scope | Activities 3–5 |
| A3 | Utilise appropriate methods and tools to track and drive progress against plans and timelines | Activities 6 and 10 |
| A4 | Identify risks to project success and take appropriate actions to manage them | Activity 7 |
| A5 | Collaborate effectively with relevant internal and external stakeholders directly impacting the project | Activity 8 |
| A6 | Deploy manpower, financial budgets and relevant resources for efficient and effective completion | Activity 9 |
| A7 | Track deliverables against schedules, monitor costs, timescales and resources, and take basic corrective actions when misaligned | Activities 11–12 |
| K1 | Elements of a small project | Topic 1 |
| K2 | Requirements of a project plan | Topic 2 |
| K3 | Application of appropriate project management methodologies and tools | Topic 3 |
| K4 | Project risks | Topic 4 |
| K5 | Project stakeholder identification | Topic 5 |

## 1.3 Running Case

A 42-person Singapore specialty grocer will introduce online ordering and two-hour click-and-collect at three outlets. The five-month pilot has a S$180,000 cap, a core team of seven, two external suppliers, and limited dependencies. It is important to operations but does not change the company's overall strategy, making it a genuine small project.

Success target: Launch at all three outlets by 30 January 2027; process at least 120 pilot orders per week; keep pick accuracy at or above 98%; achieve customer satisfaction of at least 4.2/5; and remain within the approved S$180,000 budget.

## 1.4 Complete Project Lifecycle

| Phase | Purpose |
| --- | --- |
| Initiation | Select, justify, authorise and align the project |
| Planning | Integrate requirements, scope, schedule, cost, quality, resources and risk |
| Execution | Coordinate work, people, suppliers, engagement and knowledge |
| Monitoring and Controlling | Measure, forecast, resolve, change and correct |
| Closure | Accept, hand over, close obligations, learn and transfer benefits |

The phases overlap in practice. Integration, governance, stakeholder engagement, risk and quality continue across the lifecycle.

## 1.5 Tool-Based Evidence

Each activity folder includes relevant editable Office tools from the supplied source library plus purpose-built v19 lifecycle workbooks. Save completed tools with clear versioned filenames.

## 1.6 Supplied Reference Base

WSQ - Master Trainer Slides - Effective Project Management for Small Projects - v17.pptx

PMP-35-PDU-Training-Slides-v16.pptx

WSQ - Master Trainer Slides - Agile Project Management for Business - v9.0.pptx

Project Management templates guides.pdf

# Topic 01 — Initiation of a Project

Alignment: A1, K1 · LO1

Small-project fit · value · charter · scope · team · kickoff

## Why This Topic Matters

Use the small-project screen before tailoring governance. A five-month, S$180,000 pilot with seven people needs proportionate controls, but it still needs authorisation, baselines and decisions.

## Core Concepts

A project is temporary, unique and value-seeking; operations are ongoing and repetitive.

A small project is normally under six months, has a limited budget and team, few dependencies and no significant strategic impact.

The project manager integrates people, decisions and trade-offs; they do not merely maintain a schedule.

Success balances value and outcomes with scope, schedule, cost, quality, resources and risk.

Predictive, adaptive and hybrid approaches are choices driven by uncertainty, not labels of maturity.

The business case tests whether the project should exist; the charter authorises it to exist.

A useful charter names purpose, measurable success, scope boundaries, milestones, budget, major risks, team and sponsor authority.

A kickoff creates one shared picture of why, what, who, how and what happens next.

## Applied Guidance

Use the small-project screen before tailoring governance. A five-month, S$180,000 pilot with seven people needs proportionate controls, but it still needs authorisation, baselines and decisions.

Business value includes financial return, service improvement, risk reduction and capability. Do not combine these into one unsupported number.

A charter is strongest when it exposes what the project will not do and what the project manager may decide without returning to the sponsor.

For hybrid work, keep the charter and milestone gates while allowing short build-and-feedback cycles inside the delivery phase.

## Reference-Sourced Deep Dives

### Project Work versus Operations

| Dimension | Project | Operations |
| --- | --- | --- |
| Purpose | Create a unique result | Sustain recurring value |
| Duration | Temporary | Ongoing |
| Change | Introduces change | Stabilises and improves work |
| Closure | Formal endpoint | Continues until redesigned |

Decision insight: The same people may do both; the management system changes with the nature of the work.

### The Small-Project Qualification Test

Time: Normally less than six months.

Budget: Limited enough for proportionate governance.

Team: Small core team with clear interfaces.

Dependencies: Few and manageable.

Impact: No significant strategic or enterprise-wide effect.

Uncertainty: Can be bounded through short learning cycles.

### From Output to Benefits

1. Output — click-and-collect capability

2. Outcome — orders collected predictably

3. Benefit — revenue, satisfaction and efficiency

4. Measure — owner, baseline, target and date

Decision insight: Deliverables are produced by the project; benefits are usually realised with operations.

### Project Selection Methods

| Method | Best for | Watch for |
| --- | --- | --- |
| Cost-benefit | Financial viability | Unsupported benefit assumptions |
| Weighted scoring | Multiple criteria | Biased weights |
| Payback | Liquidity and speed | Ignores later value |
| Mandatory driver | Compliance or safety | Treating obligation as optional |

Decision insight: Use more than one lens when a small financial difference hides a major operational consequence.

### Sponsor and Project Manager—Different Accountability

Sponsor: Owns investment, priority and escalation.

Project manager: Integrates delivery and advises decisions.

Business owner: Owns adoption and benefits after handover.

Functional manager: Provides capability and resolves resource conflicts.

### Business Documents at Initiation

| Artefact | Decision supported | Owner |
| --- | --- | --- |
| Business case | Invest, hold or reject | Sponsor / business owner |
| Benefits plan | How value will be measured | Benefits owner |
| Project charter | Authorise and delegate | Sponsor with PM |
| Assumptions log | What must be validated | Project manager |

Decision insight: Keep documents brief, but never combine ownership so completely that accountability disappears.

### A Charter That Can Govern

Purpose: The problem and desired outcome.

Success: Measures, targets and dates.

Boundaries: Deliverables and exclusions.

Authority: Sponsor, PM and tolerances.

Frame: Milestones, budget and constraints.

Exposure: Assumptions, dependencies and high risks.

### Assumption, Constraint, Dependency or Risk?

| Type | Meaning | Example |
| --- | --- | --- |
| Assumption | Believed true for planning | Outlet Wi-Fi capacity is sufficient |
| Constraint | Fixed limitation | S$180,000 ceiling |
| Dependency | Reliance on other work | POS API access before integration |
| Risk | Uncertain event and impact | API access may be late |

Decision insight: Classify correctly because each item needs a different response.

### Lightweight Governance with Tolerances

1. Set — scope, time, cost and risk limits

2. Measure — compare current forecast

3. Act — PM decides within authority

4. Escalate — sponsor decides beyond tolerance

Decision insight: Authority without tolerances creates hesitation; tolerances without reporting create surprise.

### Kickoff as an Alignment Decision

1. Why — value and success

2. What — scope and exclusions

3. Who — roles and decisions

4. How — method, rhythm and evidence

5. Next — 48-hour actions and owners

Decision insight: A good kickoff reveals mismatched assumptions early enough to repair them cheaply.

## Activity 1 — Screen and Select the HarbourHub Pilot

| Field | Detail |
| --- | --- |
| Phase | Initiation |
| Duration | 35 minutes |
| Objective | Confirm that the proposed work is a viable small project and recommend the best option (A1, K1). |
| Tools | Small Project Screening, Multi-Criteria Selection and Cost-Benefit Analysis |
| Situation | HarbourHub Fresh has three competing improvement ideas: click-and-collect, a loyalty app, and a warehouse automation study. Only one can be funded this quarter. The sponsor needs a transparent selection decision and evidence that the selected work fits the small-project profile. |
| Output | A completed small-project screen, weighted option scorecard, cost-benefit check and sponsor-ready selection recommendation. |

### Tool Files

02 Cost Benefit Analysis.xlsx

01 Small Project Screening and Selection.xlsx

### Detailed Procedure

1. Read the three option briefs and separate desired outcomes from proposed solutions.

2. Apply the small-project screen: temporary, unique, under six months, limited budget/team and limited interdependencies.

3. Agree five weighted decision criteria covering value, feasibility, urgency, risk and strategic fit.

4. Score each option using evidence; record the rationale beside every score.

5. Open the cost-benefit template and test the preferred option using the S$180,000 ceiling and a 20% downside case.

6. Record assumptions, exclusions and one non-financial factor that the arithmetic does not capture.

7. Recommend approve for chartering, hold for more evidence, or reject; state the sponsor decision required.

### Acceptance Criteria

The selected option satisfies every small-project criterion, the weighted score reconciles, the financial downside is visible and the recommendation states a clear gate decision.

### Debrief

Selection prevents the team from efficiently delivering the wrong project.

Weights expose priorities; narrative rationale prevents false precision.

A selected idea is still not authorised work until the charter gate is passed.

## Activity 2 — Authorise the Pilot and Run the Kickoff Gate

| Field | Detail |
| --- | --- |
| Phase | Initiation |
| Duration | 45 minutes |
| Objective | Define scope, success, authority and team arrangements for an executable small-project start (A1, K1). |
| Tools | Business Case on a Page and Project Charter |
| Situation | The click-and-collect pilot has been selected, but Operations, Finance and the two vendors hold different assumptions about success, exclusions and decision authority. The sponsor will authorise delivery only after a concise gate review. |
| Output | A one-page business case, signed-ready charter, assumptions and constraints log, milestone frame, decision tolerances and kickoff action list. |

### Tool Files

05 Business Case on a Page.docx

08 Project Charter Template.xlsx

### Detailed Procedure

1. Transfer the selection rationale and downside assumptions from Activity 1 into the business case.

2. Define measurable outcomes, benefits owner and the date on which benefits will be reviewed.

3. Write in-scope deliverables and explicit exclusions; test each boundary with the sponsor scenario.

4. Set five-month milestone limits, the S$180,000 ceiling and quality/schedule tolerances.

5. Name the sponsor, project manager, core team and vendor interfaces; state the project manager's authority.

6. Record assumptions, constraints, dependencies and the top three high-level risks.

7. Run the sponsor gate: approve, approve with conditions, hold or reject; capture rationale and conditions.

8. Conduct a 15-minute kickoff covering why, what, who, how, decisions and the next 48-hour actions.

### Acceptance Criteria

The charter names one accountable sponsor, measurable success, explicit exclusions, decision tolerances and an unambiguous authorisation decision within the small-project constraints.

### Debrief

The business case justifies investment; the charter grants authority.

Decision tolerances make lightweight governance possible.

Kickoff converts signed paper into shared commitments and immediate action.

# Topic 02 — Develop a Project Plan

Alignment: A2, K2 · LO2

Requirements · scope baseline · WBS · network · schedule · budget

## Why This Topic Matters

Start requirements with the stakeholder need, then write acceptance evidence. Words such as easy, fast and user-friendly are not testable until a measure or observation is defined.

## Core Concepts

The plan integrates subsidiary decisions; separate scope, schedule and cost files are not yet a project plan.

Progressive elaboration and rolling-wave planning add detail as uncertainty reduces without abandoning control.

Requirements must be testable, prioritised and traceable from need through deliverable and acceptance evidence.

The scope statement defines deliverables, exclusions, constraints, assumptions and acceptance criteria.

The WBS decomposes deliverables to manageable work packages; the WBS dictionary removes ambiguity.

Dependencies create the network; the longest path sets the earliest finish and carries zero or least float.

Duration estimates should separate work, waiting, risk and resource availability; use analogous, parametric, bottom-up or three-point methods deliberately.

The cost baseline is time-phased; contingency reserve covers known-unknowns while management reserve covers unknown-unknowns.

## Applied Guidance

Start requirements with the stakeholder need, then write acceptance evidence. Words such as easy, fast and user-friendly are not testable until a measure or observation is defined.

The WBS follows deliverables rather than the organisation chart. Work packages should be large enough to manage and small enough to estimate, assign and accept.

The critical path is the longest-duration path through the current network. It is not necessarily the most technically difficult or politically important work.

A baseline is the approved reference for control. A forecast is the latest expected outcome. Keep both visible; overwriting the baseline destroys the ability to explain variance.

## Reference-Sourced Deep Dives

### The Integrated Project Plan

Scope: What is authorised and accepted.

Schedule: Sequence, duration and milestones.

Cost: Time-phased funding and reserves.

Quality: Measures, assurance and control.

Resources: Skills, capacity and procurement.

Risk & stakeholders: Responses, engagement and governance.

### Requirements Elicitation

1. Identify — sources and decision roles

2. Gather — interview, observe, workshop

3. Analyse — conflicts, constraints and value

4. Specify — testable requirement

5. Validate — source confirms meaning

Decision insight: Elicitation is discovery and negotiation—not taking an order from one stakeholder.

### Weak versus Testable Requirements

| Weak wording | Testable wording | Evidence |
| --- | --- | --- |
| Fast collection | 90% ready within 10 minutes | Timestamp sample |
| Accurate picking | At least 98% line accuracy | Check sheet |
| Easy to use | New staff completes task after 30-minute training | Observed test |
| Reliable | 99.5% availability in pilot hours | System log |

Decision insight: A measure without a method or status date is still ambiguous.

### Prioritisation Choices

| Method | Decision logic | Use when |
| --- | --- | --- |
| MoSCoW | Must / Should / Could / Won't | Time-boxed scope |
| Weighted scoring | Value across criteria | Competing options |
| Kano | Basic, performance, delight | Customer experience |
| Trade-off sliders | Relative constraint priority | Governance alignment |

Decision insight: Priorities must remain traceable to outcomes, not just stakeholder preference.

### Traceability from Need to Evidence

1. Outcome — what success changes

2. Requirement — what must be true

3. Deliverable — what is produced

4. Work package — what the team performs

5. Acceptance — how completion is proven

Decision insight: Trace both directions: every need is delivered, and every deliverable has a reason.

### Scope Statement Essentials

Product scope: Characteristics of the result.

Project scope: Work required to create it.

Exclusions: What is deliberately not included.

Acceptance: Who approves against which criteria.

Constraints: Limits the plan must respect.

Assumptions: Planning beliefs to validate.

### WBS Decomposition

1. Start — authorised deliverables

2. Break down — smaller deliverable components

3. Test 100% — all work, no overlap

4. Stop — estimable, assignable, sequenced, accepted

5. Define — dictionary entry

Decision insight: Do not decompose by department when the deliverable crosses departments.

### WBS Dictionary—Why It Matters

| Field | Decision enabled | Failure prevented |
| --- | --- | --- |
| Description | Shared meaning | Different estimates for different work |
| Owner | Accountability | Unclaimed delivery |
| Acceptance | Definition of complete | Almost done forever |
| Dependencies | Sequence | Late discovery |
| Estimate basis | Confidence and revision | Unexplained padding |

Decision insight: The diagram shows structure; the dictionary makes the structure manageable.

### Dependency Relationships

| Type | Logic | Example |
| --- | --- | --- |
| Finish-to-start | A finishes before B starts | Configure before integration test |
| Start-to-start | A starts before B starts | Draft training after testing begins |
| Finish-to-finish | A finishes before B finishes | Documentation completes with testing |
| Start-to-finish | Rare transition logic | Old support ends after new starts |

Decision insight: Leads and lags change timing; they do not remove the underlying dependency.

### Critical Path Calculation

1. Forward pass — earliest start and finish

2. Project finish — largest earliest finish

3. Backward pass — latest finish and start

4. Float — late start minus early start

5. Critical path — least-float path

Decision insight: The critical path is the longest-duration route through current logic, not the most important-looking task.

### Estimating Methods

| Method | Strength | Limitation |
| --- | --- | --- |
| Analogous | Fast early estimate | Lower detail |
| Parametric | Repeatable unit logic | Needs valid relationship |
| Bottom-up | Detailed and accountable | Time-consuming |
| Three-point | Makes uncertainty visible | Still depends on judgement |

Decision insight: Record the basis so the estimate can be challenged and updated without starting over.

### Cost Baseline and Reserves

Work-package estimates: Rolled up from authorised scope.

Contingency reserve: Funded responses for identified risk.

Cost baseline: Time-phased performance reference.

Management reserve: Held outside baseline for unknown-unknowns.

Project budget: Cost baseline plus management reserve.

## Activity 3 — Discover Requirements and Map Acceptance Evidence

| Field | Detail |
| --- | --- |
| Phase | Planning |
| Duration | 35 minutes |
| Objective | Elicit, prioritise and trace requirements from stakeholder need to acceptance (A2, K2). |
| Tools | Requirements Workshop, Stakeholder Register and Traceability Matrix |
| Situation | Outlet supervisors want speed, Finance wants payment control, customers want predictable collection, and the POS vendor wants a stable interface. The charter is approved, but the stated needs are not testable. |
| Output | A stakeholder register, workshop decision log and requirements traceability matrix with priorities, owners, deliverables and measurable acceptance evidence. |

### Tool Files

25 Requirements Traceability Matrix.xlsx

03 Requirements Workshop and Stakeholder Register.xlsx

### Detailed Procedure

1. Identify requirement sources and record their influence, impact and decision role.

2. Use interviews, observation and a facilitated workshop to surface needs, constraints and conflicts.

3. Rewrite vague words such as fast, simple and reliable into measurable conditions.

4. Give every requirement an ID, source, rationale, owner and related charter outcome.

5. Apply MoSCoW and challenge each Must against the pilot success criteria.

6. Define a deliverable and acceptance method for every Must and Should.

7. Record unresolved questions, decision owners and due dates in the workshop log.

8. Run a traceability audit and repair any orphan outcome, requirement or acceptance test.

### Acceptance Criteria

Every prioritised requirement has a source, rationale, owner, deliverable and testable acceptance method; unresolved conflicts have named decision owners and dates.

### Debrief

A requirement is not complete until acceptance can be observed or measured.

Prioritisation is a trade-off decision, not a label applied by the loudest stakeholder.

Traceability protects value when scope changes later.

## Activity 4 — Build the Scope Baseline with WBS and Dictionary

| Field | Detail |
| --- | --- |
| Phase | Planning |
| Duration | 45 minutes |
| Objective | Turn approved requirements into a complete, manageable scope baseline (A2, K2). |
| Tools | Work Breakdown Structure, WBS Dictionary and Requirements Traceability Matrix |
| Situation | The team has 14 prioritised requirements, but the vendor proposal groups work by department and omits outlet readiness, training and handover. Estimates cannot be trusted until the total scope is visible. |
| Output | A scope statement, WBS, WBS dictionary and repaired traceability matrix with no missing or duplicated work. |

### Tool Files

24 Work Breakdown Structure.pptx

24 WBS Dictionary.xlsx

25 Requirements Traceability Matrix.xlsx

### Detailed Procedure

1. Write the scope statement: deliverables, exclusions, assumptions, constraints and acceptance conditions.

2. Decompose by deliverable rather than department; include project management and transition work.

3. Apply the 100% rule and test for overlap between sibling elements.

4. Stop decomposition where a work package can be estimated, assigned, sequenced and accepted.

5. Complete dictionary entries for description, owner, acceptance, dependencies, assumptions and estimate basis.

6. Map each requirement to at least one work package and each work package to a requirement or project-management need.

7. Ask another team to find omitted, duplicated or ambiguous scope and repair the baseline.

### Acceptance Criteria

The WBS covers 100% of authorised work without overlap, each work package is manageable and every requirement traces to acceptance-ready scope.

### Debrief

The WBS describes all project work; the schedule describes when that work occurs.

Transition and project-management work are real scope even when customers never see them.

A strong dictionary prevents different teams from estimating different meanings.

## Activity 5 — Develop the Integrated Schedule and Cost Baseline

| Field | Detail |
| --- | --- |
| Phase | Planning |
| Duration | 55 minutes |
| Objective | Sequence, estimate and fund the authorised scope as one realistic plan (A2, K2). |
| Tools | Network Diagram, Gantt Schedule and Budget versus Actual |
| Situation | The launch must precede Lunar New Year trading. The vendor has proposed a date without dependency logic, resource calendars or reserves. Finance requires a time-phased baseline within S$180,000. |
| Output | A network with forward/backward passes, critical path, Gantt milestones, basis of estimates and a time-phased cost baseline plus contingency within the authorised ceiling. |

### Tool Files

28 Schedule Network Diagram.xlsx

29 - Gantt Chart - Schedule - Daily Weekly Monthly and Phases.xlsx

32 Project Budget - Planned vs Actual - Weekly and Monthly.xlsx

### Detailed Procedure

1. Translate WBS work packages into activities and identify mandatory and discretionary dependencies.

2. Add finish-to-start, start-to-start, leads and lags only where the logic is defensible.

3. Estimate durations using analogous, parametric, bottom-up or three-point methods and record the basis.

4. Perform forward and backward passes; calculate total float and identify the current critical path.

5. Build the Gantt with decision milestones, resource calendars and acceptance gates.

6. Estimate cost bottom-up and cross-check with an analogous or parametric estimate.

7. Time-phase labour, vendor, equipment, training and contingency; keep management reserve separate.

8. Reconcile every scheduled work package to the budget and every milestone to acceptance evidence.

### Acceptance Criteria

The dependency network calculates correctly, the plan fits the five-month limit, all authorised work is time-phased and funded, and baseline plus contingency stays within S$180,000.

### Debrief

A Gantt is the presentation of schedule logic, not the logic itself.

The critical path can change after every update or approved change.

Baseline and forecast must remain separate so variance can be explained.

# Topic 03 — Apply Methods and Tools to Drive a Project

Alignment: A3, K3 · LO3

Quality planning · flow · root cause · Pareto · improvement

## Why This Topic Matters

Tool choice begins with the question. Use a check sheet for facts, fishbone for breadth, 5 Whys for depth, Pareto for priority and a control chart for behaviour over time.

## Core Concepts

A method defines how work is managed; a tool makes information visible. Choose both for the decision needed.

Predictive plans optimise sequence and baseline control; adaptive boards optimise flow and feedback; hybrid combines both intentionally.

Quality means conformance to requirements and fitness for use, not luxury or perfection.

Prevention and appraisal are usually cheaper than internal and external failure.

A check sheet captures facts, a control chart detects process behaviour, Pareto prioritises causes, and fishbone plus 5 Whys investigates root cause.

Root-cause analysis must end at a process or system cause the team can influence, not blame a person.

Visual work management exposes blocked work and excessive WIP before the schedule report does.

Continuous improvement closes the loop through a named action, owner, measure and review date.

## Applied Guidance

Tool choice begins with the question. Use a check sheet for facts, fishbone for breadth, 5 Whys for depth, Pareto for priority and a control chart for behaviour over time.

Common-cause variation belongs to the process; special-cause variation has an identifiable event or condition. Tampering with a stable process after every data point can make performance worse.

Corrective action addresses an observed variance or non-conformity. Preventive action lowers the probability of future variance. Both need an owner and verification.

Visual work management should expose blocked work, WIP, ageing and ownership—not become a colourful task list with no decision rules.

## Reference-Sourced Deep Dives

### Method versus Tool

| Element | Purpose | Example |
| --- | --- | --- |
| Method | Defines how work is managed | Predictive, Scrum, Kanban, PDCA |
| Tool | Makes evidence visible | WBS, board, chart, log |
| Policy | Defines operating rule | WIP limit, acceptance rule |
| Cadence | Defines review rhythm | Daily review, weekly status |

Decision insight: A familiar tool used without a decision rule becomes decoration.

### Predictive, Adaptive and Hybrid

| Signal | Predictive | Adaptive / hybrid |
| --- | --- | --- |
| Requirements | Stable and knowable | Evolving or discovery-heavy |
| Delivery | Larger gated releases | Short usable increments |
| Change | Controlled against baseline | Expected inside prioritised backlog |
| Best fit | Low uncertainty, costly rework | Fast feedback, reversible choices |

Decision insight: Tailor by deliverable when different parts of one small project carry different uncertainty.

### Direct and Manage Project Work

1. Authorise — approved plan and work package

2. Coordinate — people, suppliers and interfaces

3. Produce — deliverables and work data

4. Learn — issues, knowledge and requests

5. Update — documents and forecasts

Decision insight: Execution produces both deliverables and information needed for control.

### A Lean PMIS for a Small Project

Source of truth: Named location and owner.

Version control: Number, date, author and status.

Decision log: What, who, when and rationale.

Access: Right people, current artefact.

Archive: Superseded records remain traceable.

Security: Sensitive content has proportionate access.

### Quality Planning, Assurance and Control

| Discipline | Question | Evidence |
| --- | --- | --- |
| Planning | What quality is required? | Metrics, methods and acceptance |
| Assurance | Will the process achieve it? | Review, audit, coaching |
| Control | Does the result conform? | Inspection, tests and charts |
| Improvement | How will the system change? | Experiment and verification |

Decision insight: Inspection finds defects; assurance and improvement reduce the chance of creating them.

### HarbourHub Quality-Cost Decision

| Option | Near-term effect | Decision signal |
| --- | --- | --- |
| Add catalogue-data validation | S$4,000 prevention spend | Reduces rejection and re-pick risk |
| Test only at pilot launch | Lower spend now | Defects discovered with customers waiting |
| Accept manual correction | No tooling change | Recurring labour and queue growth |
| Decision | Fund validation before rollout | Cheaper than repeated external failure |

Decision insight: The team chooses prevention because one avoided launch-week failure can repay the control.

### Quality Tool Sequence

1. Check sheet — capture facts

2. Fishbone — broaden possible causes

3. Five Whys — test one chain

4. Pareto — focus the vital few

5. Control chart — understand behaviour

6. Experiment — verify improvement

Decision insight: Do not jump from anecdote directly to solution.

### Common Cause versus Special Cause

| Signal | Meaning | Response |
| --- | --- | --- |
| Stable random variation | System behaviour | Improve the process |
| Point beyond limits | Potential special cause | Investigate event |
| Run or trend | Non-random pattern | Test changed condition |
| Within limits but off specification | Stable but incapable | Redesign process |

Decision insight: Control limits come from process data; specification limits come from requirements.

### Kanban Operating Policies

Visualise: Show status, owner and blockers.

Limit WIP: Stop starting; start finishing.

Manage flow: Watch ageing and bottlenecks.

Make policies explicit: Entry, exit and priority rules.

Feedback: Review at a useful cadence.

Improve: Run small measurable experiments.

### PDCA Improvement Loop

1. Plan — problem, cause, hypothesis and measure

2. Do — small controlled change

3. Check — compare evidence with prediction

4. Act — standardise, adapt or stop

Decision insight: Improvement is complete only when the new practice is verified and sustained.

### Manage Project Knowledge

Explicit: Documents, data and procedures.

Tacit: Experience and judgement shared through work.

Create: Reviews, experiments and problem solving.

Use: Decision support during delivery.

Transfer: Handover and lessons for future teams.

## Activity 6 — Tailor the Delivery Method and Quality Plan

| Field | Detail |
| --- | --- |
| Phase | Execution |
| Duration | 35 minutes |
| Objective | Choose proportionate methods and tools to drive flow and prevent defects (A3, K3). |
| Tools | Delivery Approach Canvas, Quality Plan and Kanban Board |
| Situation | The catalogue and POS interface need predictable milestone control, while the outlet workflow needs rapid testing and feedback. The team must choose a hybrid delivery rhythm and define quality before build begins. |
| Output | A documented hybrid approach, phase and iteration rhythm, quality management plan, Definition of Done, Kanban policy and measurement plan. |

### Tool Files

30 Kanban Board.xlsx

35 Check Sheets.xlsx

34 Control Chart.xlsx

06 Delivery Approach and Quality Plan.xlsx

### Detailed Procedure

1. Rate requirement uncertainty, technical uncertainty, feedback speed, compliance and cost of change.

2. Choose predictive, adaptive or hybrid treatment for each major deliverable and justify the boundary.

3. Define milestone gates and short test-feedback cycles inside the execution phase.

4. Write a Definition of Done that includes acceptance, evidence, documentation and handoff conditions.

5. Set quality metrics for ready-on-time, pick accuracy, defect escape and rework.

6. Design the check-sheet sampling plan and the future control-chart review rule.

7. Configure the Kanban board, entry/exit policies, WIP limits and blocker escalation threshold.

8. Confirm which artefact is the source of truth and how versions will be controlled.

### Acceptance Criteria

The approach matches uncertainty, quality is measurable before work begins, WIP and evidence rules are explicit, and predictive/adaptive controls do not contradict one another.

### Debrief

Hybrid is intentional tailoring, not running two incompatible systems in parallel.

Quality must be designed into the workflow before it is inspected at the end.

A tool earns its place only when it changes a decision or behaviour.

## Activity 10 — Diagnose the Pilot Quality Failure

| Field | Detail |
| --- | --- |
| Phase | Monitoring and Controlling |
| Duration | 40 minutes |
| Objective | Use evidence and root-cause tools to select a controlled corrective experiment (A3, K3). |
| Tools | Check Sheet, Fishbone, Five Whys, Pareto and Control Chart |
| Situation | During testing, only 82% of orders are ready on time and pick accuracy is 94%. The vendor blames store staff; store staff blame inventory updates. The sponsor wants action before facts and hypotheses are separated. |
| Output | A check sheet, fishbone, five-whys chain, Pareto chart, control-chart interpretation and SMART corrective experiment. |

### Tool Files

35 Check Sheets.xlsx

37 Ishikawa Diagram.xlsx

38 Five Whys.xlsx

36 Pareto Principle Template.xlsx

34 Control Chart.xlsx

### Detailed Procedure

1. Enter and reconcile the supplied defect data by type, outlet, shift and date.

2. Build a fishbone across People, Process, Technology, Data, Measurement and Environment; label facts and hypotheses.

3. Select a high-frequency cause family and complete the five-whys chain to an influenceable system cause.

4. Read the chain backwards with because and repair causal jumps.

5. Rank defects in the Pareto template, calculate cumulative percentage and identify the vital few.

6. Plot daily performance and distinguish control behaviour from the customer specification.

7. Create one SMART corrective experiment with owner, measure, due date and review rule.

### Acceptance Criteria

Data totals reconcile, Pareto reaches 100%, the causal chain is actionable, the control interpretation matches the signal and the experiment has an owner and verification date.

### Debrief

Fishbone broadens, Five Whys deepens and Pareto prioritises.

Control limits describe process behaviour; specifications describe customer need.

Improvement is project work only when funded, owned and verified.

# Topic 04 — Manage Project Risk

Alignment: A4, K4 · LO4

Identify · assess · respond · contingency · monitor

## Why This Topic Matters

A risk statement separates cause, uncertain event and impact. This makes the response design testable: act on the cause, reduce probability, reduce impact or prepare contingency.

## Core Concepts

Risk is an uncertain event or condition with a positive or negative effect; an issue has already happened.

Write risks as cause-event-impact statements so the response targets the cause or reduces the impact.

The risk register records owner, probability, impact, exposure, triggers, response, contingency and residual risk.

Qualitative analysis prioritises quickly; quantitative analysis estimates the range of outcomes and decision value.

Threat responses are avoid, mitigate, transfer, accept or escalate; opportunity responses are exploit, enhance, share, accept or escalate.

A contingency plan is triggered by an observable threshold and funded from contingency reserve.

Decision trees compare expected monetary value; tornado charts reveal which assumptions deserve the most attention.

Risk reviews are recurring decisions, not a register created once and archived.

## Applied Guidance

A risk statement separates cause, uncertain event and impact. This makes the response design testable: act on the cause, reduce probability, reduce impact or prepare contingency.

Probability-impact scores are ordinal prioritisation aids. Do not pretend that multiplying two subjective ratings creates a precise financial forecast.

Expected monetary value helps compare repeated or material choices. It can still miss reputation, safety, legal duty and strategic option value.

Residual risk remains after the response; secondary risk is introduced by the response. Both return to the register with owners.

## Reference-Sourced Deep Dives

### Risk, Issue and Assumption

| Item | Time orientation | Management action |
| --- | --- | --- |
| Risk | May happen | Owner, trigger and response |
| Issue | Has happened | Contain, resolve and escalate |
| Assumption | Believed true | Validate by a date |
| Constraint | Known limit | Plan within or change formally |

Decision insight: A triggered risk becomes an issue; its response owner moves from readiness to action.

### The Risk Management Cycle

1. Plan — scales, thresholds and roles

2. Identify — threats and opportunities

3. Analyse — priority and decision value

4. Respond — action, owner, trigger and reserve

5. Monitor — residual, secondary and emerging risk

Decision insight: Risk management repeats whenever scope, schedule, suppliers or the environment change.

### Risk Breakdown Structure

Technical: Design, interface, data and quality.

External: Regulation, market, weather and supplier.

Organisational: Priority, funding, skills and governance.

Project management: Estimate, dependency, communication and scope.

Opportunity: Faster adoption, reuse, cost saving and capability.

### Writing an Actionable Risk

1. Cause — because inventory data refresh is delayed

2. Event — stock availability may be wrong

3. Impact — orders may be rejected or re-picked

4. Response — reduce cause or impact

5. Trigger — refresh latency exceeds threshold

Decision insight: Cause-event-impact wording prevents vague risks such as 'vendor risk'.

### Qualitative Risk Factors

| Factor | Question | Use |
| --- | --- | --- |
| Probability | How likely? | Exposure priority |
| Impact | How severe? | Tolerance and reserve |
| Urgency | How soon must we act? | Response timing |
| Proximity | How soon may it occur? | Monitoring cadence |
| Dormancy | How long before impact appears? | Early detection |

Decision insight: Two risks with the same score may require different action timing.

### HarbourHub Threat-Response Workshop

| Named threat | Chosen response | Owned action and trigger |
| --- | --- | --- |
| Inventory feed is late | Mitigate | IT lead adds latency alert; trigger >15 minutes |
| Vendor misses integration date | Transfer + mitigate | Milestone clause plus weekly interface test |
| Outlet rejects new process | Mitigate | Ops lead pilots job aid and observes first 20 orders |
| Cyber approval exceeds tolerance | Escalate | Sponsor decides scope trade by gate date |
| Residual launch disruption | Accept actively | Fund two-day floor support contingency |

Decision insight: Each response is specific enough to schedule, fund, monitor and verify.

### Opportunity Response Strategies

| Strategy | Intent | Example |
| --- | --- | --- |
| Exploit | Ensure opportunity occurs | Assign best resources |
| Enhance | Increase probability or benefit | Accelerate pilot learning |
| Share | Partner for capability | Revenue-sharing supplier |
| Accept | Take benefit if it occurs | No proactive spend |
| Escalate | Move to programme or strategy | Enterprise reuse |

Decision insight: Positive uncertainty deserves ownership and deliberate action too.

### Response Architecture

1. Preventive — act before trigger

2. Trigger — observable threshold

3. Contingency — act when triggered

4. Fallback — act if contingency fails

5. Residual — remaining exposure

6. Secondary — new risk from response

Decision insight: A response is not operational until timing, ownership and funding are explicit.

### Decision Tree and Sensitivity

| Tool | Question answered | Caution |
| --- | --- | --- |
| Decision tree | Which option has better expected value? | Average value can hide tail consequences |
| Tornado chart | Which assumption drives outcome most? | Range quality determines insight |
| Probability-impact matrix | What needs attention first? | Ordinal scores are not precise money |

Decision insight: Use more analysis only when the decision value exceeds the analysis effort.

### Risk Review Agenda

Triggered: Promote to issue and execute response.

Changed: Re-score probability, impact and timing.

New: Add emerging and secondary risk.

Obsolete: Close with rationale.

Reserve: Reconcile use and remaining exposure.

Escalation: Decide beyond tolerance.

## Activity 7 — Build the Risk Register and Fund Responses

| Field | Detail |
| --- | --- |
| Phase | Planning and Execution |
| Duration | 45 minutes |
| Objective | Identify, analyse and manage uncertainty with proportionate, funded action (A4, K4). |
| Tools | Risk Matrix, Decision Tree and Tornado Analysis |
| Situation | The POS interface may be late, refrigerated stock counts are unreliable, a key trainer has a short availability window and a faster payment option could improve adoption. Contingency reserve is S$18,000. |
| Output | A prioritised risk register, response and trigger plan, EMV recommendation, tornado sensitivity reading and reconciled S$18,000 contingency allocation. |

### Tool Files

48 Risk Assessment Matrix Two pages.xlsx

45 Decision Tree Analysis TDIDT.xlsx

49 Tornado Chart - Sensitivity Analysis.xlsx

### Detailed Procedure

1. Separate uncertain risks from current issues and assumptions requiring validation.

2. Write at least eight risks as cause-event-impact statements and classify them in a risk breakdown structure.

3. Score probability, impact, urgency and proximity; justify the priority threshold.

4. Assign risk owners, response owners and observable triggers.

5. Choose threat and opportunity responses; define preventive, contingency and fallback actions.

6. Use the decision tree to compare payment options and state a non-financial factor outside EMV.

7. Use the tornado chart to identify the two assumptions driving the largest outcome variation.

8. Allocate no more than S$18,000 to named risks and record residual and secondary risk.

### Acceptance Criteria

Priority risks have owners, triggers and funded responses; the EMV and sensitivity logic reconcile; contingency is allocated to named uncertainty and residual risk remains visible.

### Debrief

Risk management creates options before triggers become expensive issues.

Quantitative analysis sharpens material decisions but does not replace judgement.

Acceptance means informed monitoring and contingency, not forgetting the risk.

# Topic 05 — Collaborate with Stakeholders

Alignment: A5, K5 · LO5

Identify · analyse · communicate · engage · allocate accountability

## Why This Topic Matters

Stakeholder identification is continuous. Procurement, design choices, issues and change requests can create new stakeholders or alter influence and urgency.

## Core Concepts

A stakeholder can affect, be affected by, or perceive themselves to be affected by the project.

The stakeholder register captures interest, influence, expectations, impact, communication needs and engagement strategy.

Power-interest mapping guides attention; the salience model adds legitimacy and urgency.

The engagement assessment matrix compares current and desired states so the gap becomes actionable.

RACI clarifies who is Responsible, Accountable, Consulted and Informed; every deliverable needs one clear Accountable owner.

Communication planning matches audience, message, channel, frequency, owner and feedback route.

Engagement is two-way sense-making and decision participation, not one-way broadcasting.

Escalation should state the decision needed, options, impact of delay and recommendation.

## Applied Guidance

Stakeholder identification is continuous. Procurement, design choices, issues and change requests can create new stakeholders or alter influence and urgency.

Power-interest mapping guides management attention; salience adds legitimacy and urgency. Use both when formal authority does not explain actual influence.

A RACI matrix is a diagnostic for decision rights. One Accountable owner is the default; exceptions need an explicit governance reason.

A communication plan specifies message, audience, channel, frequency and owner. An engagement plan adds the feedback route and decision the stakeholder can shape.

## Reference-Sourced Deep Dives

### The Stakeholder Engagement Cycle

1. Identify — who affects or is affected

2. Analyse — interest, influence, impact and expectations

3. Plan — desired state and decision participation

4. Engage — communicate, listen and negotiate

5. Monitor — feedback, sentiment and changed influence

Decision insight: Stakeholder identification is continuous because project decisions change who is affected.

### Stakeholder Register Fields

Identity: Role, organisation and relationship.

Interest: What outcome matters.

Influence: Formal and informal ability to affect work.

Impact: How the project changes their work.

Expectations: Definition of success and concern.

Strategy: Engagement action and owner.

### Stakeholder Mapping Lenses

| Lens | Dimensions | Best use |
| --- | --- | --- |
| Power-interest | Authority and attention | Management strategy |
| Impact-influence | Effect and ability to act | Change and adoption |
| Power-influence | Authority and active influence | Governance |
| Stakeholder cube | Three dimensions | Complex populations |
| Salience | Power, legitimacy, urgency | Competing claims |

Decision insight: A map is a hypothesis to guide action, not a permanent label.

### Seven Salience Classes

Dormant: Power only.

Discretionary: Legitimacy only.

Demanding: Urgency only.

Dominant: Power and legitimacy.

Dangerous: Power and urgency.

Dependent: Legitimacy and urgency.

Definitive: Power, legitimacy and urgency.

### Directions of Influence

| Direction | Typical stakeholders | Leadership move |
| --- | --- | --- |
| Upward | Sponsor and executives | Decision brief and escalation |
| Downward | Team and specialists | Clarity, coaching and feedback |
| Sideward | Peers and functional managers | Negotiation and coordination |
| Outward | Customers, vendors, regulators | Expectation and interface management |

Decision insight: Influence without authority depends on evidence, trust and a clear decision request.

### Communication Model

1. Encode — sender frames meaning

2. Transmit — channel carries message

3. Decode — receiver interprets

4. Feedback — understanding is tested

5. Noise — language, culture, timing and medium interfere

Decision insight: Delivery is not communication success; shared understanding is.

### Communication Methods

| Method | Best use | Risk |
| --- | --- | --- |
| Interactive | Decision and ambiguity | Time and facilitation |
| Push | Targeted distribution | Receipt is not understanding |
| Pull | Large reference set | Stakeholder may not retrieve it |
| Visual radiator | Shared current state | Stale information destroys trust |

Decision insight: Choose channel based on urgency, complexity, sensitivity and need for feedback.

### Stakeholder Engagement Levels

| Level | Signal | Management aim |
| --- | --- | --- |
| Unaware | Does not know project | Build awareness |
| Resistant | Opposes change | Understand concern and involve |
| Neutral | Neither resists nor supports | Connect to relevant value |
| Supportive | Helps when asked | Sustain participation |
| Leading | Actively champions | Enable influence |

Decision insight: The gap between current and desired state must become an owned action.

### HarbourHub RACI Failure Test

| Observed row | Failure signal | Repair |
| --- | --- | --- |
| Pilot go-live | Sponsor and PM both marked A | Sponsor is sole A; PM remains R |
| Inventory mapping | Vendor named R with no internal owner | IT lead becomes A; vendor remains R |
| Outlet job aid | No R assigned | Operations lead owns production |
| Customer message | Six people marked C | Consult legal and operations only |
| Benefits review | Everyone marked I | Name finance owner and decision audience |

Decision insight: The repaired matrix makes every critical deliverable and decision executable.

### Evidence-Based Escalation

1. Decision — what is needed

2. Options — feasible choices

3. Impact — consequence of delay

4. Recommendation — preferred option and why

5. Deadline — latest useful decision time

Decision insight: Escalation transfers a decision, not a problem without analysis.

## Activity 8 — Align Stakeholders, Accountability and Communications

| Field | Detail |
| --- | --- |
| Phase | Execution |
| Duration | 40 minutes |
| Objective | Collaborate with stakeholders and clarify decision rights for execution (A5, K5). |
| Tools | Stakeholder Map, Salience Model, RACI and Engagement Assessment |
| Situation | The POS vendor and Operations each believe the other owns interface acceptance. Finance has not approved a payment milestone, store managers receive conflicting instructions and one influential supervisor resists the pilot. |
| Output | A stakeholder map, salience reading, validated RACI, engagement assessment, communication actions and one-minute escalation recommendation. |

### Tool Files

42 Stakeholder Impact Over Influence Matrix.xlsx

43 Salience Chart.pptx

39 RACI Template.xlsx

41 Stakeholder Engagement Assessment Matrix.xlsx

### Detailed Procedure

1. Identify internal, external, upward, downward and sideward stakeholders.

2. Position stakeholders on impact/influence and justify every high rating with evidence.

3. Apply the salience lens of power, legitimacy and urgency; compare it with the two-dimensional map.

4. Build RACI rows around deliverables and decisions; enforce one Accountable owner per critical row.

5. Correct missing R/A, duplicated A and excessive consultation patterns.

6. Rate current and desired engagement and define the decision each stakeholder must help shape.

7. Set message, channel, frequency, owner and feedback route for each material gap.

8. Deliver an escalation brief: decision, options, impact of delay, recommendation and deadline.

### Acceptance Criteria

Critical decisions have one Accountable owner, material engagement gaps have two-way actions and the escalation asks the authorised person for a clear, time-bound decision.

### Debrief

Many communication failures begin as unclear decision rights.

Engagement is participation and feedback, not message broadcasting.

Attention follows influence, impact and urgency—not title alone.

# Topic 06 — Deploy Resources

Alignment: A6 · LO6

People · budget · equipment · procurement · team performance

## Why This Topic Matters

Resource availability is the fraction of time usable for this project after operations, leave and other commitments—not the employee's full calendar.

## Core Concepts

Resource planning links each work package to required skills, quantities, timing and availability.

A responsibility assignment is not a capacity plan; availability must be tested against concurrent work.

Resource levelling changes dates to resolve over-allocation; smoothing stays within available float.

Fast tracking overlaps work and raises risk; crashing adds cost to critical-path work and may not shorten the project.

Procurement decisions consider make-or-buy, lead time, quality, interfaces, contract type and vendor capability.

Tuckman's stages require adaptive leadership: direct, coach, support and delegate as the team matures.

Conflict is normal; collaborate for important relationships and outcomes, compromise when time is limited, and escalate only with evidence.

A resource dashboard should show demand, capacity, variance, bottlenecks and decisions—not just headcount.

## Applied Guidance

Resource availability is the fraction of time usable for this project after operations, leave and other commitments—not the employee's full calendar.

Smoothing uses available float and protects the end date. Levelling resolves over-allocation even when the project finish must move.

Crashing adds cost to critical-path work; fast tracking overlaps work that was sequential. Recalculate the network and risk after either action.

Conflict mode should match outcome importance and relationship importance. Collaboration is powerful but costly; not every low-stakes disagreement needs it.

## Reference-Sourced Deep Dives

### Resource Management Plan

Identify: People, equipment, facilities and funding.

Estimate: Quantity, skill and timing.

Acquire: Internal assignment or procurement.

Develop: Capability, trust and working agreements.

Manage: Performance, conflict and feedback.

Control: Usage, availability and corrective action.

### Organisation Structure and PM Authority

| Structure | PM authority | Resource pattern |
| --- | --- | --- |
| Functional | Low | Functional manager controls |
| Weak matrix | Limited | Coordinator role |
| Balanced matrix | Shared | Negotiated authority |
| Strong matrix | Moderate to high | Dedicated PM authority |
| Project-oriented | High | Dedicated team |

Decision insight: Even a small project needs explicit escalation when formal authority is limited.

### Role, Authority, Responsibility and Competence

| Element | Question | Evidence |
| --- | --- | --- |
| Role | What function is performed? | Role description |
| Authority | What decisions may be made? | Charter and tolerance |
| Responsibility | What outcome or work is owned? | RACI and work package |
| Competence | Can the person perform it? | Skill and experience |

Decision insight: Assigning work without authority or competence creates hidden dependency.

### Two-Week Capacity Worked Example

| Skill | Demand | Usable capacity / decision |
| --- | --- | --- |
| Integration developer | 96 hours | 64 hours — defer reporting interface |
| Outlet trainer | 40 hours | 48 hours — retain buffer |
| Data analyst | 52 hours | 32 hours — buy 20 specialist hours |
| Test lead | 60 hours | 56 hours — smooth four hours into next week |

Decision insight: The constraint is skill-specific usable time, not the team's nominal headcount.

### Acquire, Develop or Procure

| Choice | Use when | Trade-off |
| --- | --- | --- |
| Internal assignment | Capability exists | Priority conflict |
| Develop skill | Need is recurring | Learning time |
| Contract resource | Short-term specialist gap | Cost and knowledge transfer |
| Outsource deliverable | Clear result and interface | Control and vendor dependency |

Decision insight: Choose the smallest intervention that resolves the critical constraint.

### Make-or-Buy Decision

| Criterion | Make | Buy |
| --- | --- | --- |
| Capability | Builds internal skill | Accesses specialist skill |
| Lead time | Depends on availability | Depends on procurement and onboarding |
| Control | Direct management | Contract and interface control |
| Cost | Fixed or opportunity cost | Price plus vendor management |
| Knowledge | Retained internally | Requires transfer plan |

Decision insight: Lowest price is not lowest total project cost when delay and interface risk are included.

### Contract Type and Risk

| Type | Cost risk | Best fit |
| --- | --- | --- |
| Firm fixed price | More seller risk | Stable, clear scope |
| Cost reimbursable | More buyer risk | Uncertain scope with control |
| Time and materials | Shared / capped | Short-term flexible effort |
| Incentive arrangement | Shared performance target | Measurable outcome |

Decision insight: The contract allocates financial risk; it does not eliminate delivery accountability.

### HarbourHub Team-Stage Diagnostic

| Observed behaviour | Stage diagnosis | Next leadership move |
| --- | --- | --- |
| Vendor and IT dispute interface ownership | Storming | Facilitate roles and decision rule |
| Outlet champions share one job aid | Norming | Reinforce standard and peer coaching |
| Test team resolves defects without escalation | Performing | Delegate within tolerance |
| Pilot staff worry about release | Adjourning | Recognise contribution and confirm transition |

Decision insight: Leadership changes with team evidence; it is not a fixed personal style.

### Conflict Approaches

| Approach | When useful | Trade-off |
| --- | --- | --- |
| Collaborate | Outcome and relationship both matter | Time and openness |
| Compromise | Time-limited middle ground | Partial satisfaction |
| Accommodate | Relationship or learning matters more | Your need deferred |
| Direct / force | Emergency or authority decision | Commitment risk |
| Avoid | Low value or cooling period | Issue may persist |

Decision insight: Conflict is information; choose the response based on stakes and relationship.

### HarbourHub Bottleneck Options

| Option tested | Schedule effect | Decision |
| --- | --- | --- |
| Smooth outlet training | Uses two days of float | Accept — no milestone impact |
| Level integration work | Moves launch by one week | Reject unless scope is traded |
| Crash data validation | Recovers three days for S$3,600 | Approve inside reserve |
| Fast-track testing | May recover four days | Reject — high rework and quality risk |

Decision insight: The selected combination protects launch without hiding cost or quality trade-offs.

### Team Performance Signals

Delivery: Commitments met with acceptance evidence.

Flow: WIP, blockers and ageing visible.

Quality: Defects and rework trend.

Collaboration: Handoffs, feedback and conflict resolved.

Learning: Capability and knowledge transfer.

Sustainability: Workload remains safe and realistic.

## Activity 9 — Deploy Resources and Resolve the Bottleneck

| Field | Detail |
| --- | --- |
| Phase | Execution |
| Duration | 45 minutes |
| Objective | Match skills, capacity, procurement and budget to critical work (A6). |
| Tools | Organisation Chart, Resource Capacity, Procurement Decision, Kanban and Budget |
| Situation | Testing needs 22 person-days in two weeks, but only 16 are available. The business analyst is assigned to testing, training and vendor clarification. The sponsor wants evidence before accepting delay or extra cost. |
| Output | An organisation map, capacity heatmap, constraint-aware Kanban, procurement comparison, compression options, budget impact and sponsor recommendation. |

### Tool Files

40 Organisation Chart.pptx

30 Kanban Board.xlsx

32 Project Budget - Planned vs Actual - Weekly and Monthly.xlsx

09 Resource Capacity and Procurement Decision.xlsx

### Detailed Procedure

1. Map sponsor, project manager, functional managers, core team and vendor interfaces.

2. Calculate usable capacity by person, skill and week after operations and other commitments.

3. Match work-package demand to capacity and quantify the constraint and queue.

4. Set WIP limits and pull rules around the constrained skill.

5. Test smoothing within float and levelling beyond available float.

6. Test crashing and fast tracking only on the current critical path; record cost and new risk.

7. Compare make/buy options using cost, lead time, quality, interface and vendor capability.

8. Update the budget and recommend an option with schedule, cost, quality and risk effects.

### Acceptance Criteria

Capacity reconciles to named work and skills, the bottleneck is explicit, procurement/compression options show complete trade-offs and the chosen deployment remains within authorised constraints.

### Debrief

A RACI assignment does not create capacity.

Manage the constraint before adding capacity elsewhere.

Crashing buys time with cost; fast tracking buys time with risk.

# Topic 07 — Track Project Deliverables and Correct Misalignments

Alignment: A7 · LO7

Performance · earned value · change · corrective action · handover · closure

## Why This Topic Matters

PV, EV and AC must share the same status date and scope basis. Otherwise SPI and CPI compare unlike quantities.

## Core Concepts

Work performance data becomes information only after comparison with the approved baseline and thresholds.

A status report should answer: where are we, why, what is forecast, what decision is needed, and who owns the action.

Earned value integrates scope, schedule and cost: PV is planned work, EV is completed value, and AC is actual spend.

CPI = EV/AC and SPI = EV/PV; indices below 1.00 signal inefficiency against the baseline.

A change request states reason, impact, options and recommendation; approved changes update baselines and traceability.

Corrective action brings performance back to plan; preventive action reduces the probability of future variance.

Schedule compression is applied to the current critical path and re-analysed after every change.

Closure confirms acceptance, transition, contract completion, records, benefits ownership and lessons learned.

## Applied Guidance

PV, EV and AC must share the same status date and scope basis. Otherwise SPI and CPI compare unlike quantities.

CPI and SPI below 1.00 are adverse. Translate indices into plain-language forecast and decision consequences rather than reporting decimals alone.

Change control is not change prevention. It makes trade-offs explicit, records authority and updates every affected baseline after approval.

Closure includes acceptance, transition, contracts, records, lessons and benefits ownership. The project may finish while benefits continue under operations.

## Reference-Sourced Deep Dives

### The Monitoring and Control Cycle

1. Collect — work performance data

2. Compare — baseline, threshold and acceptance

3. Analyse — cause and forecast

4. Decide — action, change or escalation

5. Update — owners, plans and records

6. Verify — did action change outcome?

Decision insight: Control is forward-looking: the purpose of variance is to improve the forecast and decision.

### Data, Information and Reports

| Level | Example | Use |
| --- | --- | --- |
| Data | 7 defects, S$105k actual cost | Raw observation |
| Information | Defects above threshold, CPI 0.86 | Meaning through comparison |
| Report | Forecast, cause, action and decision | Governance and coordination |

Decision insight: A dashboard without interpretation is data display, not project control.

### A Decision-Ready Status Report

Where: Current milestone and acceptance state.

Variance: Scope, time, cost, quality and resource.

Why: Cause, not just symptom.

Forecast: Expected finish and cost.

Action: Owner, due date and verification.

Decision: Escalation with options and deadline.

### Validate Scope versus Control Scope

| Process | Question | Evidence |
| --- | --- | --- |
| Validate scope | Will the authorised stakeholder accept it? | Accepted deliverable |
| Control scope | Has authorised scope changed? | Baseline, RTM and change log |
| Control quality | Does the result conform? | Inspection and test record |

Decision insight: Verified quality is not the same as formal customer acceptance.

### Earned Value Building Blocks

PV: Budgeted value of work planned by status date.

EV: Budgeted value of work actually completed.

AC: Actual cost of completed work.

BAC: Total authorised budget for measured scope.

Status date: The same cut-off for every measure.

### Variance and Performance Indices

| Measure | Formula | Interpretation |
| --- | --- | --- |
| SV | EV − PV | Negative means less value completed than planned |
| CV | EV − AC | Negative means completed value cost more than budgeted |
| SPI | EV ÷ PV | Below 1.00 means schedule inefficiency |
| CPI | EV ÷ AC | Below 1.00 means cost inefficiency |

Decision insight: Translate every index into operational consequence and required decision.

### Forecasting with EAC

| Situation | Formula | Assumption |
| --- | --- | --- |
| Current cost efficiency continues | EAC = BAC ÷ CPI | Past cost performance persists |
| Remaining work re-estimated | EAC = AC + bottom-up ETC | New detailed forecast is credible |
| Original variance is one-off | EAC = AC + (BAC − EV) | Future returns to plan |
| Cost and schedule both constrain | EAC = AC + (BAC − EV)/(CPI × SPI) | Both inefficiencies persist |

Decision insight: Forecast choice is a management assumption and must be stated.

### Issue Management

1. Log — fact, impact and detection date

2. Contain — protect customer or milestone

3. Own — resolution and decision owner

4. Resolve — root cause and action

5. Escalate — outside authority or tolerance

6. Verify — evidence and closure

Decision insight: Do not keep an issue disguised as a risk after it has occurred.

### Loyalty-Points Change Worked Example

| Analysis lens | Finding | Implication |
| --- | --- | --- |
| Value | Could lift repeat purchase | Benefit is plausible but unvalidated |
| Scope and schedule | Adds API and two test cycles | Launch slips nine working days |
| Cost and resource | S$18,000 plus scarce developer | Exceeds PM tolerance |
| Risk and quality | New data/privacy interface | Needs security and regression evidence |
| Decision | Defer to post-pilot release | Protect baseline; retain request and rationale |

Decision insight: Useful ideas are not automatically urgent: the sponsor protects the pilot while preserving the option.

### Three Types of Action

| Action | Purpose | Example |
| --- | --- | --- |
| Corrective | Bring future performance back to plan | Add test capacity to recover milestone |
| Preventive | Reduce probability of future variance | Add interface review before integration |
| Defect repair | Modify non-conforming deliverable | Correct catalogue mapping |

Decision insight: Each action needs authority, ownership, due date and verification.

### Control Across Knowledge Areas

Schedule: Critical path, float and milestone forecast.

Cost: Actuals, earned value and forecast.

Quality: Conformance, variation and corrective action.

Resources: Utilisation, capacity and bottlenecks.

Risk: Triggers, exposure and reserve.

Communication & procurement: Effectiveness, obligations and disputes.

### Closure from Acceptance to Benefits

1. Accept — criteria and authorised sign-off

2. Transition — operations, support, data and training

3. Close contracts — claims, invoices, warranties and records

4. Learn — causes and reusable recommendations

5. Transfer benefits — owner, baseline, target and review

6. Close — archive and release resources

Decision insight: The project can close only after unresolved work is completed or formally transferred.

## Activity 11 — Control Performance, Issues and Change

| Field | Detail |
| --- | --- |
| Phase | Monitoring and Controlling |
| Duration | 45 minutes |
| Objective | Track integrated performance and take authorised corrective action (A7). |
| Tools | Integrated Status, Change and Issue Log, Burndown, Budget and Control Chart |
| Situation | At week 12, PV is S$108,000, EV is S$90,000 and AC is S$105,000. The sponsor requests loyalty points for S$24,000 and three weeks while a vendor interface issue threatens acceptance. |
| Output | An integrated status report, EVM calculations and forecast, issue decision, change-impact analysis, decision log, corrective action and updated control records. |

### Tool Files

31 Burndown Chart.xlsx

32 Project Budget - Planned vs Actual - Weekly and Monthly.xlsx

34 Control Chart.xlsx

11 Integrated Status Change and Issue Log.xlsx

### Detailed Procedure

1. Set one status date and reconcile deliverable, milestone, budget, quality, risk and resource evidence.

2. Calculate SV, CV, SPI and CPI from PV, EV and AC; interpret each in plain language.

3. Using BAC S$162,000, calculate EAC and ETC under current cost performance and compare with the ceiling.

4. Triage the interface issue by severity, owner, containment, root cause and resolution date.

5. Document the loyalty-points request and analyse scope, time, cost, quality, resource and risk impacts.

6. Recommend approve, reject, defer or trade scope; record approver, rationale and deadline.

7. Update affected baselines or the decision log and notify owners and stakeholders.

8. Choose corrective or preventive action with owner, due date and verification measure.

### Acceptance Criteria

EVM and forecast reconcile, issue and change records are distinct, the decision is authorised, all affected records are updated and corrective action is measurable.

### Debrief

Status reporting is a decision system, not a colour-coded history lesson.

Change control enables deliberate trade-offs; it does not prevent change.

An approved change is incomplete until every affected baseline is updated.

## Activity 12 — Accept, Handover and Close the Project

| Field | Detail |
| --- | --- |
| Phase | Closure |
| Duration | 35 minutes |
| Objective | Close only when deliverables, transition, contracts, records and benefits ownership are evidenced (A7). |
| Tools | Acceptance, Handover, Closure and Benefits Tracker plus Retrospective |
| Situation | All three outlets are live, but final payment is requested before complete acceptance evidence, support ownership, training records and unresolved-item decisions are consolidated. Benefits will continue after project closure. |
| Output | Signed acceptance matrix, handover and training evidence, unresolved-item disposition, contract closeout, lessons register, benefits tracker and formal closure recommendation. |

### Tool Files

44 Agile Retrospective.xlsx

12 Acceptance Handover Closure and Benefits.xlsx

### Detailed Procedure

1. Trace each accepted deliverable to its requirement, criterion, evidence and authorised approver.

2. List operational ownership, support levels, data ownership, monitoring and escalation after handover.

3. Verify training completion, knowledge transfer and access to current operating documentation.

4. Resolve or formally transfer every open issue, defect, risk, change and supplier obligation.

5. Confirm final invoices, warranties, contract records and payment approval conditions.

6. Run the retrospective and convert lessons into reusable recommendations with owners.

7. Assign benefits owners, measures, baselines, targets and review dates after closure.

8. Recommend close, close with transferred actions, or remain open; record sponsor approval.

### Acceptance Criteria

Acceptance is traceable, handover ownership is explicit, open items have formal disposition, contracts and records reconcile, and benefits continue under named operational owners.

### Debrief

Elapsed time does not close a project; complete evidence and transferred accountability do.

Lessons become assets only when future owners can find and use them.

Project work ends before benefits measurement ends.

# Assessment Readiness

Written Assessment (Case Study) — apply project management judgement to a small-project scenario.

Oral Questioning — explain and justify decisions against the course methods and evidence.

Open book: course slides, Learner Guide and approved course materials only.

Answer structure: method, scenario evidence, result, trade-off and next action.

# Glossary

| Term | Definition |
| --- | --- |
| Acceptance criteria | Measurable conditions a deliverable must satisfy to be accepted. |
| Baseline | The approved scope, schedule or cost reference used to measure performance. |
| Business case | The justification comparing options, costs, benefits and risks before investment. |
| Charter | The document that authorises the project and grants the project manager authority. |
| Contingency reserve | Budget or time for identified risks whose responses are planned. |
| Corrective action | Action intended to bring future performance back in line with the plan. |
| Critical path | The longest-duration path through the schedule network, normally with least float. |
| Earned value | The budgeted value of work actually completed at the status date. |
| Float | Time an activity can move without affecting a defined schedule date. |
| Issue | A condition or event that has already occurred and requires action. |
| Milestone | A zero-duration marker for a significant event, approval or completion. |
| RACI | Responsible, Accountable, Consulted and Informed role mapping. |
| Residual risk | Risk remaining after the planned response is applied. |
| Risk trigger | Observable threshold or event indicating a risk is becoming imminent or has occurred. |
| Rolling-wave planning | Planning near-term work in detail while keeping later work at a higher level. |
| Scope creep | Uncontrolled addition of scope without approved time, cost or resource change. |
| WBS | Deliverable-oriented hierarchical decomposition of the total project scope. |