ACTIVITY 1 WORKSHEET

Authorise the HarbourHub Click & Collect Pilot

Effective Project Management for Small Projects  ·  TGS-2020505545  ·  Topic 1  ·  LO1  ·  75 minutes

| TEAM MEMBERS ____________________________________ | DATE ____________________________________ |
| --- | --- |
| TOOL https://alfredang.github.io/designthinking/ | ACTIVITY FOLDER activities/activity-01-*/ |

THE SITUATION HarbourHub Fresh has approved discovery work for a click-and-collect pilot at three outlets, but the sponsor has not yet authorised delivery. Operations wants speed, Finance wants a hard S$180,000 ceiling, store managers fear disruption, and customers want reliable collection times. Your team must decide whether this is a viable small project and define the authority to proceed.

Record your team's output below.

1.  Small-project qualification test

2.  Primary user and evidence-based need

3.  Cost–benefit outputs and sensitivity

4.  Recommended option and rationale

5.  SMART success measures

6.  In-scope deliverables

7.  Explicit exclusions

8.  Milestones and budget cap

9.  Sponsor, PM and core team

10.  Assumptions, constraints and top risks

11.  Kickoff agenda

12.  Sponsor gate decision and conditions

SELF-CHECK BEFORE YOU FINISH

☐   The charter proves the work qualifies as a small project, names one accountable sponsor, contains quantified success measures and exclusions, stays within five months and S$180,000, and carries an explicit authorisation decision.

☐   All calculations reconcile to the supplied data and approved constraints.

☐   Every team member can explain the recommendation and trade-off.

☐   Completed editable tools or exports are saved in this folder.