## Schedule Network Diagram
Schedule Network Diagram
Activities |  |  |  |  | Project Name:
ES | D | EF
Activity |  |  | Activity 9
LS | F | LF
1 | 5 | 5
Activity 1 |  |  | Activity 10
1 | 0 | 5
Activity 2 |  |  | Activity 11
Activity 3 |  |  | Activity 12
Activity 4 |  |  | Activity 13
Activity 5 |  |  | Activity 14
Activity 6 |  |  | Activity 15
Activity 7 |  |  | Activity 16
Activity 8 |  |  | Activity 17

## Critial Path Instructions
|  |  | Critical Path Instructions |  | Sheet Instructions
ES | D | EF
Activity |  |  | 1 | Enter the durations (D) | 1 | The information you add to the boxes on the left
LS | F | LF | 2 | Perform the Forward Pass |  | will carry into the boxes in the Schedule Diagram.
|  |  |  | Add Early Start (ES) and Early Finish (EF) times | 2 | To add another box to the schedule, select the box
|  |  |  | EF = ES + Duration - 1 |  | you want on the left, copy it (Ctrl + C), then right
|  |  |  | ES = (highest) previous EF + 1 |  | click and select "Paste Special > Linked Picture"
|  |  | 3 | Perform the Backward Pass | 3 | To add arrows, copy one of the existing arrows
|  |  |  | Add Late Finish (LF) and Late Start (LS) times. |  | (Ctrl + C) or go to "Insert > Shapes > Arrow".
|  |  |  | The highest EF goes in the LF box. | 4 | Arrows will connect to the Linked Pictures.
|  |  |  | LS = LF - Duration + 1 | 5 | To drag and select multiple boxes, go to "Find &
|  |  |  | LF = (lower) LS - 1 |  | Select > Select Objects". Choose it again to go
|  |  | 4 | Calculate Float. |  | back to the normal cursor.
F = LS - ES

## ©
Schedule Network Diagram Template
© 2024 David McLachlan
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
You may make archival copies and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
Do not delete this worksheet.
Limitation of Liability
This template and any related documentation are provided to you "as is." While every effort has been made to provide an outstanding product, without limiting the above you accept that this template may not meet your requirements, operate error free, or identify any or all errors or problems. This agreement does not affect any statutory rights you may have as a consumer.