ACTIVITY 4 WORKSHEET

Build the Risk Register and Fund the Right Responses

Effective Project Management for Small Projects  ·  TGS-2020505545  ·  Topic 4  ·  LO4  ·  75 minutes

| TEAM MEMBERS ____________________________________ | DATE ____________________________________ |
| --- | --- |
| TOOL https://lms-tms.tertiaryinfotech.com/ | ACTIVITY FOLDER activities/activity-04-*/ |

THE SITUATION The pilot has entered build. The POS interface may be delivered late, refrigerated stock counts are unreliable at one outlet, a key trainer is available for only two weeks, and a faster payment option could improve adoption but costs more. The remaining contingency reserve is S$18,000.

Record your team's output below.

1.  Risk versus issue decisions

2.  Cause-event-impact statements

3.  Probability and impact rationale

4.  Priority exposure

5.  Risk and response owners

6.  Triggers

7.  Preventive, contingency and fallback actions

8.  Decision-tree EMV

9.  Tornado sensitivity reading

10.  S$18,000 reserve allocation

11.  Residual and secondary risks

SELF-CHECK BEFORE YOU FINISH

☐   Every priority risk has cause-event-impact wording, an owner, trigger, funded response and residual score; the decision-tree arithmetic reconciles; and the named contingency allocations total no more than S$18,000.

☐   All calculations reconcile to the supplied data and approved constraints.

☐   Every team member can explain the recommendation and trade-off.

☐   Completed editable tools or exports are saved in this folder.