## Decision Tree Instructions
Decision Tree Guidelines |  | Sheet Guidelines
1 | Start with a main decision on the left. | 1 | Select multiple objects by going to: Home > Find & Select > Select Objects;
2 | Enter positive or negative dollar amounts |  | Choose again to deselect.
| to reflect costs or benefits. | 2 | Copy and paste items from the workflow on the left onto your board.
3 | Link actions with "decision" or "chance" nodes | 3 | Connector lines will connect to Action blocks and shapes.
4 | Add probability percentages on the connectors | 4 | Set the Print Space for printing by selecting the area you want, then going to:
| for chance nodes |  | Page Layout > Print Area > Set Print Area, and changing the Scale to suit.
5 | Add up the benefits minus costs for a particular
path to see the final outcome amount.
6 | Multiply the percentages for a particular path
to see the outcome probability of that path.
i.e. 0.6 x 0.5 = 0.3 or 30%

## Example Decision Tree
Decision Tree Analysis
| Decision Name: | Build or upgrade plant
Build new plant
-$120,000
Strong demand
$200,000
Weak demand
$90,000
Chance node (probability)
Decision node
End of branch
Example
$100,000
Action with benefit or cost
Connector
100%
Probability
Example
Decision to be made
60%
Buy or upgrade?
40%
Outcome
$80,000
Upgrade plant
-$50,000
Outcome
-$30,000
60%
40%
Weak demand
$60,000
Strong demand
$120,000
Outcome
$70,000
Outcome
$10,000
42%
18%
36%
24%
Able to meet demand
Not able to meet demand
70%
30%
60%
40%
Not able to meet
demand
- $60,000
Able to meet demand
Outcome
-$30,000
40%
Outcome
$10,000
40%
(0.60 x 0.70 = 0.42)

## Blank Decision Tree
Decision Tree Analysis
Decision Name:
Action
-$ Cost or benefit
Action
$ Cost or benefit
Action
$ Cost or benefit
Chance node (probability)
Decision node
End of branch
Example
$100,000
Action with benefit or cost
Connector
100%
Probability
Example
Decision to be made
60%
Decision to be made
40%
Outcome
$ Cost or benefit
Action
-$ Cost or benefit
Outcome
-$ Cost or benefit
Outcome
$70,000
60%
40%

## ©
Decision Tree Template
© 2024 David McLachlan
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
You may make archival copies and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
Do not delete this worksheet.
Limitation of Liability
This template and any related documentation are provided to you "as is." While every effort has been made to provide an outstanding product, without limiting the above you accept that this template may not meet your requirements, operate error free, or identify any or all errors or problems. This agreement does not affect any statutory rights you may have as a consumer.