## Sprint Burndown Chart
Sprint Burndown Chart
Sprint # | 1 |  | Sprint start date: |  | 2023-03-02 | [7 empty] | ◄ Enter the Sprint start date and sprint number
Backlog Item ID | Story Cards | Initial Estimate | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1234 | An amazing feature | 5 | 2023-03-03: 1; 2023-03-06: 2; 2023-03-11: 1
1235 | Usability feature | 3 | 2023-03-02: 3; 2023-03-04: 1; 2023-03-05: -3; 2023-03-09: 2 | ◄ Add negative values to show effort above the estimate ( or, you can increase the Initial Estimate)
1236 | Testing card | 3 | bar: 2023-03-03; 2023-03-06; 2023-03-10 to 2023-03-11
1237 | Spike / research | 8 | 2023-03-10: 2; 2023-03-11: 1; 2023-03-12: 1
1238 | Another feature | 2 | 2023-03-04: 1; 2023-03-09: 3; 2023-03-13: 2
◄ Insert more rows for more story cards
| Remaining Effort | 21 | 18 | 16 | 14 | 17 | 14 | 9 | 6 | 3 | 2 | 0
| Ideal Trend | 21 | 18.9 | 16.8 | 14.7 | 12.6 | 10.5 | 8.4 | 6.3 | 4.2 | 2.1 | 0
Points Completed this Sprint |  | 24
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10

## ©
Sprint Backlog Template
© 2024 David McLachlan
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
You may make archival copies and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
Do not delete this worksheet.
Limitation of Liability
This template and any related documentation are provided to you "as is." While every effort has been made to provide an outstanding product, without limiting the above you accept that this template may not meet your requirements, operate error free, or identify any or all errors or problems. This agreement does not affect any statutory rights you may have as a consumer.