Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

LESSON PLAN

For

Effective Project Management for Small Projects

TGS Ref No: TGS-2020505545

Conducted by

Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

Version 18.0

DOCUMENT VERSION CONTROL RECORD

| Version Number | Effective Date of Release | Summary of Included Changes | Author |
| --- | --- | --- | --- |
| 17.0 | 19 August 2026 | Legacy master trainer slide release used as the controlling syllabus. | Tertiary Infotech Academy |
| 18.0 | 19 August 2026 | Complete visual and instructional redesign; content enriched from the Agile and PMP references; seven connected tool-based activities and self-contained editable template packs added; LG and LP regenerated. | Dr Alfred Ang |

TABLE OF CONTENTS

1. Course Information	4

2. Learning Outcomes and TSC Alignment	4

3. Delivery Strategy	5

4. Assessment Strategy	5

5. Detailed Course Schedule	5

Day 1 — From idea to an integrated, risk-aware baseline	5

Day 2 — From stakeholder alignment to controlled delivery and closure	6

6. Topic and Activity Facilitation	7

Topic 01 — Initiation of a Project	7

Topic 02 — Develop a Project Plan	7

Topic 03 — Apply Methods and Tools to Drive a Project	8

Topic 04 — Manage Project Risk	8

Topic 05 — Collaborate with Stakeholders	9

Topic 06 — Deploy Resources	9

Topic 07 — Track Project Deliverables and Correct Misalignments	9

7. Trainer Delivery Notes	10

7.1 Timing Discipline	10

7.2 Evidence and Debrief	10

7.3 Common Misconceptions	10

7.4 Contingency	11

# 1. Course Information

| Field | Detail |
| --- | --- |
| Course Title | Effective Project Management for Small Projects |
| Course Reference | TGS-2020505545 |
| TSC | Project Management · ICT-PMT-3026-1.1 |
| Training Provider | Tertiary Infotech Academy Pte Ltd · UEN: 201200696W |
| Duration | 2 days · 16 training hours |
| Daily Timing | 9:30 am–6:30 pm; 1-hour lunch excluded; short breaks taken within training time |
| Mode | Instructor-led, case-based and tool-based group practice |
| Trainer | Dr Alfred Ang |

# 2. Learning Outcomes and TSC Alignment

LO1: Develop project scope and team to initiate the facilitation of a small project

LO2: Develop a realistic project plan based on the agreed project scope

LO3: Utilise appropriate methods and tools to track and drive a project

LO4: Identify, analyse and manage project risks

LO5: Collaborate effectively with project stakeholders

LO6: Deploy manpower, budget and other resources for efficient completion

LO7: Track project deliverables and correct misalignments through control and closeout

| Code | Ability / Knowledge | Delivery evidence |
| --- | --- | --- |
| A1 | Facilitate execution of small projects that are typically less than six months, with limited budget and interdependencies, and no significant strategic impact | Topic 1 · Activity 1 |
| A2 | Implement realistic project plans based on project objectives and scope | Topic 2 · Activity 2 |
| A3 | Utilise appropriate methods and tools to track and drive progress against plans and timelines | Topic 3 · Activity 3 |
| A4 | Identify risks to project success and take appropriate actions to manage them | Topic 4 · Activity 4 |
| A5 | Collaborate effectively with relevant internal and external stakeholders directly impacting the project | Topic 5 · Activity 5 |
| A6 | Deploy manpower, financial budgets and relevant resources for efficient and effective completion | Topic 6 · Activity 6 |
| A7 | Track deliverables against schedules, monitor costs, timescales and resources, and take basic corrective actions when misaligned | Topic 7 · Activity 7 |
| K1 | Elements of a small project | Topic 1 |
| K2 | Requirements of a project plan | Topic 2 |
| K3 | Application of appropriate project management methodologies and tools | Topic 3 |
| K4 | Project risks | Topic 4 |
| K5 | Project stakeholder identification | Topic 5 |

# 3. Delivery Strategy

The v17 seven-topic syllabus is retained as the controlling sequence.

The Agile and PMP references enrich adaptive/predictive selection, value delivery, estimating, governance, stakeholder engagement, quality, risk, earned value, change control and closure.

One Singapore SME case runs through all seven activities. Learners leave with a connected project evidence trail rather than unrelated exercises.

The PowerPoint remains concept-led. Detailed procedures, evidence fields and acceptance criteria are in the Learner Guide and activity folders.

Each activity uses the actual editable Office templates linked from the v17 source deck; relevant browser tools provide additional visual practice.

# 4. Assessment Strategy

| Item | Detail |
| --- | --- |
| Written Assessment | Written Assessment (Case Study) — apply project management judgement to a small-project scenario. |
| Oral Questioning | Oral Questioning — explain and justify decisions against the course methods and evidence. |
| Conditions | Open book: course slides, Learner Guide and approved course materials only. |
| Competency | A minimum of 75% attendance and a Competent result are required for funding eligibility. |
| Evidence expectation | Method, scenario evidence, calculation or artefact, trade-off, recommendation and next action. |

# 5. Detailed Course Schedule

## Day 1 — From idea to an integrated, risk-aware baseline

| Time | Min | Type | Learning and Facilitation Activity |
| --- | --- | --- | --- |
| 09:30–09:50 | 20 | Admin | Welcome, course overview, ground rules and mandatory AM digital attendance |
| 09:50–10:20 | 30 | Concept | Topic 1 — small-project fit, value, charter, scope, team and kickoff |
| 10:20–11:35 | 75 | Activity | Activity 1 — Authorise the HarbourHub Click & Collect Pilot |
| 11:35–12:05 | 30 | Concept | Topic 2 — requirements, scope baseline, WBS, dependency logic and estimating |
| 12:05–13:00 | 55 | Activity | Activity 2A — requirements, WBS and network logic |
| 13:00–14:00 | 60 | Lunch | Lunch break |
| 14:00–15:05 | 65 | Activity | Activity 2B — critical path, Gantt and cost baseline |
| 15:05–15:30 | 25 | Concept | Topic 3 — method selection, quality, flow and root-cause discipline |
| 15:30–16:45 | 75 | Activity | Activity 3 — Diagnose and Prioritise the Pilot's Quality Failure |
| 16:45–17:10 | 25 | Concept | Topic 4 — risk identification, analysis, response, contingency and monitoring |
| 17:10–18:25 | 75 | Activity | Activity 4 — Build the Risk Register and Fund the Right Responses |
| 18:25–18:30 | 5 | Recap | Day 1 synthesis, save evidence and mandatory PM digital attendance |

Training time: 480 minutes (8.0 hours), excluding lunch.

## Day 2 — From stakeholder alignment to controlled delivery and closure

| Time | Min | Type | Learning and Facilitation Activity |
| --- | --- | --- | --- |
| 09:30–09:40 | 10 | Admin | Day 1 recall, questions and mandatory AM digital attendance |
| 09:40–10:10 | 30 | Concept | Topic 5 — stakeholder identification, analysis, RACI, communication and engagement |
| 10:10–11:25 | 75 | Activity | Activity 5 — Align Stakeholders with a Map, RACI and Engagement Plan |
| 11:25–11:50 | 25 | Concept | Topic 6 — capacity, optimisation, procurement, team development and conflict |
| 11:50–12:50 | 60 | Activity | Activity 6 — Deploy the Team and Resolve the Resource Bottleneck |
| 12:50–13:00 | 10 | Recap | Morning synthesis and evidence check |
| 13:00–14:00 | 60 | Lunch | Lunch break |
| 14:00–14:30 | 30 | Concept | Topic 7 — status, earned value, change control, corrective action and closure |
| 14:30–16:15 | 105 | Activity | Activity 7 — Control the Pilot, Decide the Change and Close the Project |
| 16:15–16:35 | 20 | Wrap | End-to-end integration, assessment readiness and Q&A |
| 16:35–16:50 | 15 | Assessment | Assessment briefing and candidate instructions |
| 16:50–18:20 | 90 | Assessment | Written Case Study and Oral Questioning — exact instrument timings to mirror the authenticated live assessment plan before release |
| 18:20–18:30 | 10 | Admin | Funding reminders, TRAQOM and mandatory Assessment/PM digital attendance |

Training time: 480 minutes (8.0 hours), excluding lunch.

# 6. Topic and Activity Facilitation

## Topic 01 — Initiation of a Project

Alignment: A1, K1 · LO1 · Activity 1 (75 min)

Concept emphasis: Small-project fit · value · charter · scope · team · kickoff

Activity outcome: A cost–benefit analysis, one-page business case and signed-ready project charter with measurable success criteria, scope boundaries, milestone dates, budget cap, team and kickoff agenda.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

The business case answers whether the project should exist; the charter answers whether the team is authorised to act.

A scope boundary is incomplete until exclusions are visible—silence is where scope creep starts.

Success criteria must be measurable before the plan is built, or control later becomes opinion.

## Topic 02 — Develop a Project Plan

Alignment: A2, K2 · LO2 · Activity 2 (120 min)

Concept emphasis: Requirements · scope baseline · WBS · network · schedule · budget

Activity outcome: A requirements traceability matrix, WBS and dictionary, network diagram with critical path and float, Gantt schedule with milestones, and time-phased S$180,000 cost baseline with contingency reserve.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

A Gantt chart is an output of dependency logic, not a substitute for it.

The integrated baseline is only credible when scope, schedule and cost reconcile to the same work packages.

Float belongs to the project, not automatically to the activity owner who happens to see it.

## Topic 03 — Apply Methods and Tools to Drive a Project

Alignment: A3, K3 · LO3 · Activity 3 (75 min)

Concept emphasis: Quality planning · flow · root cause · Pareto · improvement

Activity outcome: A reconciled check sheet, fishbone diagram, five-level causal chain, Pareto chart, control-chart interpretation and a SMART corrective experiment with owner and review date.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

Fishbone broadens the search, 5 Whys deepens one chain, and Pareto tells you which chain is worth funding first.

A control limit describes process behaviour; it is not the same as a customer specification limit.

Improvement becomes project work only when it has capacity, ownership and a verification date.

## Topic 04 — Manage Project Risk

Alignment: A4, K4 · LO4 · Activity 4 (75 min)

Concept emphasis: Identify · assess · respond · contingency · monitor

Activity outcome: A prioritised risk register with owners, triggers, responses, contingency and residual exposure; one decision-tree recommendation; one tornado sensitivity reading; and a reconciled S$18,000 reserve plan.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

An owner does not prevent a risk; they watch the trigger and ensure the agreed response is ready.

Contingency is not generic padding—it is a funded response to identified uncertainty.

Quantitative tools sharpen a decision but do not replace judgement about reputation, safety or compliance.

## Topic 05 — Collaborate with Stakeholders

Alignment: A5, K5 · LO5 · Activity 5 (75 min)

Concept emphasis: Identify · analyse · communicate · engage · allocate accountability

Activity outcome: A stakeholder register and power-interest map, salience reading, validated RACI matrix, current-to-desired engagement assessment, communication plan and one evidence-based escalation brief.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

Most collaboration failures are decision-right failures before they become communication failures.

RACI clarifies accountability; it does not replace the conversation needed to gain commitment.

Stakeholder attention should follow evidence of influence, impact and urgency—not organisational seniority alone.

## Topic 06 — Deploy Resources

Alignment: A6 · LO6 · Activity 6 (60 min)

Concept emphasis: People · budget · equipment · procurement · team performance

Activity outcome: A two-week capacity plan, organisation and escalation map, workload Kanban, evaluated compression options, reconciled budget impact and a sponsor recommendation that removes the bottleneck.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

A name in a RACI matrix does not create capacity; capacity must be measured against concurrent demand.

Fast tracking buys time with risk, while crashing buys time with cost—neither is automatically a good decision.

Manage the constraint first. Adding capacity elsewhere can increase WIP without improving delivery.

## Topic 07 — Track Project Deliverables and Correct Misalignments

Alignment: A7 · LO7 · Activity 7 (105 min)

Concept emphasis: Performance · earned value · change · corrective action · handover · closure

Activity outcome: A current Kanban and burndown, earned-value analysis with forecasts, status report, change-control decision, corrective-action log, acceptance and handover checklist, lessons learned and closure recommendation.

Facilitation approach: brief the decision and constraints, allow teams to work in the editable tools, conduct a peer gate review, and debrief against the acceptance criteria.

Trainer watch-outs:

Status reporting is a decision system: variance without forecast and action is only history.

An approved change is not complete until every affected baseline and traceability record is updated.

Project closure transfers accountability for benefits and operations; it does not merely stop project work.

# 7. Trainer Delivery Notes

## 7.1 Timing Discipline

The activities are the primary applied-learning evidence. If timing slips, compress repeated explanations before reducing hands-on practice.

Call a hard stop for each stage and display the decision required. Teams should not spend the entire activity beautifying a template.

Use short breaks within team work where indicated by class energy; the formal one-hour lunch remains excluded from training time.

## 7.2 Evidence and Debrief

Require editable files or exports, not only oral reports. Ask any team member to explain the calculation or recommendation.

Use the acceptance criteria as the debrief rubric. A completed template with inconsistent numbers is not accepted.

Keep the HarbourHub facts stable. When teams make an assumption, require them to label it and explain how it will be tested.

## 7.3 Common Misconceptions

| Misconception | Correction |
| --- | --- |
| Small projects do not need governance | Tailor governance; do not remove authorisation, baselines and decision rights. |
| A Gantt chart is the project plan | It visualises schedule information; the integrated plan also covers scope, cost, quality, resources, risk and stakeholders. |
| The critical path is the most important work | It is the longest-duration path through the current dependency network. |
| A risk register manages risk | Only owned, triggered and funded responses change exposure. |
| RACI solves collaboration | It clarifies accountability; engagement and decisions still require conversation. |
| CPI below 1 means under budget | CPI below 1 means less value earned per dollar spent—an adverse cost condition. |
| Closing means the deadline passed | Closure requires acceptance, transition, contracts, records, lessons and benefits ownership. |

## 7.4 Contingency

If a browser tool is unavailable, use the matching editable Office template in the activity folder.

If a learner has no laptop, pair them with a team that has one and require role rotation so they still calculate, review and present.

If the class is small, form two teams and make each team the other's sponsor gate reviewer.