## Slide 1
TRAINER SLIDES · WSQ
Effective Project Management for Small Projects
WSQ Course Code: TGS-2020505545 ·
2 days · 16 training hours
TSC: Project Management · ICT-PMT-3026-1.1
Version v18.0 · 19 August 2026
Tertiary Infotech Academy Pte Ltd · UEN: 201200696W

## Slide 2
COURSE ADMINISTRATION
Welcome & Housekeeping
How the two days work and what evidence you will produce
Effective Project Management for Small Projects · TGS-2020505545 ·
COURSE ADMINISTRATION
1

## Slide 3
ADMIN · ATTENDANCE
Digital Attendance (Mandatory)
AM, PM and Assessment
Complete every required SSG digital attendance scan.
Scan the trainer QR
Use your mobile camera and submit the attendance record.
75% minimum
Attendance eligibility is calculated from the official record.
Assessment required
Complete the assessment and achieve Competent for funding eligibility.
Effective Project Management for Small Projects · TGS-2020505545 ·
ADMIN · ATTENDANCE
2

## Slide 4
ADMIN · FACILITATOR
Your Trainer
Name
Dr Alfred Ang
Role
Course developer and principal trainer, Tertiary Infotech Academy
Experience
20+ years across engineering, analytics, AI and digital transformation
Contact
enquiry@tertiaryinfotech.com · +65 6100 0613
Effective Project Management for Small Projects · TGS-2020505545 ·
ADMIN · FACILITATOR
3

## Slide 5
ADMIN · HOW WE WORK
Ground Rules
Participate
Use the tools, challenge assumptions and explain your decisions.
Respect
One conversation at a time; disagree with evidence, not people.
Be punctual
Activities build on one another; missed work creates downstream gaps.
Keep evidence
Save every completed template for the case study and assessment review.
Effective Project Management for Small Projects · TGS-2020505545 ·
ADMIN · HOW WE WORK
4

## Slide 6
COURSE ALIGNMENT
Learning Outcomes — 1 to 4
LO1
Develop project scope and team to initiate the facilitation of a small project
LO2
Develop a realistic project plan based on the agreed project scope
LO3
Utilise appropriate methods and tools to track and drive a project
LO4
Identify, analyse and manage project risks
Effective Project Management for Small Projects · TGS-2020505545 ·
COURSE ALIGNMENT
5

## Slide 7
COURSE ALIGNMENT
Learning Outcomes — 5 to 7
LO5
Collaborate effectively with project stakeholders
LO6
Deploy manpower, budget and other resources for efficient completion
LO7
Track project deliverables and correct misalignments through control and closeout
Effective Project Management for Small Projects · TGS-2020505545 ·
COURSE ALIGNMENT
6

## Slide 8
TSC ALIGNMENT
Skills Framework — Abilities A1 to A4
Code
Ability
Practice
A1
Facilitate execution of small projects that are typically less than six months, with limited budget and interdependencies, and no significant strategic impact
Activity 1
A2
Implement realistic project plans based on project objectives and scope
Activity 2
A3
Utilise appropriate methods and tools to track and drive progress against plans and timelines
Activity 3
A4
Identify risks to project success and take appropriate actions to manage them
Activity 4
Every assessed ability has a named tool-based activity.
Effective Project Management for Small Projects · TGS-2020505545 ·
TSC ALIGNMENT
7

## Slide 9
TSC ALIGNMENT
Skills Framework — Abilities A5 to A7
Code
Ability
Practice
A5
Collaborate effectively with relevant internal and external stakeholders directly impacting the project
Activity 5
A6
Deploy manpower, financial budgets and relevant resources for efficient and effective completion
Activity 6
A7
Track deliverables against schedules, monitor costs, timescales and resources, and take basic corrective actions when misaligned
Activity 7
The seven activities form one connected project evidence trail.
Effective Project Management for Small Projects · TGS-2020505545 ·
TSC ALIGNMENT
8

## Slide 10
TSC ALIGNMENT
Skills Framework — Knowledge
Code
Knowledge
Taught in
K1
Elements of a small project
Topic 1
K2
Requirements of a project plan
Topic 2
K3
Application of appropriate project management methodologies and tools
Topic 3
K4
Project risks
Topic 4
K5
Project stakeholder identification
Topic 5
Knowledge is applied in the activity immediately following its topic.
Effective Project Management for Small Projects · TGS-2020505545 ·
TSC ALIGNMENT
9

## Slide 11
DAY 1 · FROM IDEA TO AN INTEGRATED, RISK-AWARE BASELINE
Lesson Plan — Day 1
Initiate with value
Topic 1 · charter, boundaries, team and kickoff
Plan the work
Topic 2 · requirements, WBS, schedule, critical path and budget
Drive quality and flow
Topic 3 · visual management, root-cause and prioritisation tools
Manage uncertainty
Topic 4 · risk register, responses, contingency and decision analysis
Effective Project Management for Small Projects · TGS-2020505545 ·
DAY 1 · FROM IDEA TO AN INTEGRATED, RISK-AWARE BASELINE
10

## Slide 12
DAY 2 · FROM STAKEHOLDER ALIGNMENT TO CONTROLLED DELIVERY AND CLOSURE
Lesson Plan — Day 2
Engage stakeholders
Topic 5 · mapping, RACI, communication and engagement
Deploy resources
Topic 6 · capacity, optimisation, procurement and team performance
Control and close
Topic 7 · status, earned value, change, corrective action and handover
Assessment
Written Case Study and Oral Questioning, open book
Effective Project Management for Small Projects · TGS-2020505545 ·
DAY 2 · FROM STAKEHOLDER ALIGNMENT TO CONTROLLED DELIVERY AND CLOSURE
11

## Slide 13
SEVEN-TOPIC SYLLABUS FROM v17
Course Outline — Topics 1 to 4
Topic 01 · Initiation of a Project
Small-project fit · value · charter · scope · team · kickoff · A1, K1
Topic 02 · Develop a Project Plan
Requirements · scope baseline · WBS · network · schedule · budget · A2, K2
Topic 03 · Apply Methods and Tools to Drive a Project
Quality planning · flow · root cause · Pareto · improvement · A3, K3
Topic 04 · Manage Project Risk
Identify · assess · respond · contingency · monitor · A4, K4
Effective Project Management for Small Projects · TGS-2020505545 ·
SEVEN-TOPIC SYLLABUS FROM v17
12

## Slide 14
SEVEN-TOPIC SYLLABUS FROM v17
Course Outline — Topics 5 to 7
Topic 05 · Collaborate with Stakeholders
Identify · analyse · communicate · engage · allocate accountability · A5, K5
Topic 06 · Deploy Resources
People · budget · equipment · procurement · team performance · A6
Topic 07 · Track Project Deliverables and Correct Misalignments
Performance · earned value · change · corrective action · handover · closure · A7
Effective Project Management for Small Projects · TGS-2020505545 ·
SEVEN-TOPIC SYLLABUS FROM v17
13

## Slide 15
EDITABLE OFFICE TOOLS + VERIFIED BROWSER TOOLS
The Seven Tool Packs
Activity
Tool pack
Used to
1
Project Charter & Business Case
Define value, scope, authority and success measures
2
WBS, RTM, Network & Gantt
Turn scope into an integrated baseline
3
Fishbone, 5 Whys & Pareto
Diagnose and prioritise quality causes
4
Risk Matrix, Decision Tree & Tornado
Prioritise uncertainty and fund responses
5
Stakeholder Map, RACI & SEAM
Plan influence, accountability and engagement
6
Organisation Chart & Kanban
Deploy people and balance workload
7
Kanban, Burndown, Budget & Control
Track delivery, earned value and corrective action
Every activity folder contains its own editable tools, procedure, worksheet, dataset and acceptance criteria.
Effective Project Management for Small Projects · TGS-2020505545 ·
EDITABLE OFFICE TOOLS + VERIFIED BROWSER TOOLS
14

## Slide 16
THE RUNNING CASE
One small project runs through all seven activities.
A 42-person Singapore specialty grocer will introduce online ordering and two-hour click-and-collect at three outlets. The five-month pilot has a S$180,000 cap, a core team of seven, two external suppliers, and limited dependencies. It is important to operations but does not change the company's overall strategy, making it a genuine small project. Success means: Launch at all three outlets by 30 January 2027; process at least 120 pilot orders per week; keep pick accuracy at or above 98%; achieve customer satisfaction of at least 4.2/5; and remain within the approved S$180,000 budget.
Effective Project Management for Small Projects · TGS-2020505545 ·
THE RUNNING CASE
15

## Slide 17
ASSESSMENT · BRIEFING
Briefing for Assessment
Individual work
No discussion once assessment begins.
Open book
Slides, Learner Guide and approved materials only.
Protect the paper
No photographs, recording or unauthorised materials.
Answer with evidence
State the method, decision, rationale and expected result.
Effective Project Management for Small Projects · TGS-2020505545 ·
ASSESSMENT · BRIEFING
16

## Slide 18
ASSESSMENT · WHAT TO EXPECT
Final Assessment
Written Case Study
Written Assessment (Case Study) — apply project management judgement to a small-project scenario.
Oral Questioning
Oral Questioning — explain and justify decisions against the course methods and evidence.
Conditions
Open book: course slides, Learner Guide and approved course materials only.
Competency
A minimum of 75% attendance and a Competent result are required for funding eligibility.
Effective Project Management for Small Projects · TGS-2020505545 ·
ASSESSMENT · WHAT TO EXPECT
17

## Slide 19
TOPIC 01 · A1, K1 · LO1
Initiation of a Project
Small-project fit · value · charter · scope · team · kickoff
01
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · A1, K1 · LO1
18

## Slide 20
TOPIC 01 · CENTRAL IDEA
Small does not mean informal.
The smaller the project, the less waste it can absorb. A short charter, sharp boundaries and visible decision rights are the control system—not bureaucracy.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · CENTRAL IDEA
19

## Slide 21
TOPIC 01 · CONCEPT MAP
Initiation of a Project — Core Concepts I
01
A project is temporary, unique and value-seeking; operations are ongoing and repetitive.
02
A small project is normally under six months, has a limited budget and team, few dependencies and no significant strategic impact.
03
The project manager integrates people, decisions and trade-offs; they do not merely maintain a schedule.
04
Success balances value and outcomes with scope, schedule, cost, quality, resources and risk.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · CONCEPT MAP
20

## Slide 22
TOPIC 01 · CONCEPT MAP
Initiation of a Project — Core Concepts II
05
Predictive, adaptive and hybrid approaches are choices driven by uncertainty, not labels of maturity.
06
The business case tests whether the project should exist; the charter authorises it to exist.
07
A useful charter names purpose, measurable success, scope boundaries, milestones, budget, major risks, team and sponsor authority.
08
A kickoff creates one shared picture of why, what, who, how and what happens next.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · CONCEPT MAP
21

## Slide 23
TOPIC 01 · APPLIED FRAMEWORK
From Need to Authorised Work
01
Need
evidence and user consequence
02
Business case
options, value and viability
03
Charter
authority, boundaries and success
04
Kickoff
shared picture and first decisions
Do not plan an unauthorised idea as though it were already a project.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · APPLIED FRAMEWORK
22

## Slide 24
TOPIC 01 · DECISION TOOL
Business Case vs Project Charter
Dimension
Business Case
Project Charter
Core question
Should we invest?
Are we authorised to proceed?
Focus
Options, benefits, costs, risk
Purpose, scope, team, milestones
Owner
Sponsor / business owner
Sponsor with project manager
Decision
Select or reject option
Authorize and delegate
Both are living decision records; neither is a ceremonial form.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · DECISION TOOL
23

## Slide 25
TOPIC 01 · DECISION TOOL
Choosing a Development Approach
Signal
Predictive
Adaptive / Hybrid
Requirements
Stable and testable upfront
Evolving or discovery-heavy
Feedback
Available late or at gates
Available in short cycles
Change cost
High after commitment
Reduced through increments
Governance
Baseline and stage gates
Timeboxes plus control points
Approach follows uncertainty and reversibility—not fashion.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · DECISION TOOL
24

## Slide 26
TOPIC 01 · TOOL-BASED PRACTICE
Activity 1 Tool Pack
02 Cost Benefit Analysis
XLSX · editable project tool
05 Business Case on a Page
DOCX · editable project tool
08 Project Charter Template
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · TOOL-BASED PRACTICE
25

## Slide 27
TOPIC 01 · HANDS-ON ACTIVITY
Authorise the HarbourHub Click & Collect Pilot
ACTIVITY 1 · 75 MIN
THE SITUATION
HarbourHub Fresh has approved discovery work for a click-and-collect pilot at three outlets, but the sponsor has not yet authorised delivery. Operations wants speed, Finance wants a hard S$180,000 ceiling, store managers fear disruption, and customers want reliable collection times. Your team must decide whether this is a viable small project and define the authority to proceed.
WHAT YOU'LL DO
Validate the customer problem, quantify the investment case, define measurable success, set in/out boundaries, name the core team and sponsor, record assumptions and high-level risks, and prepare the kickoff decision.
YOU'LL PRODUCE
A cost–benefit analysis, one-page business case and signed-ready project charter with measurable success criteria, scope boundaries, milestone dates, budget cap, team and kickoff agenda.
DONE WHEN
The charter proves the work qualifies as a small project, names one accountable sponsor, contains quantified success measures and exclusions, stays within five months and S$180,000, and carries an explicit authorisation decision.
Tool: Project Charter, Cost–Benefit Analysis and Business Case templates
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 1 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 1 · LO1
26

## Slide 28
TOPIC 01 · ACTIVITY DEBRIEF
Debrief — Activity 1: What It Proves
1
The business case answers whether the project should exist; the charter answers whether the team is authorised to act.
2
A scope boundary is incomplete until exclusions are visible—silence is where scope creep starts.
3
Success criteria must be measurable before the plan is built, or control later becomes opinion.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · ACTIVITY DEBRIEF
27

## Slide 29
TOPIC 01 · A1, K1 · LO1
Topic 01 Recap
Decision
A project is temporary, unique and value-seeking; operations are ongoing and repetitive.
Method
Success balances value and outcomes with scope, schedule, cost, quality, resources and risk.
Evidence
A cost–benefit analysis, one-page business case and signed-ready project charter with measurable success criteria, scope boundaries, milestone dates, budget cap, team and kickoff agenda.
Capability
Develop project scope and team to initiate a five-month small project (A1, K1).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 01 · A1, K1 · LO1
28

## Slide 30
TOPIC 02 · A2, K2 · LO2
Develop a Project Plan
Requirements · scope baseline · WBS · network · schedule · budget
02
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · A2, K2 · LO2
29

## Slide 31
TOPIC 02 · CENTRAL IDEA
A plan is a connected model, not a collection of files.
Requirements, WBS, dependencies, dates, resources and money must describe the same work. If one changes, the others must move with it.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · CENTRAL IDEA
30

## Slide 32
TOPIC 02 · CONCEPT MAP
Develop a Project Plan — Core Concepts I
01
The plan integrates subsidiary decisions; separate scope, schedule and cost files are not yet a project plan.
02
Progressive elaboration and rolling-wave planning add detail as uncertainty reduces without abandoning control.
03
Requirements must be testable, prioritised and traceable from need through deliverable and acceptance evidence.
04
The scope statement defines deliverables, exclusions, constraints, assumptions and acceptance criteria.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · CONCEPT MAP
31

## Slide 33
TOPIC 02 · CONCEPT MAP
Develop a Project Plan — Core Concepts II
05
The WBS decomposes deliverables to manageable work packages; the WBS dictionary removes ambiguity.
06
Dependencies create the network; the longest path sets the earliest finish and carries zero or least float.
07
Duration estimates should separate work, waiting, risk and resource availability; use analogous, parametric, bottom-up or three-point methods deliberately.
08
The cost baseline is time-phased; contingency reserve covers known-unknowns while management reserve covers unknown-unknowns.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · CONCEPT MAP
32

## Slide 34
TOPIC 02 · APPLIED FRAMEWORK
The Planning Chain
01
Need
stakeholder source
02
Requirement
testable and prioritised
03
Deliverable
scope statement and WBS
04
Activity
dependency and duration
05
Baseline
schedule and budget
06
Evidence
acceptance and traceability
A broken link creates either orphan scope or unplanned work.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · APPLIED FRAMEWORK
33

## Slide 35
TOPIC 02 · DECISION TOOL
Estimating Methods
Method
Best use
Main risk
Analogous
Early estimate from similar work
False similarity
Parametric
Repeatable unit rates
Bad rate or scale
Bottom-up
Defined work packages
Time and detail cost
Three-point
Uncertain durations/costs
Optimism in inputs
Record the basis of estimate so future variance can be explained.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · DECISION TOOL
34

## Slide 36
TOPIC 02 · APPLIED FRAMEWORK
Critical Path Logic
01
List
activities and milestones
02
Link
predecessors and lags
03
Forward pass
earliest start/finish
04
Backward pass
latest start/finish
05
Float
identify scheduling flexibility
06
Critical path
focus control and compression
Recalculate after every approved change—the critical path can move.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · APPLIED FRAMEWORK
35

## Slide 37
TOPIC 02 · TOOL-BASED PRACTICE
Activity 2 Tool Pack
24 WBS Dictionary
XLSX · editable project tool
24 Work Breakdown Structure
PPTX · editable project tool
25 Requirements Traceability Matrix
XLSX · editable project tool
28 Schedule Network Diagram
XLSX · editable project tool
29 - Gantt Chart - Schedule - Daily Weekly Monthly and Phases
XLSX · editable project tool
32 Project Budget - Planned vs Actual - Weekly and Monthly
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · TOOL-BASED PRACTICE
36

## Slide 38
TOPIC 02 · HANDS-ON ACTIVITY
Build the Integrated Scope, Schedule and Cost Baseline
ACTIVITY 2 · 120 MIN
THE SITUATION
The sponsor approved the charter with one condition: the three outlets must launch before Lunar New Year trading. You have high-level deliverables but no traceable requirements, work breakdown, dependency logic or time-phased budget. A vendor has proposed a date based only on optimism.
WHAT YOU'LL DO
Translate the charter into testable requirements, a deliverable-oriented WBS and dictionary, then sequence work, estimate duration and cost, calculate the critical path, and publish an integrated baseline.
YOU'LL PRODUCE
A requirements traceability matrix, WBS and dictionary, network diagram with critical path and float, Gantt schedule with milestones, and time-phased S$180,000 cost baseline with contingency reserve.
DONE WHEN
Every requirement traces to acceptance evidence and a WBS deliverable; the network produces a defensible critical path; the Gantt fits the five-month limit; and all scheduled work is funded within S$180,000.
Tool: RTM, WBS, network, Gantt and budget templates
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 2 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 2 · LO2
37

## Slide 39
TOPIC 02 · ACTIVITY DEBRIEF
Debrief — Activity 2: What It Proves
1
A Gantt chart is an output of dependency logic, not a substitute for it.
2
The integrated baseline is only credible when scope, schedule and cost reconcile to the same work packages.
3
Float belongs to the project, not automatically to the activity owner who happens to see it.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · ACTIVITY DEBRIEF
38

## Slide 40
TOPIC 02 · A2, K2 · LO2
Topic 02 Recap
Decision
The plan integrates subsidiary decisions; separate scope, schedule and cost files are not yet a project plan.
Method
The scope statement defines deliverables, exclusions, constraints, assumptions and acceptance criteria.
Evidence
A requirements traceability matrix, WBS and dictionary, network diagram with critical path and float, Gantt schedule with milestones, and time-phased S$180,000 cost baseline with contingency reserve.
Capability
Implement a realistic project plan from the authorised objectives and scope (A2, K2).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 02 · A2, K2 · LO2
39

## Slide 41
TOPIC 03 · A3, K3 · LO3
Apply Methods and Tools to Drive a Project
Quality planning · flow · root cause · Pareto · improvement
03
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · A3, K3 · LO3
40

## Slide 42
TOPIC 03 · CENTRAL IDEA
Use the lightest tool that changes the next decision.
A tool earns its place when it turns uncertain work into visible evidence: flow, cause, variation, priority or ownership.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · CENTRAL IDEA
41

## Slide 43
TOPIC 03 · CONCEPT MAP
Apply Methods and Tools to Drive a Project — Core Concepts I
01
A method defines how work is managed; a tool makes information visible. Choose both for the decision needed.
02
Predictive plans optimise sequence and baseline control; adaptive boards optimise flow and feedback; hybrid combines both intentionally.
03
Quality means conformance to requirements and fitness for use, not luxury or perfection.
04
Prevention and appraisal are usually cheaper than internal and external failure.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · CONCEPT MAP
42

## Slide 44
TOPIC 03 · CONCEPT MAP
Apply Methods and Tools to Drive a Project — Core Concepts II
05
A check sheet captures facts, a control chart detects process behaviour, Pareto prioritises causes, and fishbone plus 5 Whys investigates root cause.
06
Root-cause analysis must end at a process or system cause the team can influence, not blame a person.
07
Visual work management exposes blocked work and excessive WIP before the schedule report does.
08
Continuous improvement closes the loop through a named action, owner, measure and review date.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · CONCEPT MAP
43

## Slide 45
TOPIC 03 · DECISION TOOL
Select the Tool for the Question
Question
Best starting tool
Output
What happened?
Check sheet
Reliable facts
Why might it happen?
Fishbone
Cause families
What is the root?
5 Whys
Actionable chain
Which causes matter most?
Pareto
Vital few
Is the process stable?
Control chart
Common vs special cause
Tools work as a sequence: facts → causes → priority → behaviour → action.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · DECISION TOOL
44

## Slide 46
TOPIC 03 · DECISION TOOL
Cost of Quality
Category
Purpose
Example
Prevention
Stop defects forming
Training and standards
Appraisal
Detect before release
Review and testing
Internal failure
Fix before customer
Rework and retest
External failure
Recover after release
Returns and reputation
Invest upstream where a dollar of prevention avoids many dollars of failure.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · DECISION TOOL
45

## Slide 47
TOPIC 03 · APPLIED FRAMEWORK
Root Cause to Improvement
01
Observe
capture the defect fact
02
Explore
map possible causes
03
Drill
test the causal chain
04
Prioritise
focus the vital few
05
Experiment
owner, measure, date
06
Verify
sustain or adapt
Stopping at a cause without a verified action is analysis theatre.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · APPLIED FRAMEWORK
46

## Slide 48
TOPIC 03 · TOOL-BASED PRACTICE
Activity 3 Tool Pack
35 Check Sheets
XLSX · editable project tool
37 Ishikawa Diagram
XLSX · editable project tool
38 Five Whys
XLSX · editable project tool
36 Pareto Principle Template
XLSX · editable project tool
34 Control Chart
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · TOOL-BASED PRACTICE
47

## Slide 49
TOPIC 03 · HANDS-ON ACTIVITY
Diagnose and Prioritise the Pilot's Quality Failure
ACTIVITY 3 · 75 MIN
THE SITUATION
During outlet testing, only 82% of orders are ready at the promised collection time and pick accuracy has fallen to 94%. The software vendor blames store staff; store staff blame late inventory updates. The sponsor wants action before the team has separated symptoms, causes and normal variation.
WHAT YOU'LL DO
Capture defect facts, map potential causes, drill to an actionable root cause, rank the vital few, interpret process behaviour and commit one measurable improvement action.
YOU'LL PRODUCE
A reconciled check sheet, fishbone diagram, five-level causal chain, Pareto chart, control-chart interpretation and a SMART corrective experiment with owner and review date.
DONE WHEN
The data total reconciles; Pareto reaches 100%; the five-whys chain ends at an actionable cause; the control chart interpretation matches the pattern; and the corrective experiment has an owner, measure and review date.
Tool: Fishbone, Check Sheet, 5 Whys, Pareto and Control Chart
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 3 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 3 · LO3
48

## Slide 50
TOPIC 03 · ACTIVITY DEBRIEF
Debrief — Activity 3: What It Proves
1
Fishbone broadens the search, 5 Whys deepens one chain, and Pareto tells you which chain is worth funding first.
2
A control limit describes process behaviour; it is not the same as a customer specification limit.
3
Improvement becomes project work only when it has capacity, ownership and a verification date.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · ACTIVITY DEBRIEF
49

## Slide 51
TOPIC 03 · A3, K3 · LO3
Topic 03 Recap
Decision
A method defines how work is managed; a tool makes information visible. Choose both for the decision needed.
Method
Prevention and appraisal are usually cheaper than internal and external failure.
Evidence
A reconciled check sheet, fishbone diagram, five-level causal chain, Pareto chart, control-chart interpretation and a SMART corrective experiment with owner and review date.
Capability
Use appropriate methods and tools to drive progress and improve quality (A3, K3).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 03 · A3, K3 · LO3
50

## Slide 52
TOPIC 04 · A4, K4 · LO4
Manage Project Risk
Identify · assess · respond · contingency · monitor
04
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · A4, K4 · LO4
51

## Slide 53
TOPIC 04 · CENTRAL IDEA
Risk management buys options before they become expensive.
The register matters only when it changes funding, sequencing, ownership or contingency before a trigger becomes an issue.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · CENTRAL IDEA
52

## Slide 54
TOPIC 04 · CONCEPT MAP
Manage Project Risk — Core Concepts I
01
Risk is an uncertain event or condition with a positive or negative effect; an issue has already happened.
02
Write risks as cause-event-impact statements so the response targets the cause or reduces the impact.
03
The risk register records owner, probability, impact, exposure, triggers, response, contingency and residual risk.
04
Qualitative analysis prioritises quickly; quantitative analysis estimates the range of outcomes and decision value.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · CONCEPT MAP
53

## Slide 55
TOPIC 04 · CONCEPT MAP
Manage Project Risk — Core Concepts II
05
Threat responses are avoid, mitigate, transfer, accept or escalate; opportunity responses are exploit, enhance, share, accept or escalate.
06
A contingency plan is triggered by an observable threshold and funded from contingency reserve.
07
Decision trees compare expected monetary value; tornado charts reveal which assumptions deserve the most attention.
08
Risk reviews are recurring decisions, not a register created once and archived.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · CONCEPT MAP
54

## Slide 56
TOPIC 04 · APPLIED FRAMEWORK
The Risk Cycle
01
Identify
cause-event-impact
02
Analyse
probability, impact, urgency
03
Plan
owner, response, trigger
04
Fund
contingency and fallback
05
Monitor
review residual and secondary risk
Triggered risk becomes an issue and moves into action management.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · APPLIED FRAMEWORK
55

## Slide 57
TOPIC 04 · DECISION TOOL
Threat Response Choices
Response
What changes
Example
Avoid
Remove the threat source
Change approach
Mitigate
Reduce probability or impact
Prototype early
Transfer
Shift financial consequence
Insurance / contract
Accept
Monitor and prepare
Contingency plan
Escalate
Move beyond authority
Sponsor decision
Acceptance is a decision with monitoring—not forgetting the risk.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · DECISION TOOL
56

## Slide 58
TOPIC 04 · DECISION TOOL
Qualitative vs Quantitative Analysis
Lens
Qualitative
Quantitative
Speed
Fast prioritisation
More data and effort
Output
Relative exposure
Range, EMV or sensitivity
Use
Most project risks
Material decision uncertainty
Caution
Scoring bias
False precision
Use quantitative analysis only where the decision value justifies the work.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · DECISION TOOL
57

## Slide 59
TOPIC 04 · TOOL-BASED PRACTICE
Activity 4 Tool Pack
48 Risk Assessment Matrix Two pages
XLSX · editable project tool
45 Decision Tree Analysis TDIDT
XLSX · editable project tool
49 Tornado Chart - Sensitivity Analysis
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · TOOL-BASED PRACTICE
58

## Slide 60
TOPIC 04 · HANDS-ON ACTIVITY
Build the Risk Register and Fund the Right Responses
ACTIVITY 4 · 75 MIN
THE SITUATION
The pilot has entered build. The POS interface may be delivered late, refrigerated stock counts are unreliable at one outlet, a key trainer is available for only two weeks, and a faster payment option could improve adoption but costs more. The remaining contingency reserve is S$18,000.
WHAT YOU'LL DO
Write cause-event-impact risk statements, score and rank exposure, assign owners and triggers, choose responses, compare alternatives by expected monetary value and allocate the limited contingency reserve.
YOU'LL PRODUCE
A prioritised risk register with owners, triggers, responses, contingency and residual exposure; one decision-tree recommendation; one tornado sensitivity reading; and a reconciled S$18,000 reserve plan.
DONE WHEN
Every priority risk has cause-event-impact wording, an owner, trigger, funded response and residual score; the decision-tree arithmetic reconciles; and the named contingency allocations total no more than S$18,000.
Tool: Risk Matrix, Decision Tree and Tornado templates
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 4 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 4 · LO4
59

## Slide 61
TOPIC 04 · ACTIVITY DEBRIEF
Debrief — Activity 4: What It Proves
1
An owner does not prevent a risk; they watch the trigger and ensure the agreed response is ready.
2
Contingency is not generic padding—it is a funded response to identified uncertainty.
3
Quantitative tools sharpen a decision but do not replace judgement about reputation, safety or compliance.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · ACTIVITY DEBRIEF
60

## Slide 62
TOPIC 04 · A4, K4 · LO4
Topic 04 Recap
Decision
Risk is an uncertain event or condition with a positive or negative effect; an issue has already happened.
Method
Qualitative analysis prioritises quickly; quantitative analysis estimates the range of outcomes and decision value.
Evidence
A prioritised risk register with owners, triggers, responses, contingency and residual exposure; one decision-tree recommendation; one tornado sensitivity reading; and a reconciled S$18,000 reserve plan.
Capability
Identify risks to project success and take proportionate action (A4, K4).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 04 · A4, K4 · LO4
61

## Slide 63
DAY 1 CLOSE
End of Day 1
Save Activities 1–4. Day 2 continues the same project from the approved risk-aware baseline.
Effective Project Management for Small Projects · TGS-2020505545 ·
DAY 1 CLOSE
62

## Slide 64
TOPIC 05 · A5, K5 · LO5
Collaborate with Stakeholders
Identify · analyse · communicate · engage · allocate accountability
05
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · A5, K5 · LO5
63

## Slide 65
TOPIC 05 · CENTRAL IDEA
Stakeholder engagement is part of delivery.
Every unresolved expectation eventually appears as a delay, rejected deliverable, unapproved invoice or uncontrolled change.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · CENTRAL IDEA
64

## Slide 66
TOPIC 05 · CONCEPT MAP
Collaborate with Stakeholders — Core Concepts I
01
A stakeholder can affect, be affected by, or perceive themselves to be affected by the project.
02
The stakeholder register captures interest, influence, expectations, impact, communication needs and engagement strategy.
03
Power-interest mapping guides attention; the salience model adds legitimacy and urgency.
04
The engagement assessment matrix compares current and desired states so the gap becomes actionable.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · CONCEPT MAP
65

## Slide 67
TOPIC 05 · CONCEPT MAP
Collaborate with Stakeholders — Core Concepts II
05
RACI clarifies who is Responsible, Accountable, Consulted and Informed; every deliverable needs one clear Accountable owner.
06
Communication planning matches audience, message, channel, frequency, owner and feedback route.
07
Engagement is two-way sense-making and decision participation, not one-way broadcasting.
08
Escalation should state the decision needed, options, impact of delay and recommendation.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · CONCEPT MAP
66

## Slide 68
TOPIC 05 · APPLIED FRAMEWORK
Stakeholder Analysis to Engagement
01
Identify
who affects or is affected
02
Analyse
interest, influence, impact
03
Prioritise
power-interest and salience
04
Plan
message, channel, frequency
05
Engage
two-way decisions
06
Monitor
current vs desired state
A stakeholder register is useful only when it changes an engagement action.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · APPLIED FRAMEWORK
67

## Slide 69
TOPIC 05 · DECISION TOOL
RACI Diagnostic
Pattern
Meaning
Correction
No A
Nobody owns the outcome
Assign one accountable owner
Multiple A
Competing decision rights
Choose one and define escalation
No R
No one performs the work
Assign delivery responsibility
Too many C
Decision gridlock
Consult only for needed input
Everyone I
Broadcast without purpose
Tailor information needs
Use deliverables and decisions as rows; vague verbs create vague accountability.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · DECISION TOOL
68

## Slide 70
TOPIC 05 · DECISION TOOL
Communication vs Engagement
Dimension
Communication
Engagement
Direction
Often one-way
Two-way
Purpose
Share information
Shape decisions and commitment
Evidence
Message delivered
Feedback changed the work
Risk
Noise and overload
Unresolved expectations
The channel matters less than whether the stakeholder can influence the decision in time.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · DECISION TOOL
69

## Slide 71
TOPIC 05 · TOOL-BASED PRACTICE
Activity 5 Tool Pack
42 Stakeholder Impact Over Influence Matrix
XLSX · editable project tool
43 Salience Chart
PPTX · editable project tool
39 RACI Template
XLSX · editable project tool
41 Stakeholder Engagement Assessment Matrix
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · TOOL-BASED PRACTICE
70

## Slide 72
TOPIC 05 · HANDS-ON ACTIVITY
Align Stakeholders with a Map, RACI and Engagement Plan
ACTIVITY 5 · 75 MIN
THE SITUATION
Two weeks before outlet testing, the POS vendor and operations manager each believe the other owns interface acceptance. Store managers receive conflicting instructions, Finance has not approved the payment milestone, and a high-influence outlet supervisor is quietly resisting the pilot.
WHAT YOU'LL DO
Identify and analyse stakeholders, prioritise engagement, remove duplicate or missing accountability, and define a two-way communication rhythm tied to upcoming decisions.
YOU'LL PRODUCE
A stakeholder register and power-interest map, salience reading, validated RACI matrix, current-to-desired engagement assessment, communication plan and one evidence-based escalation brief.
DONE WHEN
All material stakeholders are analysed; every critical deliverable has exactly one Accountable owner and at least one Responsible party; engagement gaps have two-way actions; and the escalation asks for a clear decision.
Tool: Stakeholder Map, Salience, RACI and Engagement Assessment
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 5 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 5 · LO5
71

## Slide 73
TOPIC 05 · ACTIVITY DEBRIEF
Debrief — Activity 5: What It Proves
1
Most collaboration failures are decision-right failures before they become communication failures.
2
RACI clarifies accountability; it does not replace the conversation needed to gain commitment.
3
Stakeholder attention should follow evidence of influence, impact and urgency—not organisational seniority alone.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · ACTIVITY DEBRIEF
72

## Slide 74
TOPIC 05 · A5, K5 · LO5
Topic 05 Recap
Decision
A stakeholder can affect, be affected by, or perceive themselves to be affected by the project.
Method
The engagement assessment matrix compares current and desired states so the gap becomes actionable.
Evidence
A stakeholder register and power-interest map, salience reading, validated RACI matrix, current-to-desired engagement assessment, communication plan and one evidence-based escalation brief.
Capability
Collaborate with internal and external stakeholders directly impacting the project (A5, K5).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 05 · A5, K5 · LO5
73

## Slide 75
TOPIC 06 · A6 · LO6
Deploy Resources
People · budget · equipment · procurement · team performance
06
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · A6 · LO6
74

## Slide 76
TOPIC 06 · CENTRAL IDEA
Capacity—not headcount—delivers the plan.
A seven-person team may have only three usable person-days at the constraint. Resource deployment is the discipline of matching skills and time to the critical work.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · CENTRAL IDEA
75

## Slide 77
TOPIC 06 · CONCEPT MAP
Deploy Resources — Core Concepts I
01
Resource planning links each work package to required skills, quantities, timing and availability.
02
A responsibility assignment is not a capacity plan; availability must be tested against concurrent work.
03
Resource levelling changes dates to resolve over-allocation; smoothing stays within available float.
04
Fast tracking overlaps work and raises risk; crashing adds cost to critical-path work and may not shorten the project.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · CONCEPT MAP
76

## Slide 78
TOPIC 06 · CONCEPT MAP
Deploy Resources — Core Concepts II
05
Procurement decisions consider make-or-buy, lead time, quality, interfaces, contract type and vendor capability.
06
Tuckman's stages require adaptive leadership: direct, coach, support and delegate as the team matures.
07
Conflict is normal; collaborate for important relationships and outcomes, compromise when time is limited, and escalate only with evidence.
08
A resource dashboard should show demand, capacity, variance, bottlenecks and decisions—not just headcount.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · CONCEPT MAP
77

## Slide 79
TOPIC 06 · DECISION TOOL
Four Resource Responses
Option
Schedule effect
Cost / risk effect
Smoothing
Uses float; finish unchanged
Low cost, limited relief
Levelling
May delay finish
Resolves over-allocation
Crashing
Shortens critical work
Adds cost; diminishing returns
Fast tracking
Overlaps sequence
Adds rework and quality risk
Apply compression only to the current critical path and reanalyse after the change.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · DECISION TOOL
78

## Slide 80
TOPIC 06 · APPLIED FRAMEWORK
Capacity Planning
01
Demand
effort by skill and timing
02
Availability
usable person-days
03
Gap
demand minus capacity
04
Constraint
where work queues
05
Option
smooth, level, crash or overlap
06
Decision
update plan and budget
Capacity is time and skill together; headcount alone is not a usable measure.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · APPLIED FRAMEWORK
79

## Slide 81
TOPIC 06 · DECISION TOOL
Team Stage and Leadership
Stage
Team signal
Leader response
Forming
Unclear roles and dependence
Direct and clarify
Storming
Conflict and boundary testing
Coach and facilitate
Norming
Shared standards emerge
Support and reinforce
Performing
Autonomous delivery
Delegate and protect
Adjourning
Transition and loss
Recognise and close
Using one leadership style for every stage creates either dependence or frustration.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · DECISION TOOL
80

## Slide 82
TOPIC 06 · TOOL-BASED PRACTICE
Activity 6 Tool Pack
40 Organisation Chart
PPTX · editable project tool
30 Kanban Board
XLSX · editable project tool
32 Project Budget - Planned vs Actual - Weekly and Monthly
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · TOOL-BASED PRACTICE
81

## Slide 83
TOPIC 06 · HANDS-ON ACTIVITY
Deploy the Team and Resolve the Resource Bottleneck
ACTIVITY 6 · 60 MIN
THE SITUATION
The test plan needs 22 person-days in the next two weeks, but only 16 are available. The same business analyst is assigned to testing, training materials and vendor clarification. The sponsor refuses a launch delay unless the team proves no lower-cost option exists.
WHAT YOU'LL DO
Map roles and capacity, expose over-allocation, compare smoothing, levelling, crashing and fast tracking, re-sequence work on a Kanban board and recommend a resource decision with cost and risk evidence.
YOU'LL PRODUCE
A two-week capacity plan, organisation and escalation map, workload Kanban, evaluated compression options, reconciled budget impact and a sponsor recommendation that removes the bottleneck.
DONE WHEN
The plan reconciles named work with actual capacity; the bottleneck is visible; each optimisation option has schedule, cost and risk consequences; and the chosen deployment fits the approved project constraints.
Tool: Organisation Chart, Kanban Board and Project Budget templates
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 6 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 6 · LO6
82

## Slide 84
TOPIC 06 · ACTIVITY DEBRIEF
Debrief — Activity 6: What It Proves
1
A name in a RACI matrix does not create capacity; capacity must be measured against concurrent demand.
2
Fast tracking buys time with risk, while crashing buys time with cost—neither is automatically a good decision.
3
Manage the constraint first. Adding capacity elsewhere can increase WIP without improving delivery.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · ACTIVITY DEBRIEF
83

## Slide 85
TOPIC 06 · A6 · LO6
Topic 06 Recap
Decision
Resource planning links each work package to required skills, quantities, timing and availability.
Method
Fast tracking overlaps work and raises risk; crashing adds cost to critical-path work and may not shorten the project.
Evidence
A two-week capacity plan, organisation and escalation map, workload Kanban, evaluated compression options, reconciled budget impact and a sponsor recommendation that removes the bottleneck.
Capability
Deploy manpower, budget and relevant resources for efficient completion (A6).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 06 · A6 · LO6
84

## Slide 86
TOPIC 07 · A7 · LO7
Track Project Deliverables and Correct Misalignments
Performance · earned value · change · corrective action · handover · closure
07
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · A7 · LO7
85

## Slide 87
TOPIC 07 · CENTRAL IDEA
Control means deciding early enough to change the outcome.
Variance reporting without forecast, ownership and action is history. Good control protects value and makes closure evidence-ready.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · CENTRAL IDEA
86

## Slide 88
TOPIC 07 · CONCEPT MAP
Track Project Deliverables and Correct Misalignments — Core Concepts I
01
Work performance data becomes information only after comparison with the approved baseline and thresholds.
02
A status report should answer: where are we, why, what is forecast, what decision is needed, and who owns the action.
03
Earned value integrates scope, schedule and cost: PV is planned work, EV is completed value, and AC is actual spend.
04
CPI = EV/AC and SPI = EV/PV; indices below 1.00 signal inefficiency against the baseline.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · CONCEPT MAP
87

## Slide 89
TOPIC 07 · CONCEPT MAP
Track Project Deliverables and Correct Misalignments — Core Concepts II
05
A change request states reason, impact, options and recommendation; approved changes update baselines and traceability.
06
Corrective action brings performance back to plan; preventive action reduces the probability of future variance.
07
Schedule compression is applied to the current critical path and re-analysed after every change.
08
Closure confirms acceptance, transition, contract completion, records, benefits ownership and lessons learned.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · CONCEPT MAP
88

## Slide 90
TOPIC 07 · DECISION TOOL
Earned Value at Week 12
Measure
Formula / value
Meaning
PV
S$108,000
Budgeted work planned
EV
S$90,000
Budgeted value completed
AC
S$105,000
Actual cost incurred
SPI
EV/PV = 0.83
Behind schedule
CPI
EV/AC = 0.86
Cost inefficient
Use the indices with milestones and quality evidence—no single metric tells the whole story.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · DECISION TOOL
89

## Slide 91
TOPIC 07 · APPLIED FRAMEWORK
Integrated Change Control
01
Request
reason and desired outcome
02
Analyse
scope, time, cost, risk, quality
03
Options
approve, reject, defer, trade
04
Decide
authorised owner records rationale
05
Update
baselines and traceability
06
Communicate
owners, stakeholders and vendors
An approved change is unfinished until affected baselines and acceptance evidence are updated.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · APPLIED FRAMEWORK
90

## Slide 92
TOPIC 07 · APPLIED FRAMEWORK
Closeout Gates
01
Accept
deliverables and criteria
02
Transition
operations, support and data
03
Contract
claims, payment and records
04
Learn
causes and reusable actions
05
Benefits
owner and measurement rhythm
06
Close
archive and release resources
Do not close on elapsed time; close on complete evidence and transferred accountability.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · APPLIED FRAMEWORK
91

## Slide 93
TOPIC 07 · TOOL-BASED PRACTICE
Activity 7 Tool Pack
30 Kanban Board
XLSX · editable project tool
31 Burndown Chart
XLSX · editable project tool
32 Project Budget - Planned vs Actual - Weekly and Monthly
XLSX · editable project tool
34 Control Chart
XLSX · editable project tool
44 Agile Retrospective
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · TOOL-BASED PRACTICE
92

## Slide 94
TOPIC 07 · HANDS-ON ACTIVITY
Control the Pilot, Decide the Change and Close the Project
ACTIVITY 7 · 105 MIN
THE SITUATION
At the end of week 12, the baseline planned value is S$108,000. Completed deliverables represent S$90,000 of budgeted value and actual cost is S$105,000. The sponsor also requests loyalty points, estimated at S$24,000 and three weeks. Launch evidence is incomplete and the vendor wants final payment.
WHAT YOU'LL DO
Build an evidence-based status, calculate earned value, forecast outcome, analyse the change request, select corrective action, update approved baselines and complete acceptance, handover and lessons learned.
YOU'LL PRODUCE
A current Kanban and burndown, earned-value analysis with forecasts, status report, change-control decision, corrective-action log, acceptance and handover checklist, lessons learned and closure recommendation.
DONE WHEN
Earned-value calculations and forecast reconcile; the change decision states complete impacts; corrective action has an owner and due date; and closure is supported by acceptance, handover, contract and lessons evidence.
Tool: Kanban, Burndown, Budget, Control Chart and Retrospective templates
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 7 folder.
Effective Project Management for Small Projects · TGS-2020505545 ·
Activity 7 · LO7
93

## Slide 95
TOPIC 07 · ACTIVITY DEBRIEF
Debrief — Activity 7: What It Proves
1
Status reporting is a decision system: variance without forecast and action is only history.
2
An approved change is not complete until every affected baseline and traceability record is updated.
3
Project closure transfers accountability for benefits and operations; it does not merely stop project work.
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · ACTIVITY DEBRIEF
94

## Slide 96
TOPIC 07 · A7 · LO7
Topic 07 Recap
Decision
Work performance data becomes information only after comparison with the approved baseline and thresholds.
Method
CPI = EV/AC and SPI = EV/PV; indices below 1.00 signal inefficiency against the baseline.
Evidence
A current Kanban and burndown, earned-value analysis with forecasts, status report, change-control decision, corrective-action log, acceptance and handover checklist, lessons learned and closure recommendation.
Capability
Track deliverables, monitor cost, schedule and resources, and correct misalignment (A7).
Effective Project Management for Small Projects · TGS-2020505545 ·
TOPIC 07 · A7 · LO7
95

## Slide 97
WRAP-UP
Course Wrap-Up
From authorisation to controlled handover—one connected evidence chain.
Effective Project Management for Small Projects · TGS-2020505545 ·
WRAP-UP
96

## Slide 98
WRAP-UP · END-TO-END
The Small-Project Delivery System
01
Initiate
value, boundaries and authority
02
Plan
scope, sequence, resources and cost
03
Drive
tools, quality and flow
04
Protect
risk and stakeholder alignment
05
Control
variance, change and action
06
Close
acceptance, transition and learning
Every output becomes an input to the next decision.
Effective Project Management for Small Projects · TGS-2020505545 ·
WRAP-UP · END-TO-END
97

## Slide 99
WRAP-UP · WHAT TO REMEMBER
Seven Takeaways
01
Start with value and measurable success, not a list of tasks.
02
Integrate scope, schedule and cost around the same work packages.
03
Choose the tool that changes the next decision and retire unused reporting.
04
Fund risk responses before triggers become issues.
05
Make accountability and stakeholder feedback visible.
06
Plan capacity at the constraint, not by nominal headcount.
07
Control through forecast and action; close through evidence and transfer.
Effective Project Management for Small Projects · TGS-2020505545 ·
WRAP-UP · WHAT TO REMEMBER
98

## Slide 100
ASSESSMENT · READY WHEN
Assessment Readiness Check
Knowledge
Can you explain the small-project elements, plan requirements, tools, risks and stakeholder identification?
Application
Can you produce and interpret the charter, baseline, quality analysis, risk register, RACI, resource plan and control evidence?
Judgement
Can you choose a method, explain the trade-off and recommend a proportionate action?
Evidence
Can you trace each recommendation to the case facts and an approved project artifact?
Effective Project Management for Small Projects · TGS-2020505545 ·
ASSESSMENT · READY WHEN
99

## Slide 101
AFTER THE COURSE
Support
Email
enquiry@tertiaryinfotech.com
Telephone
+65 6100 0613
Website
www.tertiarycourses.com.sg
LMS / TMS
https://lms-tms.tertiaryinfotech.com
Effective Project Management for Small Projects · TGS-2020505545 ·
AFTER THE COURSE
100

## Slide 102
Thank You!
Effective Project Management for Small Projects
TGS-2020505545 · Tertiary Infotech Academy Pte Ltd · UEN: 201200696W