## Slide 1
TRAINER SLIDES · WSQ
Effective Project Management for Small Projects
WSQ Course Code: TGS-2020505545 ·
2 days · 16 training hours
TSC: Project Management · ICT-PMT-3026-1.1
Version v19.0 · 19 August 2026
Tertiary Infotech Academy Pte Ltd · UEN: 201200696W

## Slide 2
COURSE ADMINISTRATION
Welcome & Housekeeping
How the two days work and what evidence you will produce
Effective Project Management for Small Projects · TGS-2020505545
COURSE ADMINISTRATION
1

## Slide 3
ADMIN · ATTENDANCE
Digital Attendance (Mandatory)
AM, PM and Assessment
Complete every required SSG digital attendance scan.
Scan the trainer QR
Use your mobile camera and submit the attendance record.
75% minimum
Attendance eligibility is calculated from the official record.
Assessment required
Complete the assessment and achieve Competent for funding eligibility.
Effective Project Management for Small Projects · TGS-2020505545
ADMIN · ATTENDANCE
2

## Slide 4
ADMIN · FACILITATOR
Your Trainer
Name
Dr Alfred Ang
Role
Course developer and principal trainer, Tertiary Infotech Academy
Experience
20+ years across engineering, analytics, AI and digital transformation
Contact
enquiry@tertiaryinfotech.com · +65 6100 0613
Effective Project Management for Small Projects · TGS-2020505545
ADMIN · FACILITATOR
3

## Slide 5
ADMIN · HOW WE WORK
Ground Rules
Participate
Use the tools, challenge assumptions and explain your decisions.
Respect
One conversation at a time; disagree with evidence, not people.
Be punctual
Activities build on one another; missed work creates downstream gaps.
Keep evidence
Save every completed template for the case study and assessment review.
Effective Project Management for Small Projects · TGS-2020505545
ADMIN · HOW WE WORK
4

## Slide 6
COURSE PORTAL
Login to LMS and Download Course Material
Effective Project Management for Small Projects · TGS-2020505545
ADMIN · HOW WE WORK
4
Log in at lms-tms.tertiaryinfotech.com with your registered email and the OTP sent to your inbox, then open this course to download the slides and Learner Guide.

## Slide 7
COURSE ALIGNMENT
Learning Outcomes — 1 to 4
LO1
Develop project scope and team to initiate the facilitation of a small project
LO2
Develop a realistic project plan based on the agreed project scope
LO3
Utilise appropriate methods and tools to track and drive a project
LO4
Identify, analyse and manage project risks
Effective Project Management for Small Projects · TGS-2020505545
COURSE ALIGNMENT
6

## Slide 8
COURSE ALIGNMENT
Learning Outcomes — 5 to 7
LO5
Collaborate effectively with project stakeholders
LO6
Deploy manpower, budget and other resources for efficient completion
LO7
Track project deliverables and correct misalignments through control and closeout
Effective Project Management for Small Projects · TGS-2020505545
COURSE ALIGNMENT
7

## Slide 9
TSC ALIGNMENT
Skills Framework — Abilities A1 to A4
Code
Ability
Practice
A1
Facilitate execution of small projects that are typically less than six months, with limited budget and interdependencies, and no significant strategic impact
Activities 1–2
A2
Implement realistic project plans based on project objectives and scope
Activities 3–5
A3
Utilise appropriate methods and tools to track and drive progress against plans and timelines
Activities 6 and 10
A4
Identify risks to project success and take appropriate actions to manage them
Activity 7
Every assessed ability has named tool-based evidence across the lifecycle.
Effective Project Management for Small Projects · TGS-2020505545
TSC ALIGNMENT
8

## Slide 10
TSC ALIGNMENT
Skills Framework — Abilities A5 to A7
Code
Ability
Practice
A5
Collaborate effectively with relevant internal and external stakeholders directly impacting the project
Activity 8
A6
Deploy manpower, financial budgets and relevant resources for efficient and effective completion
Activity 9
A7
Track deliverables against schedules, monitor costs, timescales and resources, and take basic corrective actions when misaligned
Activities 11–12
The twelve activities form one connected project evidence trail.
Effective Project Management for Small Projects · TGS-2020505545
TSC ALIGNMENT
9

## Slide 11
TSC ALIGNMENT
Skills Framework — Knowledge
Code
Knowledge
Taught in
K1
Elements of a small project
Topic 1
K2
Requirements of a project plan
Topic 2
K3
Application of appropriate project management methodologies and tools
Topic 3
K4
Project risks
Topic 4
K5
Project stakeholder identification
Topic 5
Knowledge is applied in the activity immediately following its topic.
Effective Project Management for Small Projects · TGS-2020505545
TSC ALIGNMENT
10

## Slide 12
DAY 1 · FROM IDEA TO AN INTEGRATED, RISK-AWARE BASELINE
Lesson Plan — Day 1
Initiate with value
Topic 1 · charter, boundaries, team and kickoff
Plan the work
Topic 2 · requirements, WBS, schedule, critical path and budget
Drive quality and flow
Topic 3 · visual management, root-cause and prioritisation tools
Manage uncertainty
Topic 4 · risk register, responses, contingency and decision analysis
Effective Project Management for Small Projects · TGS-2020505545
DAY 1 · FROM IDEA TO AN INTEGRATED, RISK-AWARE BASELINE
11

## Slide 13
DAY 2 · FROM STAKEHOLDER ALIGNMENT TO CONTROLLED DELIVERY AND CLOSURE
Lesson Plan — Day 2
Engage stakeholders
Topic 5 · mapping, RACI, communication and engagement
Deploy resources
Topic 6 · capacity, optimisation, procurement and team performance
Control and close
Topic 7 · status, earned value, change, corrective action and handover
Assessment
Written Case Study and Oral Questioning, open book
Effective Project Management for Small Projects · TGS-2020505545
DAY 2 · FROM STAKEHOLDER ALIGNMENT TO CONTROLLED DELIVERY AND CLOSURE
12

## Slide 14
SEVEN-TOPIC SYLLABUS FROM v17
Course Outline — Topics 1 to 4
Topic 01 · Initiation of a Project
Small-project fit · value · charter · scope · team · kickoff · A1, K1
Topic 02 · Develop a Project Plan
Requirements · scope baseline · WBS · network · schedule · budget · A2, K2
Topic 03 · Apply Methods and Tools to Drive a Project
Quality planning · flow · root cause · Pareto · improvement · A3, K3
Topic 04 · Manage Project Risk
Identify · assess · respond · contingency · monitor · A4, K4
Effective Project Management for Small Projects · TGS-2020505545
SEVEN-TOPIC SYLLABUS FROM v17
13

## Slide 15
SEVEN-TOPIC SYLLABUS FROM v17
Course Outline — Topics 5 to 7
Topic 05 · Collaborate with Stakeholders
Identify · analyse · communicate · engage · allocate accountability · A5, K5
Topic 06 · Deploy Resources
People · budget · equipment · procurement · team performance · A6
Topic 07 · Track Project Deliverables and Correct Misalignments
Performance · earned value · change · corrective action · handover · closure · A7
Effective Project Management for Small Projects · TGS-2020505545
SEVEN-TOPIC SYLLABUS FROM v17
14

## Slide 16
EDITABLE OFFICE TOOLS · ONE CONNECTED EVIDENCE PACK
The Twelve Tool Packs
Activity 1
Selection & Cost-Benefit — Screen and select the project
Activity 2
Business Case & Charter — Authorise and kick off
Activity 3
Requirements Workshop & RTM — Discover and trace needs
Activity 4
WBS & Dictionary — Build the scope baseline
Activity 5
Network, Gantt & Budget — Integrate schedule and cost
Activity 6
Delivery & Quality Plan — Tailor execution and quality
Activity 7
Risk Decision Tools — Fund risk responses
Activity 8
Stakeholder, RACI & SEAM — Align decisions and engagement
Activity 9
Capacity & Procurement — Deploy resources
Activity 10
Root-Cause Toolchain — Diagnose quality
Activity 11
Status, EVM, Issue & Change — Control performance
Activity 12
Acceptance, Handover & Benefits — Close and transfer
Effective Project Management for Small Projects · TGS-2020505545
EDITABLE OFFICE TOOLS · ONE CONNECTED EVIDENCE PACK
15

## Slide 17
THE RUNNING CASE
One Small Project Runs Through All Twelve Activities
Scope
A three-outlet click-and-collect pilot for HarbourHub Retail.
Time & money
Five months, a S$180,000 cap and a seven-person core team.
Interfaces
Two vendors plus outlet operations, finance, IT and customers.
Success
Launch on date; 120 orders/week; 98% accuracy; 4.2/5 satisfaction; within cap.
Effective Project Management for Small Projects · TGS-2020505545
THE RUNNING CASE
16

## Slide 18
ASSESSMENT · BRIEFING
Briefing for Assessment
Individual work
No discussion once assessment begins.
Open book
Slides, Learner Guide and approved materials only.
Protect the paper
No photographs, recording or unauthorised materials.
Answer with evidence
State the method, decision, rationale and expected result.
Effective Project Management for Small Projects · TGS-2020505545
ASSESSMENT · BRIEFING
17

## Slide 19
ASSESSMENT · WHAT TO EXPECT
Final Assessment
Written Case Study
Written Assessment (Case Study) — apply project management judgement to a small-project scenario.
Oral Questioning
Oral Questioning — explain and justify decisions against the course methods and evidence.
Conditions
Open book: course slides, Learner Guide and approved course materials only.
Competency
A minimum of 75% attendance and a Competent result are required for funding eligibility.
Effective Project Management for Small Projects · TGS-2020505545
ASSESSMENT · WHAT TO EXPECT
18

## Slide 20
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
The Complete Project Lifecycle
01
Initiation
select, justify and authorise
02
Planning
integrate scope, schedule, cost and risk
03
Execution
coordinate people, suppliers, quality and work
04
Monitor & Control
compare, forecast, decide and correct
05
Closure
accept, transition, learn and transfer benefits
The phases overlap in practice; control and engagement operate from authorisation to closure.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
19

## Slide 21
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
Lifecycle Phases and WSQ Topics
Phase
Primary course topics
Evidence produced
Initiation
Topic 1
Selection, business case, charter, kickoff
Planning
Topics 2 and 4
Requirements, baselines, risk responses
Execution
Topics 3, 5 and 6
Work, quality, engagement, resources
Monitoring & Controlling
Topics 3, 4, 5 and 7
Status, forecasts, issues, change, action
Closure
Topic 7
Acceptance, handover, lessons, benefits ownership
The seven-topic syllabus is preserved while the lifecycle makes the end-to-end operating system visible.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
20

## Slide 22
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
What Runs Across Every Phase
Integration
Keep decisions and artefacts consistent.
Stakeholders
Engage before decisions become resistance.
Risk
Refresh uncertainty as facts change.
Quality
Define, assure and control fitness for use.
Resources
Match skills and capacity to priority work.
Governance
Escalate outside agreed tolerances.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
21

## Slide 23
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
Five Phase Gates for a Small Project
01
Select
Is this the right investment?
02
Authorise
Are boundaries and authority clear?
03
Baseline
Is the plan realistic and funded?
04
Release
Is the output accepted and operationally ready?
05
Close
Are obligations complete and benefits owned?
A gate is a decision with evidence and conditions—not a ceremonial meeting.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
22

## Slide 24
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
Tailoring Control to a Small Project
Need
Lean control
Escalate when
Scope
One charter, WBS and RTM
Success criteria or exclusions move
Schedule
Milestones plus critical path
Tolerance or launch date is threatened
Cost
Time-phased budget
Forecast exceeds authority
Risk
Prioritised register
Trigger, exposure or reserve changes materially
Change
One log and named approver
Trade-off crosses a tolerance
Tailoring removes low-value ceremony while preserving decision integrity.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
23

## Slide 25
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
The Connected Evidence Chain
01
Why
selection and business case
02
What
charter, requirements and scope
03
How
schedule, budget, quality and risk
04
Now
status, issues, forecasts and change
05
Done
acceptance, handover and benefits
Each artefact must feed the next decision; isolated templates are administration, not management.
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
24

## Slide 26
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
Twelve Activities, One Project
Initiate
Activities 1–2
Plan
Activities 3–5 and 7
Execute
Activities 6, 8 and 9
Control
Activities 10–11
Close
Activity 12
Effective Project Management for Small Projects · TGS-2020505545
END-TO-END LIFECYCLE · v17 + PMP + AGILE REFERENCES
25

## Slide 27
TOPIC 01 · A1, K1 · LO1
Initiation of a Project
Small-project fit · value · charter · scope · team · kickoff
01
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · A1, K1 · LO1
26

## Slide 28
TOPIC 01 · CENTRAL IDEA
Small does not mean informal.
The smaller the project, the less waste it can absorb. A short charter, sharp boundaries and visible decision rights are the control system—not bureaucracy.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · CENTRAL IDEA
27

## Slide 29
TOPIC 01 · CONCEPT MAP
Initiation of a Project — Core Concepts I
01
A project is temporary, unique and value-seeking; operations are ongoing and repetitive.
02
A small project is normally under six months, has a limited budget and team, few dependencies and no significant strategic impact.
03
The project manager integrates people, decisions and trade-offs; they do not merely maintain a schedule.
04
Success balances value and outcomes with scope, schedule, cost, quality, resources and risk.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · CONCEPT MAP
28

## Slide 30
TOPIC 01 · CONCEPT MAP
Initiation of a Project — Core Concepts II
05
Predictive, adaptive and hybrid approaches are choices driven by uncertainty, not labels of maturity.
06
The business case tests whether the project should exist; the charter authorises it to exist.
07
A useful charter names purpose, measurable success, scope boundaries, milestones, budget, major risks, team and sponsor authority.
08
A kickoff creates one shared picture of why, what, who, how and what happens next.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · CONCEPT MAP
29

## Slide 31
TOPIC 01 · APPLIED FRAMEWORK
From Need to Authorised Work
01
Need
evidence and user consequence
02
Business case
options, value and viability
03
Charter
authority, boundaries and success
04
Kickoff
shared picture and first decisions
Do not plan an unauthorised idea as though it were already a project.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · APPLIED FRAMEWORK
30

## Slide 32
TOPIC 01 · DECISION TOOL
Business Case vs Project Charter
Dimension
Business Case
Project Charter
Core question
Should we invest?
Are we authorised to proceed?
Focus
Options, benefits, costs, risk
Purpose, scope, team, milestones
Owner
Sponsor / business owner
Sponsor with project manager
Decision
Select or reject option
Authorize and delegate
Both are living decision records; neither is a ceremonial form.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · DECISION TOOL
31

## Slide 33
TOPIC 01 · DECISION TOOL
Choosing a Development Approach
Signal
Predictive
Adaptive / Hybrid
Requirements
Stable and testable upfront
Evolving or discovery-heavy
Feedback
Available late or at gates
Available in short cycles
Change cost
High after commitment
Reduced through increments
Governance
Baseline and stage gates
Timeboxes plus control points
Approach follows uncertainty and reversibility—not fashion.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · DECISION TOOL
32

## Slide 34
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Project Work versus Operations
Dimension
Project
Operations
Purpose
Create a unique result
Sustain recurring value
Duration
Temporary
Ongoing
Change
Introduces change
Stabilises and improves work
Closure
Formal endpoint
Continues until redesigned
The same people may do both; the management system changes with the nature of the work.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
33

## Slide 35
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
The Small-Project Qualification Test
Time
Normally less than six months.
Budget
Limited enough for proportionate governance.
Team
Small core team with clear interfaces.
Dependencies
Few and manageable.
Impact
No significant strategic or enterprise-wide effect.
Uncertainty
Can be bounded through short learning cycles.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
34

## Slide 36
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
From Output to Benefits
01
Output
click-and-collect capability
02
Outcome
orders collected predictably
03
Benefit
revenue, satisfaction and efficiency
04
Measure
owner, baseline, target and date
Deliverables are produced by the project; benefits are usually realised with operations.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
35

## Slide 37
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Project Selection Methods
Method
Best for
Watch for
Cost-benefit
Financial viability
Unsupported benefit assumptions
Weighted scoring
Multiple criteria
Biased weights
Payback
Liquidity and speed
Ignores later value
Mandatory driver
Compliance or safety
Treating obligation as optional
Use more than one lens when a small financial difference hides a major operational consequence.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
36

## Slide 38
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Sponsor and Project Manager—Different Accountability
Sponsor
Owns investment, priority and escalation.
Project manager
Integrates delivery and advises decisions.
Business owner
Owns adoption and benefits after handover.
Functional manager
Provides capability and resolves resource conflicts.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
37

## Slide 39
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Business Documents at Initiation
Artefact
Decision supported
Owner
Business case
Invest, hold or reject
Sponsor / business owner
Benefits plan
How value will be measured
Benefits owner
Project charter
Authorise and delegate
Sponsor with PM
Assumptions log
What must be validated
Project manager
Keep documents brief, but never combine ownership so completely that accountability disappears.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
38

## Slide 40
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
A Charter That Can Govern
Purpose
The problem and desired outcome.
Success
Measures, targets and dates.
Boundaries
Deliverables and exclusions.
Authority
Sponsor, PM and tolerances.
Frame
Milestones, budget and constraints.
Exposure
Assumptions, dependencies and high risks.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
39

## Slide 41
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Assumption, Constraint, Dependency or Risk?
Type
Meaning
Example
Assumption
Believed true for planning
Outlet Wi-Fi capacity is sufficient
Constraint
Fixed limitation
S$180,000 ceiling
Dependency
Reliance on other work
POS API access before integration
Risk
Uncertain event and impact
API access may be late
Classify correctly because each item needs a different response.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
40

## Slide 42
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Lightweight Governance with Tolerances
01
Set
scope, time, cost and risk limits
02
Measure
compare current forecast
03
Act
PM decides within authority
04
Escalate
sponsor decides beyond tolerance
Authority without tolerances creates hesitation; tolerances without reporting create surprise.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
41

## Slide 43
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
Kickoff as an Alignment Decision
01
Why
value and success
02
What
scope and exclusions
03
Who
roles and decisions
04
How
method, rhythm and evidence
05
Next
48-hour actions and owners
A good kickoff reveals mismatched assumptions early enough to repair them cheaply.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · REFERENCE-SOURCED DEEP DIVE
42

## Slide 44
TOPIC 01 · TOOL-BASED PRACTICE
Activity 1 Tool Pack
XLSX
02 Cost Benefit Analysis
Editable evidence file
XLSX
01 Small Project Screening and Selection
Editable evidence file
DECISION ENABLED
A completed small-project screen, weighted option scorecard, cost-benefit check and sponsor-ready selection recommendation.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · TOOL-BASED PRACTICE
43

## Slide 45
TOPIC 01 · HANDS-ON ACTIVITY
Screen and Select the HarbourHub Pilot
ACTIVITY 1 · 35 MIN
THE SITUATION
HarbourHub Fresh has three competing improvement ideas: click-and-collect, a loyalty app, and a warehouse automation study. Only one can be funded this quarter. The sponsor needs a transparent selection decision and evidence that the selected work fits the small-project profile.
WHAT YOU'LL DO
Apply the small-project screen, compare options using weighted criteria, test the financial case and document the recommendation, assumptions and rejection reasons.
YOU'LL PRODUCE
A completed small-project screen, weighted option scorecard, cost-benefit check and sponsor-ready selection recommendation.
DONE WHEN
The selected option satisfies every small-project criterion, the weighted score reconciles, the financial downside is visible and the recommendation states a clear gate decision.
Tool: Small Project Screening, Multi-Criteria Selection and Cost-Benefit Analysis
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 1 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 1 · LO1
44

## Slide 46
TOPIC 01 · ACTIVITY DEBRIEF
Debrief — Activity 1: What It Proves
1
Selection prevents the team from efficiently delivering the wrong project.
2
Weights expose priorities; narrative rationale prevents false precision.
3
A selected idea is still not authorised work until the charter gate is passed.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · ACTIVITY DEBRIEF
45

## Slide 47
TOPIC 01 · TOOL-BASED PRACTICE
Activity 2 Tool Pack
DOCX
05 Business Case on a Page
Editable evidence file
XLSX
08 Project Charter Template
Editable evidence file
DECISION ENABLED
A one-page business case, signed-ready charter, assumptions and constraints log, milestone frame, decision tolerances and kickoff action list.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · TOOL-BASED PRACTICE
46

## Slide 48
TOPIC 01 · HANDS-ON ACTIVITY
Authorise the Pilot and Run the Kickoff Gate
ACTIVITY 2 · 45 MIN
THE SITUATION
The click-and-collect pilot has been selected, but Operations, Finance and the two vendors hold different assumptions about success, exclusions and decision authority. The sponsor will authorise delivery only after a concise gate review.
WHAT YOU'LL DO
Convert the selected option into a measurable business case and charter, define boundaries, name decision rights and conduct a short sponsor gate and kickoff.
YOU'LL PRODUCE
A one-page business case, signed-ready charter, assumptions and constraints log, milestone frame, decision tolerances and kickoff action list.
DONE WHEN
The charter names one accountable sponsor, measurable success, explicit exclusions, decision tolerances and an unambiguous authorisation decision within the small-project constraints.
Tool: Business Case on a Page and Project Charter
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 2 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 2 · LO1
47

## Slide 49
TOPIC 01 · ACTIVITY DEBRIEF
Debrief — Activity 2: What It Proves
1
The business case justifies investment; the charter grants authority.
2
Decision tolerances make lightweight governance possible.
3
Kickoff converts signed paper into shared commitments and immediate action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · ACTIVITY DEBRIEF
48

## Slide 50
TOPIC 01 · A1, K1 · LO1
Topic 01 Recap
Decision
A project is temporary, unique and value-seeking; operations are ongoing and repetitive.
Method
Success balances value and outcomes with scope, schedule, cost, quality, resources and risk.
Evidence
A one-page business case, signed-ready charter, assumptions and constraints log, milestone frame, decision tolerances and kickoff action list.
Capability
Define scope, success, authority and team arrangements for an executable small-project start (A1, K1).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 01 · A1, K1 · LO1
49

## Slide 51
TOPIC 02 · A2, K2 · LO2
Develop a Project Plan
Requirements · scope baseline · WBS · network · schedule · budget
02
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · A2, K2 · LO2
50

## Slide 52
TOPIC 02 · CENTRAL IDEA
A plan is a connected model, not a collection of files.
Requirements, WBS, dependencies, dates, resources and money must describe the same work. If one changes, the others must move with it.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · CENTRAL IDEA
51

## Slide 53
TOPIC 02 · CONCEPT MAP
Develop a Project Plan — Core Concepts I
01
The plan integrates subsidiary decisions; separate scope, schedule and cost files are not yet a project plan.
02
Progressive elaboration and rolling-wave planning add detail as uncertainty reduces without abandoning control.
03
Requirements must be testable, prioritised and traceable from need through deliverable and acceptance evidence.
04
The scope statement defines deliverables, exclusions, constraints, assumptions and acceptance criteria.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · CONCEPT MAP
52

## Slide 54
TOPIC 02 · CONCEPT MAP
Develop a Project Plan — Core Concepts II
05
The WBS decomposes deliverables to manageable work packages; the WBS dictionary removes ambiguity.
06
Dependencies create the network; the longest path sets the earliest finish and carries zero or least float.
07
Duration estimates should separate work, waiting, risk and resource availability; use analogous, parametric, bottom-up or three-point methods deliberately.
08
The cost baseline is time-phased; contingency reserve covers known-unknowns while management reserve covers unknown-unknowns.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · CONCEPT MAP
53

## Slide 55
TOPIC 02 · APPLIED FRAMEWORK
The Planning Chain
01
Need
stakeholder source
02
Requirement
testable and prioritised
03
Deliverable
scope statement and WBS
04
Activity
dependency and duration
05
Baseline
schedule and budget
06
Evidence
acceptance and traceability
A broken link creates either orphan scope or unplanned work.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · APPLIED FRAMEWORK
54

## Slide 56
TOPIC 02 · DECISION TOOL
Estimating Methods
Method
Best use
Main risk
Analogous
Early estimate from similar work
False similarity
Parametric
Repeatable unit rates
Bad rate or scale
Bottom-up
Defined work packages
Time and detail cost
Three-point
Uncertain durations/costs
Optimism in inputs
Record the basis of estimate so future variance can be explained.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · DECISION TOOL
55

## Slide 57
TOPIC 02 · APPLIED FRAMEWORK
Critical Path Logic
01
List
activities and milestones
02
Link
predecessors and lags
03
Forward pass
earliest start/finish
04
Backward pass
latest start/finish
05
Float
identify scheduling flexibility
06
Critical path
focus control and compression
Recalculate after every approved change—the critical path can move.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · APPLIED FRAMEWORK
56

## Slide 58
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
The Integrated Project Plan
Scope
What is authorised and accepted.
Schedule
Sequence, duration and milestones.
Cost
Time-phased funding and reserves.
Quality
Measures, assurance and control.
Resources
Skills, capacity and procurement.
Risk & stakeholders
Responses, engagement and governance.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
57

## Slide 59
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Requirements Elicitation
01
Identify
sources and decision roles
02
Gather
interview, observe, workshop
03
Analyse
conflicts, constraints and value
04
Specify
testable requirement
05
Validate
source confirms meaning
Elicitation is discovery and negotiation—not taking an order from one stakeholder.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
58

## Slide 60
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Weak versus Testable Requirements
Weak wording
Testable wording
Evidence
Fast collection
90% ready within 10 minutes
Timestamp sample
Accurate picking
At least 98% line accuracy
Check sheet
Easy to use
New staff completes task after 30-minute training
Observed test
Reliable
99.5% availability in pilot hours
System log
A measure without a method or status date is still ambiguous.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
59

## Slide 61
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Prioritisation Choices
Method
Decision logic
Use when
MoSCoW
Must / Should / Could / Won't
Time-boxed scope
Weighted scoring
Value across criteria
Competing options
Kano
Basic, performance, delight
Customer experience
Trade-off sliders
Relative constraint priority
Governance alignment
Priorities must remain traceable to outcomes, not just stakeholder preference.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
60

## Slide 62
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Traceability from Need to Evidence
01
Outcome
what success changes
02
Requirement
what must be true
03
Deliverable
what is produced
04
Work package
what the team performs
05
Acceptance
how completion is proven
Trace both directions: every need is delivered, and every deliverable has a reason.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
61

## Slide 63
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Scope Statement Essentials
Product scope
Characteristics of the result.
Project scope
Work required to create it.
Exclusions
What is deliberately not included.
Acceptance
Who approves against which criteria.
Constraints
Limits the plan must respect.
Assumptions
Planning beliefs to validate.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
62

## Slide 64
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
WBS Decomposition
01
Start
authorised deliverables
02
Break down
smaller deliverable components
03
Test 100%
all work, no overlap
04
Stop
estimable, assignable, sequenced, accepted
05
Define
dictionary entry
Do not decompose by department when the deliverable crosses departments.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
63

## Slide 65
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
WBS Dictionary—Why It Matters
Field
Decision enabled
Failure prevented
Description
Shared meaning
Different estimates for different work
Owner
Accountability
Unclaimed delivery
Acceptance
Definition of complete
Almost done forever
Dependencies
Sequence
Late discovery
Estimate basis
Confidence and revision
Unexplained padding
The diagram shows structure; the dictionary makes the structure manageable.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
64

## Slide 66
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Dependency Relationships
Type
Logic
Example
Finish-to-start
A finishes before B starts
Configure before integration test
Start-to-start
A starts before B starts
Draft training after testing begins
Finish-to-finish
A finishes before B finishes
Documentation completes with testing
Start-to-finish
Rare transition logic
Old support ends after new starts
Leads and lags change timing; they do not remove the underlying dependency.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
65

## Slide 67
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Critical Path Calculation
01
Forward pass
earliest start and finish
02
Project finish
largest earliest finish
03
Backward pass
latest finish and start
04
Float
late start minus early start
05
Critical path
least-float path
The critical path is the longest-duration route through current logic, not the most important-looking task.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
66

## Slide 68
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Estimating Methods
Method
Strength
Limitation
Analogous
Fast early estimate
Lower detail
Parametric
Repeatable unit logic
Needs valid relationship
Bottom-up
Detailed and accountable
Time-consuming
Three-point
Makes uncertainty visible
Still depends on judgement
Record the basis so the estimate can be challenged and updated without starting over.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
67

## Slide 69
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
Cost Baseline and Reserves
Work-package estimates
Rolled up from authorised scope.
Contingency reserve
Funded responses for identified risk.
Cost baseline
Time-phased performance reference.
Management reserve
Held outside baseline for unknown-unknowns.
Project budget
Cost baseline plus management reserve.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · REFERENCE-SOURCED DEEP DIVE
68

## Slide 70
TOPIC 02 · TOOL-BASED PRACTICE
Activity 3 Tool Pack
XLSX
25 Requirements Traceability Matrix
Editable evidence file
XLSX
03 Requirements Workshop and Stakeholder Register
Editable evidence file
DECISION ENABLED
A stakeholder register, workshop decision log and requirements traceability matrix with priorities, owners, deliverables and measurable acceptance evidence.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · TOOL-BASED PRACTICE
69

## Slide 71
TOPIC 02 · HANDS-ON ACTIVITY
Discover Requirements and Map Acceptance Evidence
ACTIVITY 3 · 35 MIN
THE SITUATION
Outlet supervisors want speed, Finance wants payment control, customers want predictable collection, and the POS vendor wants a stable interface. The charter is approved, but the stated needs are not testable.
WHAT YOU'LL DO
Identify sources, facilitate a structured workshop, convert needs into testable requirements, prioritise with MoSCoW and define acceptance evidence and ownership.
YOU'LL PRODUCE
A stakeholder register, workshop decision log and requirements traceability matrix with priorities, owners, deliverables and measurable acceptance evidence.
DONE WHEN
Every prioritised requirement has a source, rationale, owner, deliverable and testable acceptance method; unresolved conflicts have named decision owners and dates.
Tool: Requirements Workshop, Stakeholder Register and Traceability Matrix
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 3 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 3 · LO2
70

## Slide 72
TOPIC 02 · ACTIVITY DEBRIEF
Debrief — Activity 3: What It Proves
1
A requirement is not complete until acceptance can be observed or measured.
2
Prioritisation is a trade-off decision, not a label applied by the loudest stakeholder.
3
Traceability protects value when scope changes later.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · ACTIVITY DEBRIEF
71

## Slide 73
TOPIC 02 · TOOL-BASED PRACTICE
Activity 4 Tool Pack
PPTX
24 Work Breakdown Structure
Editable evidence file
XLSX
24 WBS Dictionary
Editable evidence file
XLSX
25 Requirements Traceability Matrix
Editable evidence file
DECISION ENABLED
A scope statement, WBS, WBS dictionary and repaired traceability matrix with no missing or duplicated work.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · TOOL-BASED PRACTICE
72

## Slide 74
TOPIC 02 · HANDS-ON ACTIVITY
Build the Scope Baseline with WBS and Dictionary
ACTIVITY 4 · 45 MIN
THE SITUATION
The team has 14 prioritised requirements, but the vendor proposal groups work by department and omits outlet readiness, training and handover. Estimates cannot be trusted until the total scope is visible.
WHAT YOU'LL DO
Create a deliverable-oriented WBS, apply the 100% rule, define work packages in the dictionary and reconcile every requirement and acceptance criterion to scope.
YOU'LL PRODUCE
A scope statement, WBS, WBS dictionary and repaired traceability matrix with no missing or duplicated work.
DONE WHEN
The WBS covers 100% of authorised work without overlap, each work package is manageable and every requirement traces to acceptance-ready scope.
Tool: Work Breakdown Structure, WBS Dictionary and Requirements Traceability Matrix
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 4 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 4 · LO2
73

## Slide 75
TOPIC 02 · ACTIVITY DEBRIEF
Debrief — Activity 4: What It Proves
1
The WBS describes all project work; the schedule describes when that work occurs.
2
Transition and project-management work are real scope even when customers never see them.
3
A strong dictionary prevents different teams from estimating different meanings.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · ACTIVITY DEBRIEF
74

## Slide 76
TOPIC 02 · TOOL-BASED PRACTICE
Activity 5 Tool Pack
XLSX
28 Schedule Network Diagram
Editable evidence file
XLSX
29 - Gantt Chart - Schedule - Daily Weekly Monthly and Phases
Editable evidence file
XLSX
32 Project Budget - Planned vs Actual - Weekly and Monthly
Editable evidence file
DECISION ENABLED
A network with forward/backward passes, critical path, Gantt milestones, basis of estimates and a time-phased cost baseline plus contingency within the authorised ceiling.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · TOOL-BASED PRACTICE
75

## Slide 77
TOPIC 02 · HANDS-ON ACTIVITY
Develop the Integrated Schedule and Cost Baseline
ACTIVITY 5 · 55 MIN
THE SITUATION
The launch must precede Lunar New Year trading. The vendor has proposed a date without dependency logic, resource calendars or reserves. Finance requires a time-phased baseline within S$180,000.
WHAT YOU'LL DO
Sequence work packages, calculate the critical path and float, estimate duration and cost using explicit methods, set milestones and reconcile schedule, budget and reserve.
YOU'LL PRODUCE
A network with forward/backward passes, critical path, Gantt milestones, basis of estimates and a time-phased cost baseline plus contingency within the authorised ceiling.
DONE WHEN
The dependency network calculates correctly, the plan fits the five-month limit, all authorised work is time-phased and funded, and baseline plus contingency stays within S$180,000.
Tool: Network Diagram, Gantt Schedule and Budget versus Actual
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 5 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 5 · LO2
76

## Slide 78
TOPIC 02 · ACTIVITY DEBRIEF
Debrief — Activity 5: What It Proves
1
A Gantt is the presentation of schedule logic, not the logic itself.
2
The critical path can change after every update or approved change.
3
Baseline and forecast must remain separate so variance can be explained.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · ACTIVITY DEBRIEF
77

## Slide 79
TOPIC 02 · A2, K2 · LO2
Topic 02 Recap
Decision
The plan integrates subsidiary decisions; separate scope, schedule and cost files are not yet a project plan.
Method
The scope statement defines deliverables, exclusions, constraints, assumptions and acceptance criteria.
Evidence
A network with forward/backward passes, critical path, Gantt milestones, basis of estimates and a time-phased cost baseline plus contingency within the authorised ceiling.
Capability
Sequence, estimate and fund the authorised scope as one realistic plan (A2, K2).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 02 · A2, K2 · LO2
78

## Slide 80
TOPIC 03 · A3, K3 · LO3
Apply Methods and Tools to Drive a Project
Quality planning · flow · root cause · Pareto · improvement
03
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · A3, K3 · LO3
79

## Slide 81
TOPIC 03 · CENTRAL IDEA
Use the lightest tool that changes the next decision.
A tool earns its place when it turns uncertain work into visible evidence: flow, cause, variation, priority or ownership.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · CENTRAL IDEA
80

## Slide 82
TOPIC 03 · CONCEPT MAP
Apply Methods and Tools to Drive a Project — Core Concepts I
01
A method defines how work is managed; a tool makes information visible. Choose both for the decision needed.
02
Predictive plans optimise sequence and baseline control; adaptive boards optimise flow and feedback; hybrid combines both intentionally.
03
Quality means conformance to requirements and fitness for use, not luxury or perfection.
04
Prevention and appraisal are usually cheaper than internal and external failure.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · CONCEPT MAP
81

## Slide 83
TOPIC 03 · CONCEPT MAP
Apply Methods and Tools to Drive a Project — Core Concepts II
05
A check sheet captures facts, a control chart detects process behaviour, Pareto prioritises causes, and fishbone plus 5 Whys investigates root cause.
06
Root-cause analysis must end at a process or system cause the team can influence, not blame a person.
07
Visual work management exposes blocked work and excessive WIP before the schedule report does.
08
Continuous improvement closes the loop through a named action, owner, measure and review date.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · CONCEPT MAP
82

## Slide 84
TOPIC 03 · DECISION TOOL
Select the Tool for the Question
Question
Best starting tool
Output
What happened?
Check sheet
Reliable facts
Why might it happen?
Fishbone
Cause families
What is the root?
5 Whys
Actionable chain
Which causes matter most?
Pareto
Vital few
Is the process stable?
Control chart
Common vs special cause
Tools work as a sequence: facts → causes → priority → behaviour → action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · DECISION TOOL
83

## Slide 85
TOPIC 03 · DECISION TOOL
Cost of Quality
Category
Purpose
Example
Prevention
Stop defects forming
Training and standards
Appraisal
Detect before release
Review and testing
Internal failure
Fix before customer
Rework and retest
External failure
Recover after release
Returns and reputation
Invest upstream where a dollar of prevention avoids many dollars of failure.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · DECISION TOOL
84

## Slide 86
TOPIC 03 · APPLIED FRAMEWORK
Root Cause to Improvement
01
Observe
capture the defect fact
02
Explore
map possible causes
03
Drill
test the causal chain
04
Prioritise
focus the vital few
05
Experiment
owner, measure, date
06
Verify
sustain or adapt
Stopping at a cause without a verified action is analysis theatre.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · APPLIED FRAMEWORK
85

## Slide 87
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Method versus Tool
Element
Purpose
Example
Method
Defines how work is managed
Predictive, Scrum, Kanban, PDCA
Tool
Makes evidence visible
WBS, board, chart, log
Policy
Defines operating rule
WIP limit, acceptance rule
Cadence
Defines review rhythm
Daily review, weekly status
A familiar tool used without a decision rule becomes decoration.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
86

## Slide 88
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Predictive, Adaptive and Hybrid
Signal
Predictive
Adaptive / hybrid
Requirements
Stable and knowable
Evolving or discovery-heavy
Delivery
Larger gated releases
Short usable increments
Change
Controlled against baseline
Expected inside prioritised backlog
Best fit
Low uncertainty, costly rework
Fast feedback, reversible choices
Tailor by deliverable when different parts of one small project carry different uncertainty.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
87

## Slide 89
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Direct and Manage Project Work
01
Authorise
approved plan and work package
02
Coordinate
people, suppliers and interfaces
03
Produce
deliverables and work data
04
Learn
issues, knowledge and requests
05
Update
documents and forecasts
Execution produces both deliverables and information needed for control.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
88

## Slide 90
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
A Lean PMIS for a Small Project
Source of truth
Named location and owner.
Version control
Number, date, author and status.
Decision log
What, who, when and rationale.
Access
Right people, current artefact.
Archive
Superseded records remain traceable.
Security
Sensitive content has proportionate access.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
89

## Slide 91
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Quality Planning, Assurance and Control
Discipline
Question
Evidence
Planning
What quality is required?
Metrics, methods and acceptance
Assurance
Will the process achieve it?
Review, audit, coaching
Control
Does the result conform?
Inspection, tests and charts
Improvement
How will the system change?
Experiment and verification
Inspection finds defects; assurance and improvement reduce the chance of creating them.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
90

## Slide 92
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
HarbourHub Quality-Cost Decision
Option
Near-term effect
Decision signal
Add catalogue-data validation
S$4,000 prevention spend
Reduces rejection and re-pick risk
Test only at pilot launch
Lower spend now
Defects discovered with customers waiting
Accept manual correction
No tooling change
Recurring labour and queue growth
Decision
Fund validation before rollout
Cheaper than repeated external failure
The team chooses prevention because one avoided launch-week failure can repay the control.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
91

## Slide 93
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Quality Tool Sequence
01
Check sheet
capture facts
02
Fishbone
broaden possible causes
03
Five Whys
test one chain
04
Pareto
focus the vital few
05
Control chart
understand behaviour
06
Experiment
verify improvement
Do not jump from anecdote directly to solution.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
92

## Slide 94
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Common Cause versus Special Cause
Signal
Meaning
Response
Stable random variation
System behaviour
Improve the process
Point beyond limits
Potential special cause
Investigate event
Run or trend
Non-random pattern
Test changed condition
Within limits but off specification
Stable but incapable
Redesign process
Control limits come from process data; specification limits come from requirements.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
93

## Slide 95
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Kanban Operating Policies
Visualise
Show status, owner and blockers.
Limit WIP
Stop starting; start finishing.
Manage flow
Watch ageing and bottlenecks.
Make policies explicit
Entry, exit and priority rules.
Feedback
Review at a useful cadence.
Improve
Run small measurable experiments.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
94

## Slide 96
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
PDCA Improvement Loop
01
Plan
problem, cause, hypothesis and measure
02
Do
small controlled change
03
Check
compare evidence with prediction
04
Act
standardise, adapt or stop
Improvement is complete only when the new practice is verified and sustained.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
95

## Slide 97
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
Manage Project Knowledge
Explicit
Documents, data and procedures.
Tacit
Experience and judgement shared through work.
Create
Reviews, experiments and problem solving.
Use
Decision support during delivery.
Transfer
Handover and lessons for future teams.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · REFERENCE-SOURCED DEEP DIVE
96

## Slide 98
TOPIC 03 · TOOL-BASED PRACTICE
Activity 6 Tool Pack
30 Kanban Board
XLSX · editable project tool
35 Check Sheets
XLSX · editable project tool
34 Control Chart
XLSX · editable project tool
06 Delivery Approach and Quality Plan
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · TOOL-BASED PRACTICE
97

## Slide 99
TOPIC 03 · HANDS-ON ACTIVITY
Tailor the Delivery Method and Quality Plan
ACTIVITY 6 · 35 MIN
THE SITUATION
The catalogue and POS interface need predictable milestone control, while the outlet workflow needs rapid testing and feedback. The team must choose a hybrid delivery rhythm and define quality before build begins.
WHAT YOU'LL DO
Assess uncertainty and reversibility, tailor predictive and adaptive controls, define the Definition of Done, quality metrics, review cadence, WIP limits and evidence rules.
YOU'LL PRODUCE
A documented hybrid approach, phase and iteration rhythm, quality management plan, Definition of Done, Kanban policy and measurement plan.
DONE WHEN
The approach matches uncertainty, quality is measurable before work begins, WIP and evidence rules are explicit, and predictive/adaptive controls do not contradict one another.
Tool: Delivery Approach Canvas, Quality Plan and Kanban Board
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 6 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 6 · LO3
98

## Slide 100
TOPIC 03 · ACTIVITY DEBRIEF
Debrief — Activity 6: What It Proves
1
Hybrid is intentional tailoring, not running two incompatible systems in parallel.
2
Quality must be designed into the workflow before it is inspected at the end.
3
A tool earns its place only when it changes a decision or behaviour.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · ACTIVITY DEBRIEF
99

## Slide 101
TOPIC 03 · TOOL-BASED PRACTICE
Activity 10 Tool Pack
35 Check Sheets
XLSX · editable project tool
37 Ishikawa Diagram
XLSX · editable project tool
38 Five Whys
XLSX · editable project tool
36 Pareto Principle Template
XLSX · editable project tool
34 Control Chart
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · TOOL-BASED PRACTICE
100

## Slide 102
TOPIC 03 · HANDS-ON ACTIVITY
Diagnose the Pilot Quality Failure
ACTIVITY 10 · 40 MIN
THE SITUATION
During testing, only 82% of orders are ready on time and pick accuracy is 94%. The vendor blames store staff; store staff blame inventory updates. The sponsor wants action before facts and hypotheses are separated.
WHAT YOU'LL DO
Reconcile defect data, broaden possible causes, test a causal chain, prioritise the vital few, interpret process behaviour and design one measurable corrective experiment.
YOU'LL PRODUCE
A check sheet, fishbone, five-whys chain, Pareto chart, control-chart interpretation and SMART corrective experiment.
DONE WHEN
Data totals reconcile, Pareto reaches 100%, the causal chain is actionable, the control interpretation matches the signal and the experiment has an owner and verification date.
Tool: Check Sheet, Fishbone, Five Whys, Pareto and Control Chart
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 10 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 10 · LO3
101

## Slide 103
TOPIC 03 · ACTIVITY DEBRIEF
Debrief — Activity 10: What It Proves
1
Fishbone broadens, Five Whys deepens and Pareto prioritises.
2
Control limits describe process behaviour; specifications describe customer need.
3
Improvement is project work only when funded, owned and verified.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · ACTIVITY DEBRIEF
102

## Slide 104
TOPIC 03 · A3, K3 · LO3
Topic 03 Recap
Decision
A method defines how work is managed; a tool makes information visible. Choose both for the decision needed.
Method
Prevention and appraisal are usually cheaper than internal and external failure.
Evidence
A check sheet, fishbone, five-whys chain, Pareto chart, control-chart interpretation and SMART corrective experiment.
Capability
Use evidence and root-cause tools to select a controlled corrective experiment (A3, K3).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 03 · A3, K3 · LO3
103

## Slide 105
TOPIC 04 · A4, K4 · LO4
Manage Project Risk
Identify · assess · respond · contingency · monitor
04
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · A4, K4 · LO4
104

## Slide 106
TOPIC 04 · CENTRAL IDEA
Risk management buys options before they become expensive.
The register matters only when it changes funding, sequencing, ownership or contingency before a trigger becomes an issue.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · CENTRAL IDEA
105

## Slide 107
TOPIC 04 · CONCEPT MAP
Manage Project Risk — Core Concepts I
01
Risk is an uncertain event or condition with a positive or negative effect; an issue has already happened.
02
Write risks as cause-event-impact statements so the response targets the cause or reduces the impact.
03
The risk register records owner, probability, impact, exposure, triggers, response, contingency and residual risk.
04
Qualitative analysis prioritises quickly; quantitative analysis estimates the range of outcomes and decision value.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · CONCEPT MAP
106

## Slide 108
TOPIC 04 · CONCEPT MAP
Manage Project Risk — Core Concepts II
05
Threat responses are avoid, mitigate, transfer, accept or escalate; opportunity responses are exploit, enhance, share, accept or escalate.
06
A contingency plan is triggered by an observable threshold and funded from contingency reserve.
07
Decision trees compare expected monetary value; tornado charts reveal which assumptions deserve the most attention.
08
Risk reviews are recurring decisions, not a register created once and archived.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · CONCEPT MAP
107

## Slide 109
TOPIC 04 · APPLIED FRAMEWORK
The Risk Cycle
01
Identify
cause-event-impact
02
Analyse
probability, impact, urgency
03
Plan
owner, response, trigger
04
Fund
contingency and fallback
05
Monitor
review residual and secondary risk
Triggered risk becomes an issue and moves into action management.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · APPLIED FRAMEWORK
108

## Slide 110
TOPIC 04 · DECISION TOOL
Threat Response Choices
Response
What changes
Example
Avoid
Remove the threat source
Change approach
Mitigate
Reduce probability or impact
Prototype early
Transfer
Shift financial consequence
Insurance / contract
Accept
Monitor and prepare
Contingency plan
Escalate
Move beyond authority
Sponsor decision
Acceptance is a decision with monitoring—not forgetting the risk.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · DECISION TOOL
109

## Slide 111
TOPIC 04 · DECISION TOOL
Qualitative vs Quantitative Analysis
Lens
Qualitative
Quantitative
Speed
Fast prioritisation
More data and effort
Output
Relative exposure
Range, EMV or sensitivity
Use
Most project risks
Material decision uncertainty
Caution
Scoring bias
False precision
Use quantitative analysis only where the decision value justifies the work.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · DECISION TOOL
110

## Slide 112
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Risk, Issue and Assumption
Item
Time orientation
Management action
Risk
May happen
Owner, trigger and response
Issue
Has happened
Contain, resolve and escalate
Assumption
Believed true
Validate by a date
Constraint
Known limit
Plan within or change formally
A triggered risk becomes an issue; its response owner moves from readiness to action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
111

## Slide 113
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
The Risk Management Cycle
01
Plan
scales, thresholds and roles
02
Identify
threats and opportunities
03
Analyse
priority and decision value
04
Respond
action, owner, trigger and reserve
05
Monitor
residual, secondary and emerging risk
Risk management repeats whenever scope, schedule, suppliers or the environment change.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
112

## Slide 114
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Risk Breakdown Structure
Technical
Design, interface, data and quality.
External
Regulation, market, weather and supplier.
Organisational
Priority, funding, skills and governance.
Project management
Estimate, dependency, communication and scope.
Opportunity
Faster adoption, reuse, cost saving and capability.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
113

## Slide 115
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Writing an Actionable Risk
01
Cause
because inventory data refresh is delayed
02
Event
stock availability may be wrong
03
Impact
orders may be rejected or re-picked
04
Response
reduce cause or impact
05
Trigger
refresh latency exceeds threshold
Cause-event-impact wording prevents vague risks such as 'vendor risk'.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
114

## Slide 116
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Qualitative Risk Factors
Factor
Question
Use
Probability
How likely?
Exposure priority
Impact
How severe?
Tolerance and reserve
Urgency
How soon must we act?
Response timing
Proximity
How soon may it occur?
Monitoring cadence
Dormancy
How long before impact appears?
Early detection
Two risks with the same score may require different action timing.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
115

## Slide 117
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
HarbourHub Threat-Response Workshop
Named threat
Chosen response
Owned action and trigger
Inventory feed is late
Mitigate
IT lead adds latency alert; trigger >15 minutes
Vendor misses integration date
Transfer + mitigate
Milestone clause plus weekly interface test
Outlet rejects new process
Mitigate
Ops lead pilots job aid and observes first 20 orders
Cyber approval exceeds tolerance
Escalate
Sponsor decides scope trade by gate date
Residual launch disruption
Accept actively
Fund two-day floor support contingency
Each response is specific enough to schedule, fund, monitor and verify.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
116

## Slide 118
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Opportunity Response Strategies
Strategy
Intent
Example
Exploit
Ensure opportunity occurs
Assign best resources
Enhance
Increase probability or benefit
Accelerate pilot learning
Share
Partner for capability
Revenue-sharing supplier
Accept
Take benefit if it occurs
No proactive spend
Escalate
Move to programme or strategy
Enterprise reuse
Positive uncertainty deserves ownership and deliberate action too.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
117

## Slide 119
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Response Architecture
01
Preventive
act before trigger
02
Trigger
observable threshold
03
Contingency
act when triggered
04
Fallback
act if contingency fails
05
Residual
remaining exposure
06
Secondary
new risk from response
A response is not operational until timing, ownership and funding are explicit.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
118

## Slide 120
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Decision Tree and Sensitivity
Tool
Question answered
Caution
Decision tree
Which option has better expected value?
Average value can hide tail consequences
Tornado chart
Which assumption drives outcome most?
Range quality determines insight
Probability-impact matrix
What needs attention first?
Ordinal scores are not precise money
Use more analysis only when the decision value exceeds the analysis effort.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
119

## Slide 121
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
Risk Review Agenda
Triggered
Promote to issue and execute response.
Changed
Re-score probability, impact and timing.
New
Add emerging and secondary risk.
Obsolete
Close with rationale.
Reserve
Reconcile use and remaining exposure.
Escalation
Decide beyond tolerance.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · REFERENCE-SOURCED DEEP DIVE
120

## Slide 122
TOPIC 04 · TOOL-BASED PRACTICE
Activity 7 Tool Pack
XLSX
48 Risk Assessment Matrix Two pages
Editable evidence file
XLSX
45 Decision Tree Analysis TDIDT
Editable evidence file
XLSX
49 Tornado Chart - Sensitivity Analysis
Editable evidence file
DECISION ENABLED
A prioritised risk register, response and trigger plan, EMV recommendation, tornado sensitivity reading and reconciled S$18,000 contingency allocation.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · TOOL-BASED PRACTICE
121

## Slide 123
TOPIC 04 · HANDS-ON ACTIVITY
Build the Risk Register and Fund Responses
ACTIVITY 7 · 45 MIN
THE SITUATION
The POS interface may be late, refrigerated stock counts are unreliable, a key trainer has a short availability window and a faster payment option could improve adoption. Contingency reserve is S$18,000.
WHAT YOU'LL DO
Write cause-event-impact risks, rank exposure, assign owners and triggers, choose responses, compare alternatives using EMV and sensitivity, and allocate contingency.
YOU'LL PRODUCE
A prioritised risk register, response and trigger plan, EMV recommendation, tornado sensitivity reading and reconciled S$18,000 contingency allocation.
DONE WHEN
Priority risks have owners, triggers and funded responses; the EMV and sensitivity logic reconcile; contingency is allocated to named uncertainty and residual risk remains visible.
Tool: Risk Matrix, Decision Tree and Tornado Analysis
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 7 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 7 · LO4
122

## Slide 124
TOPIC 04 · ACTIVITY DEBRIEF
Debrief — Activity 7: What It Proves
1
Risk management creates options before triggers become expensive issues.
2
Quantitative analysis sharpens material decisions but does not replace judgement.
3
Acceptance means informed monitoring and contingency, not forgetting the risk.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · ACTIVITY DEBRIEF
123

## Slide 125
TOPIC 04 · A4, K4 · LO4
Topic 04 Recap
Decision
Risk is an uncertain event or condition with a positive or negative effect; an issue has already happened.
Method
Qualitative analysis prioritises quickly; quantitative analysis estimates the range of outcomes and decision value.
Evidence
A prioritised risk register, response and trigger plan, EMV recommendation, tornado sensitivity reading and reconciled S$18,000 contingency allocation.
Capability
Identify, analyse and manage uncertainty with proportionate, funded action (A4, K4).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 04 · A4, K4 · LO4
124

## Slide 126
DAY 1 CLOSE
End of Day 1
Save Activities 1–7. Day 2 continues the same project from the approved risk-aware baseline.
Effective Project Management for Small Projects · TGS-2020505545
DAY 1 CLOSE
125

## Slide 127
TOPIC 05 · A5, K5 · LO5
Collaborate with Stakeholders
Identify · analyse · communicate · engage · allocate accountability
05
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · A5, K5 · LO5
126

## Slide 128
TOPIC 05 · CENTRAL IDEA
Stakeholder engagement is part of delivery.
Every unresolved expectation eventually appears as a delay, rejected deliverable, unapproved invoice or uncontrolled change.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · CENTRAL IDEA
127

## Slide 129
TOPIC 05 · CONCEPT MAP
Collaborate with Stakeholders — Core Concepts I
01
A stakeholder can affect, be affected by, or perceive themselves to be affected by the project.
02
The stakeholder register captures interest, influence, expectations, impact, communication needs and engagement strategy.
03
Power-interest mapping guides attention; the salience model adds legitimacy and urgency.
04
The engagement assessment matrix compares current and desired states so the gap becomes actionable.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · CONCEPT MAP
128

## Slide 130
TOPIC 05 · CONCEPT MAP
Collaborate with Stakeholders — Core Concepts II
05
RACI clarifies who is Responsible, Accountable, Consulted and Informed; every deliverable needs one clear Accountable owner.
06
Communication planning matches audience, message, channel, frequency, owner and feedback route.
07
Engagement is two-way sense-making and decision participation, not one-way broadcasting.
08
Escalation should state the decision needed, options, impact of delay and recommendation.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · CONCEPT MAP
129

## Slide 131
TOPIC 05 · APPLIED FRAMEWORK
Stakeholder Analysis to Engagement
01
Identify
who affects or is affected
02
Analyse
interest, influence, impact
03
Prioritise
power-interest and salience
04
Plan
message, channel, frequency
05
Engage
two-way decisions
06
Monitor
current vs desired state
A stakeholder register is useful only when it changes an engagement action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · APPLIED FRAMEWORK
130

## Slide 132
TOPIC 05 · DECISION TOOL
RACI Diagnostic
Pattern
Meaning
Correction
No A
Nobody owns the outcome
Assign one accountable owner
Multiple A
Competing decision rights
Choose one and define escalation
No R
No one performs the work
Assign delivery responsibility
Too many C
Decision gridlock
Consult only for needed input
Everyone I
Broadcast without purpose
Tailor information needs
Use deliverables and decisions as rows; vague verbs create vague accountability.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · DECISION TOOL
131

## Slide 133
TOPIC 05 · DECISION TOOL
Communication vs Engagement
Dimension
Communication
Engagement
Direction
Often one-way
Two-way
Purpose
Share information
Shape decisions and commitment
Evidence
Message delivered
Feedback changed the work
Risk
Noise and overload
Unresolved expectations
The channel matters less than whether the stakeholder can influence the decision in time.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · DECISION TOOL
132

## Slide 134
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
The Stakeholder Engagement Cycle
01
Identify
who affects or is affected
02
Analyse
interest, influence, impact and expectations
03
Plan
desired state and decision participation
04
Engage
communicate, listen and negotiate
05
Monitor
feedback, sentiment and changed influence
Stakeholder identification is continuous because project decisions change who is affected.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
133

## Slide 135
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Stakeholder Register Fields
Identity
Role, organisation and relationship.
Interest
What outcome matters.
Influence
Formal and informal ability to affect work.
Impact
How the project changes their work.
Expectations
Definition of success and concern.
Strategy
Engagement action and owner.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
134

## Slide 136
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Stakeholder Mapping Lenses
Lens
Dimensions
Best use
Power-interest
Authority and attention
Management strategy
Impact-influence
Effect and ability to act
Change and adoption
Power-influence
Authority and active influence
Governance
Stakeholder cube
Three dimensions
Complex populations
Salience
Power, legitimacy, urgency
Competing claims
A map is a hypothesis to guide action, not a permanent label.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
135

## Slide 137
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Seven Salience Classes
Dormant
Power only.
Discretionary
Legitimacy only.
Demanding
Urgency only.
Dominant
Power and legitimacy.
Dangerous
Power and urgency.
Dependent
Legitimacy and urgency.
Definitive
Power, legitimacy and urgency.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
136

## Slide 138
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Directions of Influence
Direction
Typical stakeholders
Leadership move
Upward
Sponsor and executives
Decision brief and escalation
Downward
Team and specialists
Clarity, coaching and feedback
Sideward
Peers and functional managers
Negotiation and coordination
Outward
Customers, vendors, regulators
Expectation and interface management
Influence without authority depends on evidence, trust and a clear decision request.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
137

## Slide 139
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Communication Model
01
Encode
sender frames meaning
02
Transmit
channel carries message
03
Decode
receiver interprets
04
Feedback
understanding is tested
05
Noise
language, culture, timing and medium interfere
Delivery is not communication success; shared understanding is.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
138

## Slide 140
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Communication Methods
Method
Best use
Risk
Interactive
Decision and ambiguity
Time and facilitation
Push
Targeted distribution
Receipt is not understanding
Pull
Large reference set
Stakeholder may not retrieve it
Visual radiator
Shared current state
Stale information destroys trust
Choose channel based on urgency, complexity, sensitivity and need for feedback.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
139

## Slide 141
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Stakeholder Engagement Levels
Level
Signal
Management aim
Unaware
Does not know project
Build awareness
Resistant
Opposes change
Understand concern and involve
Neutral
Neither resists nor supports
Connect to relevant value
Supportive
Helps when asked
Sustain participation
Leading
Actively champions
Enable influence
The gap between current and desired state must become an owned action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
140

## Slide 142
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
HarbourHub RACI Failure Test
Observed row
Failure signal
Repair
Pilot go-live
Sponsor and PM both marked A
Sponsor is sole A; PM remains R
Inventory mapping
Vendor named R with no internal owner
IT lead becomes A; vendor remains R
Outlet job aid
No R assigned
Operations lead owns production
Customer message
Six people marked C
Consult legal and operations only
Benefits review
Everyone marked I
Name finance owner and decision audience
The repaired matrix makes every critical deliverable and decision executable.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
141

## Slide 143
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
Evidence-Based Escalation
01
Decision
what is needed
02
Options
feasible choices
03
Impact
consequence of delay
04
Recommendation
preferred option and why
05
Deadline
latest useful decision time
Escalation transfers a decision, not a problem without analysis.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · REFERENCE-SOURCED DEEP DIVE
142

## Slide 144
TOPIC 05 · TOOL-BASED PRACTICE
Activity 8 Tool Pack
42 Stakeholder Impact Over Influence Matrix
XLSX · editable project tool
43 Salience Chart
PPTX · editable project tool
39 RACI Template
XLSX · editable project tool
41 Stakeholder Engagement Assessment Matrix
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · TOOL-BASED PRACTICE
143

## Slide 145
TOPIC 05 · HANDS-ON ACTIVITY
Align Stakeholders, Accountability and Communications
ACTIVITY 8 · 40 MIN
THE SITUATION
The POS vendor and Operations each believe the other owns interface acceptance. Finance has not approved a payment milestone, store managers receive conflicting instructions and one influential supervisor resists the pilot.
WHAT YOU'LL DO
Map influence and salience, diagnose engagement gaps, clarify RACI, design a two-way communication rhythm and prepare an evidence-based escalation brief.
YOU'LL PRODUCE
A stakeholder map, salience reading, validated RACI, engagement assessment, communication actions and one-minute escalation recommendation.
DONE WHEN
Critical decisions have one Accountable owner, material engagement gaps have two-way actions and the escalation asks the authorised person for a clear, time-bound decision.
Tool: Stakeholder Map, Salience Model, RACI and Engagement Assessment
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 8 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 8 · LO5
144

## Slide 146
TOPIC 05 · ACTIVITY DEBRIEF
Debrief — Activity 8: What It Proves
1
Many communication failures begin as unclear decision rights.
2
Engagement is participation and feedback, not message broadcasting.
3
Attention follows influence, impact and urgency—not title alone.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · ACTIVITY DEBRIEF
145

## Slide 147
TOPIC 05 · A5, K5 · LO5
Topic 05 Recap
Decision
A stakeholder can affect, be affected by, or perceive themselves to be affected by the project.
Method
The engagement assessment matrix compares current and desired states so the gap becomes actionable.
Evidence
A stakeholder map, salience reading, validated RACI, engagement assessment, communication actions and one-minute escalation recommendation.
Capability
Collaborate with stakeholders and clarify decision rights for execution (A5, K5).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 05 · A5, K5 · LO5
146

## Slide 148
TOPIC 06 · A6 · LO6
Deploy Resources
People · budget · equipment · procurement · team performance
06
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · A6 · LO6
147

## Slide 149
TOPIC 06 · CENTRAL IDEA
Capacity—not headcount—delivers the plan.
A seven-person team may have only three usable person-days at the constraint. Resource deployment is the discipline of matching skills and time to the critical work.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · CENTRAL IDEA
148

## Slide 150
TOPIC 06 · CONCEPT MAP
Deploy Resources — Core Concepts I
01
Resource planning links each work package to required skills, quantities, timing and availability.
02
A responsibility assignment is not a capacity plan; availability must be tested against concurrent work.
03
Resource levelling changes dates to resolve over-allocation; smoothing stays within available float.
04
Fast tracking overlaps work and raises risk; crashing adds cost to critical-path work and may not shorten the project.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · CONCEPT MAP
149

## Slide 151
TOPIC 06 · CONCEPT MAP
Deploy Resources — Core Concepts II
05
Procurement decisions consider make-or-buy, lead time, quality, interfaces, contract type and vendor capability.
06
Tuckman's stages require adaptive leadership: direct, coach, support and delegate as the team matures.
07
Conflict is normal; collaborate for important relationships and outcomes, compromise when time is limited, and escalate only with evidence.
08
A resource dashboard should show demand, capacity, variance, bottlenecks and decisions—not just headcount.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · CONCEPT MAP
150

## Slide 152
TOPIC 06 · DECISION TOOL
Four Resource Responses
Option
Schedule effect
Cost / risk effect
Smoothing
Uses float; finish unchanged
Low cost, limited relief
Levelling
May delay finish
Resolves over-allocation
Crashing
Shortens critical work
Adds cost; diminishing returns
Fast tracking
Overlaps sequence
Adds rework and quality risk
Apply compression only to the current critical path and reanalyse after the change.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · DECISION TOOL
151

## Slide 153
TOPIC 06 · APPLIED FRAMEWORK
Capacity Planning
01
Demand
effort by skill and timing
02
Availability
usable person-days
03
Gap
demand minus capacity
04
Constraint
where work queues
05
Option
smooth, level, crash or overlap
06
Decision
update plan and budget
Capacity is time and skill together; headcount alone is not a usable measure.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · APPLIED FRAMEWORK
152

## Slide 154
TOPIC 06 · DECISION TOOL
Team Stage and Leadership
Stage
Team signal
Leader response
Forming
Unclear roles and dependence
Direct and clarify
Storming
Conflict and boundary testing
Coach and facilitate
Norming
Shared standards emerge
Support and reinforce
Performing
Autonomous delivery
Delegate and protect
Adjourning
Transition and loss
Recognise and close
Using one leadership style for every stage creates either dependence or frustration.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · DECISION TOOL
153

## Slide 155
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Resource Management Plan
Identify
People, equipment, facilities and funding.
Estimate
Quantity, skill and timing.
Acquire
Internal assignment or procurement.
Develop
Capability, trust and working agreements.
Manage
Performance, conflict and feedback.
Control
Usage, availability and corrective action.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
154

## Slide 156
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Organisation Structure and PM Authority
Structure
PM authority
Resource pattern
Functional
Low
Functional manager controls
Weak matrix
Limited
Coordinator role
Balanced matrix
Shared
Negotiated authority
Strong matrix
Moderate to high
Dedicated PM authority
Project-oriented
High
Dedicated team
Even a small project needs explicit escalation when formal authority is limited.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
155

## Slide 157
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Role, Authority, Responsibility and Competence
Element
Question
Evidence
Role
What function is performed?
Role description
Authority
What decisions may be made?
Charter and tolerance
Responsibility
What outcome or work is owned?
RACI and work package
Competence
Can the person perform it?
Skill and experience
Assigning work without authority or competence creates hidden dependency.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
156

## Slide 158
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Two-Week Capacity Worked Example
Skill
Demand
Usable capacity / decision
Integration developer
96 hours
64 hours — defer reporting interface
Outlet trainer
40 hours
48 hours — retain buffer
Data analyst
52 hours
32 hours — buy 20 specialist hours
Test lead
60 hours
56 hours — smooth four hours into next week
The constraint is skill-specific usable time, not the team's nominal headcount.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
157

## Slide 159
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Acquire, Develop or Procure
Choice
Use when
Trade-off
Internal assignment
Capability exists
Priority conflict
Develop skill
Need is recurring
Learning time
Contract resource
Short-term specialist gap
Cost and knowledge transfer
Outsource deliverable
Clear result and interface
Control and vendor dependency
Choose the smallest intervention that resolves the critical constraint.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
158

## Slide 160
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Make-or-Buy Decision
Criterion
Make
Buy
Capability
Builds internal skill
Accesses specialist skill
Lead time
Depends on availability
Depends on procurement and onboarding
Control
Direct management
Contract and interface control
Cost
Fixed or opportunity cost
Price plus vendor management
Knowledge
Retained internally
Requires transfer plan
Lowest price is not lowest total project cost when delay and interface risk are included.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
159

## Slide 161
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Contract Type and Risk
Type
Cost risk
Best fit
Firm fixed price
More seller risk
Stable, clear scope
Cost reimbursable
More buyer risk
Uncertain scope with control
Time and materials
Shared / capped
Short-term flexible effort
Incentive arrangement
Shared performance target
Measurable outcome
The contract allocates financial risk; it does not eliminate delivery accountability.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
160

## Slide 162
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
HarbourHub Team-Stage Diagnostic
Observed behaviour
Stage diagnosis
Next leadership move
Vendor and IT dispute interface ownership
Storming
Facilitate roles and decision rule
Outlet champions share one job aid
Norming
Reinforce standard and peer coaching
Test team resolves defects without escalation
Performing
Delegate within tolerance
Pilot staff worry about release
Adjourning
Recognise contribution and confirm transition
Leadership changes with team evidence; it is not a fixed personal style.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
161

## Slide 163
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Conflict Approaches
Approach
When useful
Trade-off
Collaborate
Outcome and relationship both matter
Time and openness
Compromise
Time-limited middle ground
Partial satisfaction
Accommodate
Relationship or learning matters more
Your need deferred
Direct / force
Emergency or authority decision
Commitment risk
Avoid
Low value or cooling period
Issue may persist
Conflict is information; choose the response based on stakes and relationship.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
162

## Slide 164
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
HarbourHub Bottleneck Options
Option tested
Schedule effect
Decision
Smooth outlet training
Uses two days of float
Accept — no milestone impact
Level integration work
Moves launch by one week
Reject unless scope is traded
Crash data validation
Recovers three days for S$3,600
Approve inside reserve
Fast-track testing
May recover four days
Reject — high rework and quality risk
The selected combination protects launch without hiding cost or quality trade-offs.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
163

## Slide 165
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
Team Performance Signals
Delivery
Commitments met with acceptance evidence.
Flow
WIP, blockers and ageing visible.
Quality
Defects and rework trend.
Collaboration
Handoffs, feedback and conflict resolved.
Learning
Capability and knowledge transfer.
Sustainability
Workload remains safe and realistic.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · REFERENCE-SOURCED DEEP DIVE
164

## Slide 166
TOPIC 06 · TOOL-BASED PRACTICE
Activity 9 Tool Pack
40 Organisation Chart
PPTX · editable project tool
30 Kanban Board
XLSX · editable project tool
32 Project Budget - Planned vs Actual - Weekly and Monthly
XLSX · editable project tool
09 Resource Capacity and Procurement Decision
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · TOOL-BASED PRACTICE
165

## Slide 167
TOPIC 06 · HANDS-ON ACTIVITY
Deploy Resources and Resolve the Bottleneck
ACTIVITY 9 · 45 MIN
THE SITUATION
Testing needs 22 person-days in two weeks, but only 16 are available. The business analyst is assigned to testing, training and vendor clarification. The sponsor wants evidence before accepting delay or extra cost.
WHAT YOU'LL DO
Map authority and skills, calculate demand-capacity gaps, test smoothing, levelling, crashing and fast tracking, compare make/buy options and recommend a funded deployment decision.
YOU'LL PRODUCE
An organisation map, capacity heatmap, constraint-aware Kanban, procurement comparison, compression options, budget impact and sponsor recommendation.
DONE WHEN
Capacity reconciles to named work and skills, the bottleneck is explicit, procurement/compression options show complete trade-offs and the chosen deployment remains within authorised constraints.
Tool: Organisation Chart, Resource Capacity, Procurement Decision, Kanban and Budget
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 9 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 9 · LO6
166

## Slide 168
TOPIC 06 · ACTIVITY DEBRIEF
Debrief — Activity 9: What It Proves
1
A RACI assignment does not create capacity.
2
Manage the constraint before adding capacity elsewhere.
3
Crashing buys time with cost; fast tracking buys time with risk.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · ACTIVITY DEBRIEF
167

## Slide 169
TOPIC 06 · A6 · LO6
Topic 06 Recap
Decision
Resource planning links each work package to required skills, quantities, timing and availability.
Method
Fast tracking overlaps work and raises risk; crashing adds cost to critical-path work and may not shorten the project.
Evidence
An organisation map, capacity heatmap, constraint-aware Kanban, procurement comparison, compression options, budget impact and sponsor recommendation.
Capability
Match skills, capacity, procurement and budget to critical work (A6).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 06 · A6 · LO6
168

## Slide 170
TOPIC 07 · A7 · LO7
Track Project Deliverables and Correct Misalignments
Performance · earned value · change · corrective action · handover · closure
07
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · A7 · LO7
169

## Slide 171
TOPIC 07 · CENTRAL IDEA
Control means deciding early enough to change the outcome.
Variance reporting without forecast, ownership and action is history. Good control protects value and makes closure evidence-ready.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · CENTRAL IDEA
170

## Slide 172
TOPIC 07 · CONCEPT MAP
Track Project Deliverables and Correct Misalignments — Core Concepts I
01
Work performance data becomes information only after comparison with the approved baseline and thresholds.
02
A status report should answer: where are we, why, what is forecast, what decision is needed, and who owns the action.
03
Earned value integrates scope, schedule and cost: PV is planned work, EV is completed value, and AC is actual spend.
04
CPI = EV/AC and SPI = EV/PV; indices below 1.00 signal inefficiency against the baseline.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · CONCEPT MAP
171

## Slide 173
TOPIC 07 · CONCEPT MAP
Track Project Deliverables and Correct Misalignments — Core Concepts II
05
A change request states reason, impact, options and recommendation; approved changes update baselines and traceability.
06
Corrective action brings performance back to plan; preventive action reduces the probability of future variance.
07
Schedule compression is applied to the current critical path and re-analysed after every change.
08
Closure confirms acceptance, transition, contract completion, records, benefits ownership and lessons learned.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · CONCEPT MAP
172

## Slide 174
TOPIC 07 · DECISION TOOL
Earned Value at Week 12
Measure
Formula / value
Meaning
PV
S$108,000
Budgeted work planned
EV
S$90,000
Budgeted value completed
AC
S$105,000
Actual cost incurred
SPI
EV/PV = 0.83
Behind schedule
CPI
EV/AC = 0.86
Cost inefficient
Use the indices with milestones and quality evidence—no single metric tells the whole story.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · DECISION TOOL
173

## Slide 175
TOPIC 07 · APPLIED FRAMEWORK
Integrated Change Control
01
Request
reason and desired outcome
02
Analyse
scope, time, cost, risk, quality
03
Options
approve, reject, defer, trade
04
Decide
authorised owner records rationale
05
Update
baselines and traceability
06
Communicate
owners, stakeholders and vendors
An approved change is unfinished until affected baselines and acceptance evidence are updated.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · APPLIED FRAMEWORK
174

## Slide 176
TOPIC 07 · APPLIED FRAMEWORK
Closeout Gates
01
Accept
deliverables and criteria
02
Transition
operations, support and data
03
Contract
claims, payment and records
04
Learn
causes and reusable actions
05
Benefits
owner and measurement rhythm
06
Close
archive and release resources
Do not close on elapsed time; close on complete evidence and transferred accountability.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · APPLIED FRAMEWORK
175

## Slide 177
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
The Monitoring and Control Cycle
01
Collect
work performance data
02
Compare
baseline, threshold and acceptance
03
Analyse
cause and forecast
04
Decide
action, change or escalation
05
Update
owners, plans and records
06
Verify
did action change outcome?
Control is forward-looking: the purpose of variance is to improve the forecast and decision.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
176

## Slide 178
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Data, Information and Reports
Level
Example
Use
Data
7 defects, S$105k actual cost
Raw observation
Information
Defects above threshold, CPI 0.86
Meaning through comparison
Report
Forecast, cause, action and decision
Governance and coordination
A dashboard without interpretation is data display, not project control.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
177

## Slide 179
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
A Decision-Ready Status Report
Where
Current milestone and acceptance state.
Variance
Scope, time, cost, quality and resource.
Why
Cause, not just symptom.
Forecast
Expected finish and cost.
Action
Owner, due date and verification.
Decision
Escalation with options and deadline.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
178

## Slide 180
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Validate Scope versus Control Scope
Process
Question
Evidence
Validate scope
Will the authorised stakeholder accept it?
Accepted deliverable
Control scope
Has authorised scope changed?
Baseline, RTM and change log
Control quality
Does the result conform?
Inspection and test record
Verified quality is not the same as formal customer acceptance.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
179

## Slide 181
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Earned Value Building Blocks
PV
Budgeted value of work planned by status date.
EV
Budgeted value of work actually completed.
AC
Actual cost of completed work.
BAC
Total authorised budget for measured scope.
Status date
The same cut-off for every measure.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
180

## Slide 182
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Variance and Performance Indices
Measure
Formula
Interpretation
SV
EV − PV
Negative means less value completed than planned
CV
EV − AC
Negative means completed value cost more than budgeted
SPI
EV ÷ PV
Below 1.00 means schedule inefficiency
CPI
EV ÷ AC
Below 1.00 means cost inefficiency
Translate every index into operational consequence and required decision.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
181

## Slide 183
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Forecasting with EAC
Situation
Formula
Assumption
Current cost efficiency continues
EAC = BAC ÷ CPI
Past cost performance persists
Remaining work re-estimated
EAC = AC + bottom-up ETC
New detailed forecast is credible
Original variance is one-off
EAC = AC + (BAC − EV)
Future returns to plan
Cost and schedule both constrain
EAC = AC + (BAC − EV)/(CPI × SPI)
Both inefficiencies persist
Forecast choice is a management assumption and must be stated.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
182

## Slide 184
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Issue Management
01
Log
fact, impact and detection date
02
Contain
protect customer or milestone
03
Own
resolution and decision owner
04
Resolve
root cause and action
05
Escalate
outside authority or tolerance
06
Verify
evidence and closure
Do not keep an issue disguised as a risk after it has occurred.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
183

## Slide 185
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Loyalty-Points Change Worked Example
Analysis lens
Finding
Implication
Value
Could lift repeat purchase
Benefit is plausible but unvalidated
Scope and schedule
Adds API and two test cycles
Launch slips nine working days
Cost and resource
S$18,000 plus scarce developer
Exceeds PM tolerance
Risk and quality
New data/privacy interface
Needs security and regression evidence
Decision
Defer to post-pilot release
Protect baseline; retain request and rationale
Useful ideas are not automatically urgent: the sponsor protects the pilot while preserving the option.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
184

## Slide 186
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Three Types of Action
Action
Purpose
Example
Corrective
Bring future performance back to plan
Add test capacity to recover milestone
Preventive
Reduce probability of future variance
Add interface review before integration
Defect repair
Modify non-conforming deliverable
Correct catalogue mapping
Each action needs authority, ownership, due date and verification.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
185

## Slide 187
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Control Across Knowledge Areas
Schedule
Critical path, float and milestone forecast.
Cost
Actuals, earned value and forecast.
Quality
Conformance, variation and corrective action.
Resources
Utilisation, capacity and bottlenecks.
Risk
Triggers, exposure and reserve.
Communication & procurement
Effectiveness, obligations and disputes.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
186

## Slide 188
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
Closure from Acceptance to Benefits
01
Accept
criteria and authorised sign-off
02
Transition
operations, support, data and training
03
Close contracts
claims, invoices, warranties and records
04
Learn
causes and reusable recommendations
05
Transfer benefits
owner, baseline, target and review
06
Close
archive and release resources
The project can close only after unresolved work is completed or formally transferred.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · REFERENCE-SOURCED DEEP DIVE
187

## Slide 189
TOPIC 07 · TOOL-BASED PRACTICE
Activity 11 Tool Pack
31 Burndown Chart
XLSX · editable project tool
32 Project Budget - Planned vs Actual - Weekly and Monthly
XLSX · editable project tool
34 Control Chart
XLSX · editable project tool
11 Integrated Status Change and Issue Log
XLSX · editable project tool
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · TOOL-BASED PRACTICE
188

## Slide 190
TOPIC 07 · HANDS-ON ACTIVITY
Control Performance, Issues and Change
ACTIVITY 11 · 45 MIN
THE SITUATION
At week 12, PV is S$108,000, EV is S$90,000 and AC is S$105,000. The sponsor requests loyalty points for S$24,000 and three weeks while a vendor interface issue threatens acceptance.
WHAT YOU'LL DO
Calculate earned value and forecast, integrate quality and milestone evidence, triage the issue, analyse the change, obtain an authorised decision and define corrective action.
YOU'LL PRODUCE
An integrated status report, EVM calculations and forecast, issue decision, change-impact analysis, decision log, corrective action and updated control records.
DONE WHEN
EVM and forecast reconcile, issue and change records are distinct, the decision is authorised, all affected records are updated and corrective action is measurable.
Tool: Integrated Status, Change and Issue Log, Burndown, Budget and Control Chart
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 11 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 11 · LO7
189

## Slide 191
TOPIC 07 · ACTIVITY DEBRIEF
Debrief — Activity 11: What It Proves
1
Status reporting is a decision system, not a colour-coded history lesson.
2
Change control enables deliberate trade-offs; it does not prevent change.
3
An approved change is incomplete until every affected baseline is updated.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · ACTIVITY DEBRIEF
190

## Slide 192
TOPIC 07 · TOOL-BASED PRACTICE
Activity 12 Tool Pack
XLSX
44 Agile Retrospective
Editable evidence file
XLSX
12 Acceptance Handover Closure and Benefits
Editable evidence file
DECISION ENABLED
Signed acceptance matrix, handover and training evidence, unresolved-item disposition, contract closeout, lessons register, benefits tracker and formal closure recommendation.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · TOOL-BASED PRACTICE
191

## Slide 193
TOPIC 07 · HANDS-ON ACTIVITY
Accept, Handover and Close the Project
ACTIVITY 12 · 35 MIN
THE SITUATION
All three outlets are live, but final payment is requested before complete acceptance evidence, support ownership, training records and unresolved-item decisions are consolidated. Benefits will continue after project closure.
WHAT YOU'LL DO
Validate acceptance, transfer operations and knowledge, resolve contracts and open items, capture lessons and assign post-project benefits measures before recommending closure.
YOU'LL PRODUCE
Signed acceptance matrix, handover and training evidence, unresolved-item disposition, contract closeout, lessons register, benefits tracker and formal closure recommendation.
DONE WHEN
Acceptance is traceable, handover ownership is explicit, open items have formal disposition, contracts and records reconcile, and benefits continue under named operational owners.
Tool: Acceptance, Handover, Closure and Benefits Tracker plus Retrospective
Full procedure, evidence fields and acceptance criteria: Learner Guide and Activity 12 folder.
Effective Project Management for Small Projects · TGS-2020505545
Activity 12 · LO7
192

## Slide 194
TOPIC 07 · ACTIVITY DEBRIEF
Debrief — Activity 12: What It Proves
1
Elapsed time does not close a project; complete evidence and transferred accountability do.
2
Lessons become assets only when future owners can find and use them.
3
Project work ends before benefits measurement ends.
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · ACTIVITY DEBRIEF
193

## Slide 195
TOPIC 07 · A7 · LO7
Topic 07 Recap
Decision
Work performance data becomes information only after comparison with the approved baseline and thresholds.
Method
CPI = EV/AC and SPI = EV/PV; indices below 1.00 signal inefficiency against the baseline.
Evidence
Signed acceptance matrix, handover and training evidence, unresolved-item disposition, contract closeout, lessons register, benefits tracker and formal closure recommendation.
Capability
Close only when deliverables, transition, contracts, records and benefits ownership are evidenced (A7).
Effective Project Management for Small Projects · TGS-2020505545
TOPIC 07 · A7 · LO7
194

## Slide 196
WRAP-UP
Course Wrap-Up
From authorisation to controlled handover—one connected evidence chain.
Effective Project Management for Small Projects · TGS-2020505545
WRAP-UP
195

## Slide 197
WRAP-UP · END-TO-END
The Small-Project Delivery System
01
Initiate
value, boundaries and authority
02
Plan
scope, sequence, resources and cost
03
Drive
tools, quality and flow
04
Protect
risk and stakeholder alignment
05
Control
variance, change and action
06
Close
acceptance, transition and learning
Every output becomes an input to the next decision.
Effective Project Management for Small Projects · TGS-2020505545
WRAP-UP · END-TO-END
196

## Slide 198
WRAP-UP · WHAT TO REMEMBER
Lifecycle Takeaways
01
Start with value and measurable success, not a list of tasks.
02
Integrate scope, schedule and cost around the same work packages.
03
Choose the tool that changes the next decision and retire unused reporting.
04
Fund risk responses before triggers become issues.
05
Make accountability and stakeholder feedback visible.
06
Plan capacity at the constraint, not by nominal headcount.
07
Control through forecast and action; close through evidence and transfer.
Effective Project Management for Small Projects · TGS-2020505545
WRAP-UP · WHAT TO REMEMBER
197

## Slide 199
ASSESSMENT · READY WHEN
Assessment Readiness Check
Knowledge
Can you explain the small-project elements, plan requirements, tools, risks and stakeholder identification?
Application
Can you produce and interpret the charter, baseline, quality analysis, risk register, RACI, resource plan and control evidence?
Judgement
Can you choose a method, explain the trade-off and recommend a proportionate action?
Evidence
Can you trace each recommendation to the case facts and an approved project artifact?
Effective Project Management for Small Projects · TGS-2020505545
ASSESSMENT · READY WHEN
198

## Slide 200
AFTER THE COURSE
Support
Email
enquiry@tertiaryinfotech.com
Telephone
+65 6100 0613
Website
www.tertiarycourses.com.sg
LMS / TMS
https://lms-tms.tertiaryinfotech.com
Effective Project Management for Small Projects · TGS-2020505545
AFTER THE COURSE
199

## Slide 201
Thank You!
Effective Project Management for Small Projects
TGS-2020505545 · Tertiary Infotech Academy Pte Ltd · UEN: 201200696W